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	CFP: Non-Technical Survey and Risk Education in Iraq
	 Standard CFP



‘Call For Proposals’ (CFP)
Project title: Non-Technical Survey and Risk Education in Iraq
Reference No. IRQ/UNMAS/21218/2018/001
Contents of this CFP:

1. This document
1. Annex A – Grant Application Template
1. Annex B – Grant Budget Template
1. Annex C – Reporting Requirements
1. Annex D – Grant Support Agreement (GSA) Template

1. General instructions for proposal submission: 
How to submit?
Interested organisations are requested to submit their proposal in English to the UNMAS Iraq programme, on their organisation’s headed paper and at the email addresses below. The following documents are required to be submitted by the Deadline:
· Annex A – Grant Application Template; and
· Annex B – Grant Budget Template.

The proposal should align with all criteria listed in Paragraph 2 and respond in full to the scope of work as outlined in Paragraph 3. Organisations are requested to follow the formatting guide within the Annexes attached, while adjusting to suit their specific project outlines.
When to submit?
Deadline: 24 April 2018 by 1300h Iraq local time 
Where to submit?
By email to Samee Ullah at sameeullah@unops.org 
Questions?
Please submit questions to Samee Ullah at sameeullah@unops.org  and Fjola Magnusdottir (FjolaMA@unops.org) before 15 April 2018 by 1300h Iraq local time. Any responses to questions will be posted on the UNOPS website by 18 April 2018. 







2. Eligibility criteria as per project agreement

Limitations: 
· Grant applications shall only be accepted from not-for-profit non-governmental organizations (NGOs) - national or international - that are registered by the Directorate of NGOs to operate in Iraq and hold Non-Technical Survey (NTS) and Risk Education (RE) accreditation from the Directorate of Mine Action. Should the registration and accreditation expire during the foreseen grant period, the grantee must make every effort to ensure that the registration and accreditation is extended and must notify UNMAS Iraq minimum two calendar months prior to expiration if the extension is not expected. This will in such case lead to termination of the agreement. If the organization is not accredited, they must show evidence in the proposal that the organization has a partnership with an Iraqi NGO that holds valid registration and relevant accreditation.
· Organizations must have proven experience conducting Non-Technical Survey (NTS) and community-based Risk Education (RE) in conflict/post-conflict environments. 
· Organizations must have proven experience working as an implementing partner to UNOPS or a large institutional donor (e.g., European Union, United States Department of State) in mine action. 
Minimum requirements/qualifications:
· To build the capacity of the local communities where operations are planned, organizations must either work with a local NGO and/or employ local personnel from the relevant Iraqi administered state/district, who will be trained, mentored and supervised to carry out NTS and RE under this grant, all in accordance with International Mine Action Standards (IMAS).
· Gender equality, women’s empowerment, disability and protection must be mainstreamed into the approach.  Specifically the applicant must explain how each of these four key priorities will be addressed. 
· Organizations must have an existing structure and available capacities to provide teams to deliver NTS and RE.
· Applicants are required to demonstrate that they have the programmatic and administrative capacity to be able to meet administrative requirements of the grant.
· Teams must be self-sustaining and have the appropriate security clearances to deploy to the proposed areas for the duration of the grant without direct support from UNMAS Iraq. 
· The organization must have a presence in Baghdad, Iraq in order to participate in the mine action coordination mechanisms with the Directorate of Mine Action, UNMAS Iraq and other liaison as necessary. 
· The organisation must utilize the United Nations ‘Gender Guidelines for Mine Action Programmes’ to ensure gender is incorporated in programme design and implementation

Other critical considerations: 
· One grant will be awarded against this Call for Proposals (CFP) for activities to be completed in all liberated areas previously held by Islamic State of Iraq and the Levant (ISIL) in Iraq (see the annexed map). Given the scale and scope of the project, flexibility is necessary in order to relocate and re-task teams due to access issues, as well as to allow for shifting priorities and needs. 
· The proposal shall not exceed USD 2,000,000 for up to a maximum of 12 months with an anticipated start date of 1 June 2018. Applicants should be aware that actual start dates may vary, and must demonstrate an ability to remain flexible on mobilization as required. 
· UNMAS Iraq require all liberated areas to be surveyed, including areas of Ninewa, Anbar, Kirkuk, Diyala and Salah al-Din governorates. The Grantee must be capable of working in multiple areas concurrently with teams deployed simultaneously to enable the project to finish on time. 
· Any equipment purchases necessary to carry out the activities in this CFP are not to be charged directly in the grant proposal budget. Rather, organizations should procure equipment from their own funds and lease it to UNOPS at a fair rate. All lease costs included in budgets will be carefully considered during the evaluation of grant proposals. 
· Teams will be subjected to regular Quality Assurance evaluations. Inability to meet IMAS may result in termination of the Agreement at any time during the implementation.
· To enable the sustainability of the capacity upon completion of this project; the project must account for trained individuals to continue to do this type of work in their own communities. 
· Iraqi NGOs have the option of submitting a stand-alone proposal, or partnering with another organization through a consortium[footnoteRef:1]. [1:  Sub-agreements are allowed (see Section 9 – General Conditions for Grant Support Agreements) 
] 

· While primary evaluation shall be of the implementing Grantee, the demonstrated capacity of the local partner(s), if relevant, shall also be considered during the evaluations

Desirable qualifications: 
· Demonstrated capacity to engage in grass-roots projects, in a culturally-responsive manner shall be considered particularly desirable. 
· Innovative approach to activities detailed in this CFP shall be considered highly desirable.
· Particularly, innovative approaches to Community-based RE, including the use of new technology and methodologies where appropriate and effective will be considered desirable. 
· Grantees are strongly encouraged to have an in-house Information Management staff member(s) to work specifically with the Directorate of Mine Action (DMA) in this regard and ensure high quality data collection. 

3. Description of scope of work  

Background
The extensive military conflict has had profound and far-reaching consequences on human security in Iraq. The use of complex improvised explosive devices (IEDs) in Iraq is unprecedented, and the Government of Iraq suffered numerous losses from the use of such devices as part of asymmetrical campaigns in recent years and the remains of explosive hazards (EH) in the aftermath of the conflict has compromised the safety and security of civilians and public spaces, such as schools and hospitals. While disaggregated casualty figures are not available, according to casualty figures recorded by the United Nations Assistance Mission for Iraq (UNAMI) in 2017, at least 3,298 civilians were killed and another 4,781 were injured in acts of terrorism, violence and armed conflict in Iraq. The safe removal of EH, including IEDs, is critical to facilitate the safe return of millions of displaced people, as well as to allow the GoI and the international community to undertake critical post-conflict interventions, particularly in areas liberated from ISIL. Equally critical is capacity development support directed towards relevant national structures to ensure continued sustainable national response.
The scale, scope and complexity of the new explosive contamination problem in liberated areas is substantial and beyond the Government’s national response capacity. The nature and extent of contamination requires a comprehensive specialised explosive hazard management response to allow the full complement of recovery, stabilization and development assistance efforts in Iraq to proceed. This entails an effort in which civilian organizations complement the work of the ISF and the police and the UN and partners support and help build capacity. 
Government Priorities
The DMA, in its National Strategic and Executive Plan for Mine Action 2017-2021, outlined its commitment to work towards an Iraq “free from explosive hazard, where everyone lives in a safe environment.”  The Government understands that addressing explosive hazard threats saves lives and enables the provision of humanitarian, stabilization and development support to its population.  
The strategy highlights that DMA aims to “mitigate the risks posed by improvised explosive devices, mines and explosive remnants of war (ERW) contamination and reduce the associated social economic and humanitarian impact resulting from EH contamination” with the aim to be able to survey, mark and render safe 50 per cent of known contamination by 2021. Risk education programmes targeting at-risk communities and liberated areas in Anbar, Ninewa Salah al-Din, Dyala and Kirkuk have been identified as the highest priority for risk education.

Overall Project Objective 

The overall objective of this grant is to support vulnerable people in Iraq affected by the crisis to receive inclusive humanitarian assistance and have greater access to protection services. 

More specifically, the objective of this grant is to produce a collaborative non-technical survey (NTS) of areas that experienced recent military action in the fight against ISIL (since 2014) and provide RE in these locations to inform people on how to report hazards and how to stay safe. This will be undertaken through the employment of local residents of each governorate impacted by the explosive hazards’ contamination and covered as part of this project (see map on page 7). 

The product of this grant, an enhanced database of suspected hazardous areas and the full survey report, will be utilized to support the Government of Iraq, national and international organizations, humanitarian agencies and the UN to plan and implement humanitarian activities. 

This intervention will contribute to following Government of Iraq (GoI) and UN objectives: 
· Directorate of Mine Action “National Strategic and Executive Plan for Mine Action 2017-2021”
· Obligations under the Antipersonnel Mine Ban Convention 
· Obligations under the Convention on Cluster Munitions 
· Objective 1 of the Strategy of the United Nations on Mine Action 2013-18; 
· Protection of civilians mandate under the Global Protection Cluster; and

Expected Results

The ultimate purpose of the intervention relates to employment and empowerment of impacted communities as well as re-instilling confidence in the Government as to the survey of explosive hazards[footnoteRef:2] and provision of RE. The quality of the survey and Risk Education (RE) is paramount to the safety of Iraqis living in affected areas and normalization of communities. The quality of the product and collaboration with Government counterparts is critical to the success of this intervention and ultimately depends on the presence of skilled and experienced managerial and technical personnel as well as relevant and appropriate training. The successful grantee is expected to achieve this through the deployment of: [2:  The term explosive hazard includes landmines, Explosive Remnants of War (ERW) and Improvised Explosive Devices (IED).] 

1. Multiple NTS teams (recruitment of high numbers of personnel will be an advantage) capable of NTS and emergency RE, including mixed gender teams. 
2. Multiple RE teams (recruitment of high numbers of personnel will be an advantage) capable of community-based RE.

Project Outcomes
The successful Grantee is expected to provide the following outcomes:

Job creation, training and skill transfer
· Qualified and competent national staff capable of conducting NTS and delivering RE. 
· Multiple jobs created for Iraqis.

Communities affected by the crisis have greater awareness of reporting mechanisms for explosive hazards 
· Enhanced understanding and confidence of how to access the Government of Iraq reporting systems for suspected explosive hazards.
· A collaborative approach with the local authorities in urban locations or camps to ensure relevant local reporting mechanisms are mainstreamed into RE messages 

Communities and Internally Displaced People (IDPs) know how to behave in the presence of explosive hazards 
· Ensure an innovative and relevant approach to RE in urban populations in liberated areas and associated camps of displaced persons, in collaboration with the Directorate of Mine Action. 

Enhance the quality and quantity of data and information management
· Ensure a collaborative approach with the Directorate of Mine Action to adhere to national standards for data collection and entry into IMSMA. 




Capacity Building of Iraqi NGOs (if relevant): 
· Should an international organization engage with a national NGO, the expectation is for the international not-for-profit to carry out an organizational assessment of the relevant NGO to identify potential areas of development that can be enhanced (for example: governance, management, financial transparency, proposal writing, M&E, reporting, etc.). It is then expected that the international NGO will design a formal (with an assessment requirement) and an informal training schedule which may include attaching staff to the organization on a part-time basis.


Additional grant specifications
Branding and Visibility
· In addition, UNMAS Iraq may require specific branding on products, uniforms, equipment, and activities in compliance with UNMAS and donor requirements. To be discussed and agreed with UNMAS Iraq after signature of the grant agreement but prior to the Grantee purchasing uniforms and other associated items that could be branded. 

Location 
· Relevant staff shall be recruited from and trained from the relevant area of operations in Ninewa, Anbar, Kirkuk, Diyala and Salah al-Din respectively. 

	Map: prioritized governorates for NTS and RE operations
[image: C:\Users\lindsayh\AppData\Local\Microsoft\Windows\Temporary Internet Files\Content.Word\20180129 UNMAS Map.jpg]
	Ninewa, Anbar, Kirkuk, Diyala and Salah al-Din are five prioritized governorates. 

Highlighted in orange - Ninewa governorate
Highlighted in pink - Kirkuk governorate
Highlighted in green - Salah al-Din governorate
Highlighted in purple - Diyala governorate
Highlighted in pale orange - Anbar governorate
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4. Evaluation process
In line with UNOPS evaluation principles of fairness, transparency and integrity, an independent Grant Evaluation and Selection Committee will be responsible for the review of proposals and the Grantee selection. The review is based on the criteria outlined in the ‘Call for Proposals’ (CFP) and includes an assessment of the grant proposal’s formal, technical and financial aspects. 
A two-stage procedure will be utilised in evaluating the grant proposals, with evaluation of the technical component being completed prior to any budget component being considered and compared to market research results from the relevant area where the activity will be conducted. The budget component will be evaluated only for those applicants whose technical component meets the requirements for the CFP.	

The technical component, which has a total possible value of 100 points, will be evaluated using the below criteria.  

	Criteria
	Maximum Score

	Organizational Background, Operational and Financial Capacity to implement the grant activities 
	25

	Objectives, Expected Results and Logical Framework
	25

	Description of Activities / Methodology 
	25

	Timelines / Implementation and Monitoring Plans
	15

	Risks to Successful Implementation
	10

	Maximum Score: Technical Component
	100



Only proposals that have a Technical Component receiving more than 70 points out of the potential 100 points shall be considered for financial evaluation.
Financial proposals will be evaluated following the completion of the technical evaluation. 
A Grant will be awarded to the applicant with the most attractive combination of technical and financial proposals, with a strong focus on the technical proposal, as highlighted in section 2.
UNOPS reserves the right not to award any grants for any reason.


5. UNOPS Grant Support Agreement 

The UNOPS Standard Grant Support Agreement (GSA) containing UNOPS General Conditions for Grant Support Agreements (Annex D of the UNOPS Grant Support Agreement template) is attached. The GSA constitutes an integral part of this CFP as it is mandatory to accept this agreement with its conditions before submitting a proposal.   

Call for Proposals (CFP) Annex A: 
Grant Application template 
Component 1: Organisational Background and Capacity to implement the grant activities 
(max 3 pages)

This section should clearly demonstrate that the proposing organisation has the experience, capacity, and commitment to implement successfully the proposed grant activities. Suggested issues to be covered in this section include:
1. Background of the proposing organisation – Is it a community-based organisation, national or sub-national 
2. NGO, research or training institution, municipal government branch? 
3. Purpose and core activities of the organisation
4. Organisational approach (philosophy), i.e. how does the organisation deliver its projects? 
5. Length of existence and relevant experience
6. Organisational structure, governance and administrative framework: number of paid staff members, managerial and financial capacity 
7. Membership and affiliation to associations or umbrella groupings 
8. Legal status - registration and accreditation of IP or Grantee with government approved authority
9. Specific location(s) of activities
10. Target population group (women, men, girls and boys, number of youth, diverse groups, etc.)
11. Previous experience relevant to the proposed grant activities. Provide past performance of implementing successful NTS and RE projects in fragile in conflict / post-conflict environments in the past 5 years (can be attached as annex, outside page limit for this section). 
12. Provide evidence that the organization is currently registered with the Government of Iraq Directorate of NGO and has valid NTS and RE accreditation from the Directorate of Mine Action (outside this page limit). 
13. Outline the team proposed for the implementation of the intervention by function including the person who will be overall responsible for implementation of the intervention. Describe qualifications and tasks foreseen for each member of management team. Please note that upon allocation of grant support agreement, the applicant must provide the CV of each of the proposed senior team members. 
14. See Appendices 1 – 5 in Section 7 for further elements for evaluating the applicant operational capacity (outside this page limit). 

Component 2: Objectives, Expected Results and Logical Framework (max 8 pages)
This section should contain a clear and specific statement of what the proposal will accomplish. Suggested issues to address include:


Objectives (Maximum 1 page) 
· Describe how the grant will be utilized to contribute to the broader and specific objectives of the intervention 

Expected Results (Maximum 5 pages) 
· Provide a detailed description of outcomes, outputs and activities that will be undertaken to achieve the expected results 
· The specific results that the grant activities will produce. The expected results are the measurable changes which will have occurred by the end as a result of the planned intervention (in view of objectively verifiable indicators) 

Logical Framework (Maximum 2 pages) 
· Indicators must link into overall project objectives
· Propose specific and measurable indicators relating to project performance and impact which can form the basis for monitoring and evaluation. These indicators will be refined, and will form an important part of the grant agreement between the proposing organisation and UNOPS.
[bookmark: _Toc267561837]Component 3: Description of Activities / Methodology (max 5 pages)
This section should describe what will actually be done to produce the expected results and accomplish the proposed objectives. There should be a clear and direct linkage between the activities and the outcomes. The proponent must ensure that the activities are a means to getting the intended outcomes. Note that weakness in this area may be a major reason for failure to receive funding as this is the actual component to be implemented as grant project. 
Activity descriptions should be as specific as necessary, identifying what will be done, who will do it, when it will be done (beginning, duration, completion), and where it will be done. In describing the activities, an indication should be made regarding the organisations and individuals involved in or benefiting from the activity. 
Points below to be included, but not limited to:
The Grantee should outline its understanding of the specific context in the area (Ninewa, Anbar, Kirkuk, Diyala and Salah al-Din governorates), identifying risks and challenges associated with working in this particular environment. 
In this section, the Grantee shall clearly outline the project approach, inclusive of methodologies for survey and information gathering, implementation timelines, logistics, and other operational plans; 
The Grantee should be able to recruit and train multiple teams covering all areas to complete the detailed NTS activities within the stipulated months. It is recommended to keep these teams small and mobile, with minimum security footprint. The Grantee shall outline the number and composition of teams to be deployed, founded on a community-based model with locally recruited and based staff, thereby better facilitating the collection of information on the ground. The Grantee shall further list the composition of posts to be deployed in each team and establish a suitable management structure, which also must be presented.  
The Grantee must select either a local NGO or recruit and employ local personnel that will be trained and form combined NTS and emergency RE teams. In addition, complementary RE teams will be recruited and trained. The training curriculum for the local partner/personnel, inclusive of detailed training approaches and pedagogy, must be included in the proposal. If relevant, the Grantee shall be responsible for facilitating training of the national partner(s) in an appropriate location which shall be presented in the proposal. The proposal shall also include a description of the training to be completed. 
The Grantee shall clearly lay out a capacity building scheme for the national personnel they will employ. 
The Grantee shall have sufficient information management capacity dedicated as required for this grant.
The NTS and RE shall be carried out according to IMAS and Iraqi National Mine Action Standards. 
The Grantee is expected to use current Iraqi DMA survey forms, and RE reporting forms and also produce high quality maps corresponding to each survey. Each week an outcome case study is to be presented to UNMAS Iraq, highlighting work carried out and beneficiaries and outcomes of the survey including photos.
The Grantee shall be responsible for all supporting activities associated with the above, communications equipment, uniforms, training area costs, mentoring costs, coordination, and administration and the security measures of the organization and its staff. 
The Grantee shall be responsible for engaging the Directorate of Mine Action and ensuring adherence to DMA standards and processes. 
Gender equality, women’s empowerment, disability and protection must be mainstreamed into the approach.  Specifically, the grantee must explain how each of these four key priorities will be incorporated into the implementation methodology. 
Component 4: Timelines / Implementation and Monitoring Plans (max 2 pages)

Timeline/Implementation Plan (Maximum 1 page) 
This section may be presented in graphical (table) form and can be attached as an Annex. It should indicate the sequence of all major activities and implementation milestones, including targeted beginning and ending dates for each step. Provide as much detail as necessary. The Implementation Plan should show a logical flow of steps, indicating that all the things that must happen have been carefully thought through from the start to the end of the grant project.

Monitoring Plan (Maximum 1 page)
Should contain an explanation of the plan for monitoring and evaluating the grant project, both during its implementation (formative) and at completion (summative). Suggested key issues to be addressed: are:
· How the performance of the grant activities will be tracked in terms of achievement of the steps and milestones set forth in the Implementation Plan
· How the impact of the project will be assessed in terms of achieving the project's objective/s
· How any mid-course correction and adjustment of the design and plans will be facilitated on the basis of feedback received
· How the participation of community members in the monitoring and evaluation processes will be achieved.
· How UNMAS Iraq/UNOPS will be notified immediately about any predicted or actual deviation from targets, workplan or budget.
Component 5: Risks to Successful Implementation (1 page)
Identify and list any major risk factors that could result in the grant activities not producing the expected results. These should include both internal factors (for example, the technology involved fails to work as projected) and external factors (for example, significant currency fluctuations resulting into changes in the economics of the grant project).
Include in this section also the key assumptions on which the grant activity plan is based on. In this case, the assumptions are mostly related to external factors (for example, government environmental policy remaining stable) which are anticipated in planning, and on which the feasibility of the grant activities depend.
This section should also include mitigation techniques to facilitate completion of the project objective. 

Component 6: Grant Budget Breakdown
The development and management of a realistic budget is an important part of developing and implementing successful grant activities. Careful attention to issues of financial management and integrity will enhance the effectiveness and impact. The following important principles should be kept in mind in preparing a project budget:
· The budget should be realistic. Find out what planned activities will actually cost, and do not assume that you will be able to make do for less.
· The budget should include all costs associated with managing and administering the grant project. In particular, include the cost of monitoring and evaluation.
· Reasonable indirect costs related to administration of the grant are permitted, up to a maximum of 10%.
· Grant funds should be overall spent according to the agreed budget.
· All relevant, financial records should be made available upon request. These may be independently audited, and usually will become public information.
· The budget line items are general categories intended to assist in thinking through where money will be spent. If a planned expenditure does not appear to fit in any of the standard line item categories, list the item under other costs, and state what the money is to be used for.
· It is highly recommended to use excel for your budget submission
· The figures contained in the Budget Sheet should agree with those on the proposal header and text.
· See template attached (Annex B) for the budget submission	

Component 7: Annexes

No page limit

Appendices to Grant Application Template (Annex A) - required
· Appendix 1: Provide past performance of implementing successful NTS and RE projects in fragile in conflict / post-conflict environments in the past 5 years  
· Appendix 2: Provide evidence that the organization is currently registered with the Government of Iraq Directorate of NGO and has valid NTS and RE accreditation from the Directorate of Mine Action  
· Appendix 3: Organization chart of the team and location where the staff members will be based 
· Appendix 4: CV of the person responsible for implementing this intervention (Project Manager) 
· Appendix 5: Proposed salary scale for national staff within the project 



Call for Proposals (CFP) Annex B
Budget Template
A detailed budget (with budget breakdown for expenses totalling above 5,000 USD) is required in an excel format. A template for this budget is provided as an excel supplement in this CFP (Annex B). 



Call for Proposals (CFP) Annex C
Reporting Requirements
All reports must be submitted in English. 
All report templates will be discussed and agreed with UNMAS Iraq programme after signature of the grant agreement. 

C.1 Brief weekly update must be submitted to the UNMAS Iraq Programme in English.
Following items to be covered:
1. Prepare weekly activity plans as required and in line with national mine action requirements, and ensure all activities are reported to the DMA as applicable and the IMSMA. 

2. Provide a weekly update to the UNMAS Iraq Programme with number of beneficiaries with SADD format, disability data, names of locations where distribution are conducted together with a GPS coordinate. 

C.2 Monthly update must be submitted to the UNMAS Iraq Programme in English.
0. The grantee shall be responsible for drafting monthly NTS reports in consultation with UNMAS Iraq Programme. The format of the report will be agreed upon at the start of the project and indicators may change during the life of the project. The report should include: 
· Relevant maps accurately identifying and delineating Suspected Hazardous Areas (SHA) and Confirmed Hazardous Areas (CHA);
· Type, distribution and density of the explosive hazard contamination; 
· The socio-economic impact of explosive hazard contamination including the livelihood situation of communities such as agriculture, industries, trading etc.; 
· The impact on humanitarian and stabilization activities;
· The impact on returning population in re-taken areas;
· Explosive incidents recorded within the defined area;
· Explosive incident survivors encountered;
· RE delivered and number of beneficiaries disaggregated;
· Recommendations; and
· Emergency support required to support humanitarian actions i.e. RE or clearance   

0. Prepare monthly activity plans as required and in line with national mine action requirements, and ensure all activities are reported to the DMA and IMSMA as applicable. 

0. Submit at least one case study report per month including activity photos with captions in a format provided by UNMAS Iraq. Organisations must obtain and submit (along with photos) the written permission of parents and legal guardians for images of boys or girls (under 18) where you can see their faces.

C.3 Ad hoc updates submitted as requested as per Cluster and or GoI requirements

1. Mine action sub-cluster partners should ensure that activities are also reported into the HRP online activity database and to UNMAS Iraq sub-cluster lead.
2. Report all potential threats or other key information that is provided by the beneficiaries or other community members to UNMAS Iraq.

C.4 Final Narrative Report must be in English and in line with the approved proposal:

A final narrative and financial report, along with a summary of monthly achievements will be required following the completion of the project. The reports will highlight any challenges that require the attention of UNMAS Iraq, the national/regional mine action authorities and the mine action sub-cluster. Progress made on the project should be documented with (high resolution) photographs and success stories.
· A final report in the form of a publication of high quality, in color with maps clearly illustrating the explosive hazard contamination, accurate locations and socio-economic impact area by area. 
· The final draft product report is to be presented to DMA, and stakeholders (agreed to by DMA), for feedback before publishing and sharing externally. It is envisioned that at minimum a ½ day workshop may be required in Baghdad.
· The final product publication must be endorsed by the DMA and UNMAS Iraq and may be requested to bear the DMA logo in addition to donor logos. 
· The final product publication must be made available in hard copy and in high quality PDF.  It is recommended to engage a graphic designer if the organization does not hold in-house capacity















Call for Proposals (CFP) Annex D 
Grant Support Agreement

IN SUPPORT OF

[Insert short grant activity or project title ]

GRANTEE NAME:

GRANT NUMBER: …/…/……./…./…


This Grant Support Agreement (hereinafter referred to as “Agreement’) made is between the United Nations Office for Project Services (hereinafter referred to as “UNOPS”) and [insert Grantee’s name and address] (hereinafter referred to as “Grantee”).

WHEREAS UNOPS desires to provide grant support to the Grantee in the context of the implementation of [insert short grant activity or primary project/programme description] (hereinafter referred to as the “Activity”), as more specifically described in Annex A, on the terms and conditions hereinafter set forth, and

WHEREAS the Grantee is ready and willing to accept such funds from UNOPS for the above-mentioned activities on the terms and conditions as herein set forth.

NOW, THEREFORE, the Grantee and UNOPS agree as follows:
1. Agreement Documents

1.1 The following documents attached hereto shall be deemed to form an integral part of this Agreement in the following order of precedence: 

i.  This agreement
ii.  Annex A: Terms of Reference
iii.  Annex B: Grant Budget 
iv.  Annex C: Reporting
v.  Annex D: UNOPS General Conditions for Grant Support Agreements 

1.2 This Agreement and the Annexes attached hereto shall form the entire Agreement between the Grantee and UNOPS, superseding the contents of any other negotiations and/or agreements, whether oral or in writing, pertaining to the subject of this Agreement.

2. Purpose of the Agreement

2.1 The purpose of this Agreement is to provide support for the Activity being [insert short grant activity description] in [insert country] as described in Annex A (the Terms of Reference). None of the funds provided pursuant to this Agreement may be used for any purposes other than those expressly set forth in Annex A.

2.2 Grant support is being provided to the Grantee on the condition that the action is implemented, and the funds are administered by the Grantee, in accordance with this Agreement. 
	
3. Duration of this Agreement

3.1 This Agreement is effective and funds are granted by UNOPS as of [insert start date] or the date of the last signature below, whichever is the later.  

3.2 Funds granted hereunder are available for program expenditures for the estimated period from the effective date specified in clause 3.1 above to [insert end date]. 

4. Role of the Grantee 

4.1	The Grantee shall:
a. Have full responsibility for ensuring that the Activity is implemented in accordance with the Agreement

b. Be responsible, in the event of financial review, audit or evaluation for providing the necessary accounting documents

c. Be responsible for providing all documents and information to UNOPS which may be required under the relevant payment requests

d. Make the arrangements for providing the financial status documentation and financial guarantee, when requested

e. Ensure professional management of the Activity, including performance monitoring and reporting activities.

5. Grant Amount and Payments

5.1 UNOPS hereby grants to the Grantee the total amount of USD [insert US Dollar amount in figures and words] as shown in the Budget in Annex B.

5.2 Payments to the Grantee shall be made in accordance with the following schedule upon the submission by the Grantee of appropriate milestone reports along with payment requests, subject to the Grantee’s continued performance of its obligations under this Agreement:[footnoteRef:3] [3: Any advance payment made under the Agreement totalling more than USD30,000 of the total Grant Amount be conditional on the provision of a justification and subsequent approval by UNOPS. Moreover, following the receipt of such exceptional justification, UNOPS may, at its own discretion, further request the Grantee to submit documentation regarding its financial status together with reasonable cash flow estimates.Any advance payment exceeding USD250, 000 shall be conditional on a financial guarantee of an amount equivalent to the advance payment.] 


[Note: Delete or insert milestones as required, but be sure to include the complete payment schedule with all milestones/payments that cover the entire term of the Grant Support Agreement.]

Milestone 1: [insert US dollar amount in figures and words], upon signature of this Agreement by both parties. 
Milestone 2: [insert US dollar amount in figures and words], upon certification by UNOPS of receipt and acceptance of the first milestone report and interim financial report on the use of Grant funds by [insert date in month-year format].
Milestone 3: [insert US dollar amount in figures and words], upon certification by UNOPS of receipt and acceptance of the second milestone report and interim financial report on the use of Grant funds by[insert date in month-year format].										
Milestone 4: [insert us dollar amount in figures and words], upon certification by UNOPS of receipt and acceptance of the third milestone report and interim financial report on the use of Grant funds by [insert date in month-year format].
[bookmark: OLE_LINK1][bookmark: OLE_LINK2]Milestone…: [insert us dollar amount in figures and words], upon certification by UNOPS of receipt and acceptance of the final milestone summary report and final financial report on the use of Grant funds by [insert date in month-year format].
5.3 Choose one of the following two clause options. Option A deals with the situation where the Grantee has a bank account. Option B deals with the situation where the Grantee has no bank account. Please delete the clause which is not relevant.

Option A: 
All payments to the Grantee shall be in US dollars, and shall be deposited into the Grantee’s bank account in accordance with the ATLAS vendor profile form completed and submitted by the Grantee to UNOPS.
	or
Option B:
All amounts in this Article IV are expressed in US dollars but shall be paid to the Grantee in local currency, calculated by reference to the UN rate of exchange as at the month and year of the payment.  Payment amounts shall be paid in accordance with the payment schedule set out in article 5.2 by cheque to the representative of the Grantee authorized in writing by the Grantee to accept such payment on its behalf. 

5.3.1 The amount of payment of such Grant funds is not subject to any adjustment or revision because of price or currency fluctuations or the actual costs incurred by the Grantee in the performance of the activities under this Agreement.

6. Reporting and Evaluation

6.1 The Grantee shall submit the following milestone reports during the life of this Agreement in the formats provided in Annex C, and in line with above Payment Schedule, (as per clause 5.2):

(a) To UNOPS, financial reports on the use of Grant funds [insert frequency, e.g. six months]; and
(b) To [insert as applicable: UNOPS or funding source/client], milestone narrative reports every [insert frequency]. 

6.2 Within 90 (ninety) calendar days of the end date specified in clause 3.2 above, the Grantee shall submit the following reports in the formats provided in Annex C:

(a) To UNOPS, a final financial report on the use of Grant funds[footnoteRef:4]; and [4:  For total grants above US$ 50,000 a certified final financial report is required.] 

(b) To [insert as applicable: UNOPS or funding source/client], the final narrative milestone summary report.

6.3 Failure to submit the reports specified in clause 5.2 without due cause shall constitute a failure to fulfil a substantial obligation of this Agreement, in accordance with Article 15 of the General Conditions.

The Grantee shall be deemed discharged from its obligation under this Agreement only upon the receipt and acceptance of the reports referred to in clause 5.2 and the return of any unspent funds in accordance with this Agreement. 

7. Special Conditions

7. Paragraph 11 of the General Conditions (Annex D) is replaced in its entirety by the following:

Types of Assets

11.1 	This Agreement may include the use by the Recipient of the following four categories of assets:

1. Category 1: An asset purchased not using funds in this Agreement. For greater clarity, this includes any separately identifiable assets leased to UNOPS for the furtherance of the activities described in this Agreement.
1. Category 2 (Non-expendable): An asset provided by UNOPS or, purchased using funds in this Agreement, which has a value of at least US $1,000 at the time of purchase.
1. Category 3 (Non-expendable): An asset provided by UNOPS or purchased using funds in this Agreement, which has a value under US $1,000 at the time of purchase but is considered an attractive or special item.[footnoteRef:5] [5:  This includes items such as detectors, projectors, satellite phones, computers, cameras, televisions, fax machines, and tape recorders. It also includes items that could pose a security risk if not properly stored or tracked. If the Recipient is unsure whether an asset is considered “attractive” or “special”, the Recipient shall seek advice from UNOPS.] 

1. Category 4 (Expendable): An asset provided by UNOPS or purchased using funds in this Agreement, which is not included in Category 2 or Category 3.

11.2 	All assets falling into Category 1 shall be clearly marked in a manner that allows such assets to be clearly differentiated from assets in Categories 2, 3 and 4. Category 1 assets remain the property of the Recipient at all times.

Use of Assets

11.3 	Assets falling into Categories 1, 2, 3 or 4 shall be used exclusively by the Recipient for the purposes of this Agreement. Breach of this clause shall constitute immediate grounds for the termination of this Agreement.

11.4 	Assets falling into Categories 2, 3 or 4 remain the property of UNOPS at all times but shall remain in the Recipient’s custody. These assets are governed by the following right-of-use conditions:

1. The right-of-use of these assets is revocable by UNOPS at any time. UNOPS may revoke the right-of-use with immediate effect and demand prompt return of any or all asset(s) in a fit condition subject only to normal wear and tear. Any revocability of assets shall trigger an immediate discussion between the parties. 
1. The Recipient shall take out appropriate insurance coverage for the assets (including third-party liability), and UNOPS may at any time request proof of such insurance.
1. The Recipient shall be solely responsible for the asset(s), their conditions and their use, including compliance with regulations or laws for use in the locations indicated above and any third party claims related to such use.
1. The Recipient shall properly operate and maintain the asset(s) and bear all costs associated therewith. The Recipient shall be wholly responsible for the provision of a scheduled maintenance program and shall assume the costs of all spare parts, servicing and maintenance and repairs where necessary. The Recipient shall maintain proof of maintenance, including service records.
1. The Recipient shall provide appropriate personnel to operate the asset(s). Any such personnel shall be duly qualified for operating the asset(s) and be licensed if so required in the territory of operation. The Recipient shall also provide appropriate death and disability insurance for any personnel responsible for operating any of the asset(s). UNOPS undertake no responsibilities whatsoever in respect of life, health, accident, travel or any other insurance coverage of any person operating the asset(s).

Category 2 and 3 Assets: Inventory Management

11.5 	Where the Recipient purchases Category 2 and 3 assets, the following information and supporting documents are required for each purchase:

· Invoice showing the following: cost of asset, freight, insurance, installation, custom clearance, and any other related cost; date of purchase
· Receipt and inspection report
· Import documentation, if applicable
· Registration, if applicable

11.6 	The Recipient shall provide UNOPS with a report of all Category 2 and 3 assets.

11.7 	The Recipient shall be responsible for inventory control in terms of reconciling and resolving any discrepancies between the physical inventory count and the existing inventory records. Information derived from physical inspections shall be reconciled with available records as soon as possible.

11.8 	The Recipient shall perform periodic inventory reconciliation to verify assets against existing inventory reports. The Recipient shall ensure a complete and accurate check of all assets and identify items, if any, that require further investigation or reconciliation.

Disposal or Return of Category 2, 3 and 4 Assets

11.9 	Unless otherwise advised by UNOPS, Category 4 assets shall automatically become the property of the Recipient at the end of the Agreement. The Recipient accepts such assets on an “as is” basis.

11.10 	Within thirty days after the end of the Agreement, the Recipient shall provide UNOPS with a consolidated inventory report. The Recipient may include a request for the future use of any asset in the Report, including donation to the Recipient. Within the next thirty days, UNOPS shall (a) concur with Recipient’s request, if applicable; (b) instruct the Recipient to dispose of the asset in a different manner, as specified by UNOPS; or (c) instruct the Recipient to return the assets to UNOPS’ custody. Prior to any assets being returned to UNOPS, the asset(s) shall be jointly inspected by UNOPS to ensure that they are operational and have been maintained to the satisfaction of UNOPS. The Recipient is required to service and clean any assets prior to its return to UNOPS.

11.11 	Notwithstanding paragraph 11.10 above, the Recipient shall in any case return Category 2 and 3 assets within 90 days of the end of the Agreement.

Loss, Damage and Theft of Category 2, 3 and 4 Assets

11.12 	Within 30 days of the damage, theft or other loss of a Category 2 or 3 asset, the Recipient shall provide UNOPS with a comprehensive report regarding the circumstances. The following documents shall be included in the Recipient’s report, which shall be signed by the Recipient’s Director:

· circumstance of the incident;
· any negligence of personnel involved;
· supportive documentation (i.e. statement from personnel, photos, etc);
· details related to the asset lost (description, quantity, serial number, purchase value);
· police report for the incident or an explanation why the police report cannot be obtained;
· estimated repair or replacement cost.

11.13 	Where the Recipient is unable to provide the documents above due to circumstances beyond its control, it shall inform UNOPS accordingly and propose alternate documentation or information.

11.14 	After becoming aware of damage, theft or other loss of the asset, the Recipient shall use its best efforts to seek recovery under the applicable insurance.

11.15 	Should negligence be established as the cause of the loss or damage to an asset, the greater of the replacement or depreciated value of the asset (plus freight and insurance, as necessary) shall be deducted from Recipient’s final payment or otherwise recovered.

8. Correspondence

8.1 All further correspondence regarding the implementation of this Agreement should be addressed to:

	For UNOPS:

[insert name, address, e-mail, phone]
	For the Grantee:

[insert name, address, e-mail, phone]



8.2 Any notice given by UNOPS or the Grantee shall be sufficient only if in writing and delivered in person, mailed or delivered electronically to the respective addresses specified in article 8.1 above.



IN WITNESS WHEREOF, the undersigned, duly appointed representatives of UNOPS and of the Grantee, have on behalf of UNOPS and the Grantee, respectively, signed the present Agreement on the dates indicated below their respective signatures.

	FOR UNOPS:


____________________________________
[insert name]
[title], [office]

Date (mandatory): 
	FOR THE GRANTEE:


____________________________________
[insert name]
[title]

Date (mandatory):



ANNEX A

TERMS OF REFERENCE:
Description and scope of grant activity/project
ANNEX B
GRANT BUDGET

ANNEX C
REPORTING


D.1 Milestone report / final milestone summary report (narrative) 

D2. Financial report (on the use of grant funds)

D.3 Final financial report (on the use of grant funds)

ANNEX D
GENERAL CONDITIONS FOR GRANT SUPPORT AGREEMENTS

Liability and General Obligations of Grantee
1.1 
The Grantee shall be responsible for complying with any legal obligations incumbent on them.
1.2 
The Grantee shall carry out all activities for which it is responsible under this Agreement with due diligence and efficiency. 
1.3 
UNOPS shall not, under any circumstances or any grounds, be held liable in the event of a claim under the Agreement relating to any damage caused during the Activity’s execution.
1.4 
The Grantees shall make good any damage sustained by UNOPS as a result of the execution or faulty execution of the Activity.
1.5 
Subject to the express terms of this Agreement, it is understood that the Grantee shall have exclusive control over the administration and implementation of this Agreement and that UNOPS shall not interfere in the exercise of such control. However, both the quality of the Grantee’s work and the progress being made toward successfully achieving the goals of such activities shall be subject to review by UNOPS.  If at any time UNOPS is not satisfied with the quality of work or the progress being made toward achieving such goals, UNOPS may in its discretion (i) withhold payment of funds until in its opinion the situation has been corrected; or (ii) declare this Agreement terminated by written notice to the Grantee; and/or (iii) seek any other remedy as may be necessary. UNOPS’ determination as to the quality of work being performed and the progress being made toward such goals shall be final and shall be binding and conclusive upon the Grantee insofar as further payments by UNOPS are concerned.
1.6 
UNOPS undertakes no responsibilities in respect of life, health, accident, travel or any other insurance coverage for any person who may be necessary or desirable for the purpose of this Agreement or for any personnel undertaking activities under this Agreement. Such responsibilities shall be borne by the Grantee. 
1.7 
The rights and obligations of the Grantee are limited to the terms and conditions of this Agreement. Accordingly, the Grantee and personnel performing services on its behalf shall not be entitled to any benefit, payment, compensation or entitlement from UNOPS except as expressly provided in this Agreement.

2. 
Intellectual Property Rights

2.1 
All intellectual property rights, including but not limited to maps, drawings, photographs, mosaics, plans, manuscripts, records, reports, recommendations, estimates, documents, images, sounds and other materials, except pre-existing materials, publicly or privately owned, collected, created, developed or prepared as a consequence of or in the course of the performance of this Activity, shall become the sole property of the Funding Source, unless otherwise stipulated in the Project Agreement. 
2.2 
The Grantee shall hold harmless and fully indemnify UNOPS from and against all claims and proceedings for infringement of any patent rights, design trademark or name or other protected rights resulting from Grantee’s performance.


3. 
Confidentiality

3.1 
UNOPS and the Grantee undertake to preserve the confidentiality of any document, information or other material directly related to the Activity that is deemed or classified as confidential, where disclosure could cause prejudice to the other party.

4. 
Allowable Costs
4.1 
The Grantee shall be reimbursed for costs incurred in carrying out the purposes of this Agreement which are determined by UNOPS to be reasonable, allocable, and allowable in accordance with the terms of this Agreement. The following definitions of what may be considered as reasonable, allocable, and allowable costs apply:
(a) 
Reasonable: shall mean those costs which are generally recognized as ordinary and necessary and would be incurred by a prudent person in the conduct of normal business.
(b) 
Allocable costs: shall mean those costs which are incurred specifically in connection to the Agreement, and are provided in the estimated budget at Annex B.
(c) 
Allowable costs: shall mean those costs which conform to any limitations in the Agreement. 
4.2 
The reasonable, allocable and/or allowable costs must be incurred during the period of the Agreement, specified in Article 3 of the Agreement, and recorded in the Grantee’s accounts in accordance with accepted accounting procedures.
4.3 
Prior to incurring a questionable or unique cost, the Grantee shall obtain UNOPS's written determination on whether the cost will be allowable.
4.4 
It is UNOPS policy that no funds shall be paid as profit or fee to a Grantee under this Agreement or any sub-Grantee. This restriction does not apply to contractual relationships entered into by the Grantee under this Agreement.



5. 
Accounting, Audit and Records

5.1 
The Grantee undertakes to provide any detailed information requested by UNOPS to verify that the Activity and the provisions of the Agreement are being properly implemented.
5.2 
Prior Grantee shall maintain all financial records, supporting documents, statistical records and all other records pertinent to this Agreement in accordance with generally accepted accounting principles [or applicable national legislation] to sufficiently substantiate charges to this Agreement. Accounting records that are supported by documentation will as a minimum be adequate to verify all costs incurred under the Agreement, receipt, and use of goods and services acquired under the Agreement, the costs of the program supplied from other sources, and the overall progress of the program. Unless otherwise notified, the Grantee’s records and sub-Grantee records which pertain to this Agreement shall be retained for a period of seven years from the date of submission of the final financial report and may be audited by UNOPS and/or its representatives.
5.3 
The Grantee shall furnish, compile and make available at all times to UNOPS any records or information, oral or written, which UNOPS may reasonably request in respect of the funds received by the Grantee.

5.4 
UNOPS shall retain the right to conduct a financial review, require an audit, or otherwise ensure adequate accountability of organizations expending UNOPS funds. 
5.5  The Grantee shall allow UNOPS staff and outside personnel (including third party entities engaged by UNOPS) the appropriate right of access to sites and premises of the Activity, and to all records and information required in order to conduct a financial review or audit.
5.6 
This provision in its entirety shall be incorporated into all sub-grants to eligible sub-Grantees which exceed USD 30,000. Sub-grants to eligible sub-Grantees which are for more than USD 2,500 but less than USD 30,000 shall at a minimum incorporate article 5.2 of this provision.

6. 
Bank accounts, Payment Advances and Refunds

6.1 
The Grantee shall maintain advances of UNOPS funds in dedicated and separate accounts to the Grantee’s ordinary funds. Such accounts must be interest bearing, unless: 
(a) 
The Grantee receives less than $100,000 in UNOPS awards per year;
(b) 
The best reasonably available interest bearing account would not be expected to earn interest in excess of $250 per year on UNOPS cash balances; or
(c) 
The depository would require an average or minimum balance so high that it would not be practical to maintain the advance in an interest bearing account. 
6.2 
Interest earned on advances will be remitted to UNOPS. However, the Grantee may retain up to $250 of interest earnings per account per year, for administrative expenses.
6.3 
At the time the Agreement expires or is terminated, the following types of funds shall immediately revert to UNOPS: 
(a) 
Any balance of funds that has not been disbursed to the Grantee; or
(b) 
UNOPS has advanced funds to the Grantee, but the Grantee has not expended them. 
6.4 
Notwithstanding 6.3 above, funds which the Grantee has obligated in legally binding transactions applicable to this Agreement will not revert to UNOPS. 
6.5 
UNOPS reserves the right to require refund by the Grantee of any amount which the Grantee did not spend in accordance with the terms and conditions of this Agreement. In the event that a final audit has not been performed prior to the closeout of this Agreement, UNOPS retains the right to a refund until all claims which may result from the final audit have been resolved between UNOPS and the Grantee.
6.6 
The Grantee acknowledges that UNOPS and its representatives have made no actual or implied promise of funding except for the amounts specified by this Agreement.  If any of the funds are returned to UNOPS or if this Agreement is rescinded, the Grantee acknowledges that UNOPS will have no further obligation to the Grantee as a result of such return or rescission.

7. 
Revision of Agreement Budget
7.1 
The approved Agreement budget is the financial expression of the Grantee's programme as approved during the award of the Agreement process. 

7.2 
The Grantee is required to report, in writing, deviations from budget and programme plans, and request prior approvals from UNOPS for any of the following reasons: 
(a) 
To change the scope or the objectives of the programme and/or revise the funding allocated among project objectives. 
(b) 
To change a key person where specified in the Agreement, or allow a 25% reduction in time devoted to the project. 
(c) 
Additional funding is needed. 
(d) 
Where indirect costs have been authorized, the Grantee plans to transfer funds budgeted for indirect costs to absorb increases in direct costs or vice versa. 
(e) 
The Grantee intends to contract or sub-grant any of the work under this Agreement, and such contracts or sub-grants were not included in the approved Agreement budget. 
7.3 
The Grantee is further restricted from transferring funds among cost categories. The Grantee is required to get the prior approval of UNOPS before making budget shifts which expect to exceed 50 % of the total Grant budget. 
7.4 
UNOPS is under no obligation to reimburse the Grantee for costs incurred in excess of the total grant amount specified in this Agreement. An increase to the total grant amount shall require an amendment to the Agreement in writing.
7.5 
The total grant amount under this Agreement is not subject to any adjustment or revision because of price or currency fluctuations or the actual costs incurred by the Grantee in the performance of the activities under this Agreement.  

8. 
Procurement of Goods and Services	

8.1 
Where implementation of the Activity requires the award of procurement contracts, the Grantee shall maintain a written code or standards of conduct that shall govern the performance of its employees engaged in the awarding and administration of contracts. No employee, officer, or agent shall participate in the selection, award, or administration of a contract supported by UNOPS funds if a real or apparent conflict of interest would be involved. Such conflict would arise when the employee, officer or agent, or any member of the employee’s immediate family, the employee’s partner, or an organization which employs or is about to employ any of the parties indicated herein, has a financial or other interest in the firm selected for an award. The officers, employees, and agents of the Grantee shall neither solicit nor accept gratuities, favours, or anything of monetary value from contractors or parties to sub-agreements. However, the Grantee may set standards for situations in which the financial interest is not substantial or the gift is an unsolicited item of nominal value. The standards of conduct shall provide for disciplinary actions to be applied for violations of such standards by officers, employees, or agents of the Grantee.
8.2 
The Grantee shall establish written procurement procedures if procurement of goods or services in excess of USD 2,500 is envisaged under this Agreement. All procurement transactions shall be conducted in a manner to provide, to the maximum extent practical, transparent, open and free competition and the use of resources in an ethical, efficient and effective manner. The Grantee shall be alert to organizational conflicts of interest as well as non-competitive practices among contractors that may restrict or eliminate competition or otherwise restrain trade. In order to ensure objective contractor performance and eliminate unfair competitive advantage, contractors that develop or draft specifications, requirements, statements of work, invitations for bids, and/or requests for proposals shall be excluded from competing for such procurements. Contracts shall be made to the offeror whose offer is responsive to the solicitation and is most advantageous to the Grantee, price, quality, and other factors considered. Solicitations shall clearly establish all requirements that the bidder or offeror shall fulfil in order to be evaluated by the Grantee. Any and all offers may be rejected when it is in the Grantee's interest to do so.
8.3 
Contracts shall be made only with responsible contractors who possess the potential ability to perform successfully under the terms and conditions of the proposed procurement. Consideration shall be given to such matters as contractor integrity, record of past performance, financial and technical resources, or accessibility to other necessary resources.
8.4 
Grantees shall ensure that the conditions applicable under these General Conditions are also applicable to the contractor.

9. 
Sub-Grant Agreements

9.1 
Sub-grant agreements shall be made only with responsible Grantees who possess the potential ability to perform successfully under the terms and conditions of a proposed agreement. Consideration shall be given to such matters as integrity, record of past performance, financial and technical resources, or accessibility to other necessary resources.
9.2 
All sub-grant agreements shall at a minimum contain provisions to define a sound and complete agreement in addition to those that are specifically required by any other provisions in this Agreement. Whenever a provision within this Agreement is required to be inserted in a sub-agreement, the Grantee shall insert a statement in the sub-agreement that in all instances where UNOPS is mentioned, the Grantee's name will be substituted.
9.3 
Grantees shall ensure that the conditions applicable under these General Conditions are also applicable to the sub-grantees.


10. 
Third Party Claims

The Grantee shall be solely liable for claims by third parties arising from the Grantee’s acts or omissions in the course of performing this Agreement and under no circumstances shall UNOPS be held liable for such claims by third parties. The Grantee shall indemnify, defend, save and hold UNOPS harmless in respect of such claims. This indemnity shall survive the termination or expiration of the Agreement.


11. 
Non-expendable equipment

11.1 
Title to all non-expendable equipment purchased with project funds supplied by UNOPS shall be the property of the Funding Source. 
11.2 
The Grantee shall maintain records of non-expendable equipment with an acquisition value of USD 500 or more purchased with project funds supplied by UNOPS. The Grantee will submit an inventory of such equipment to UNOPS attached to each milestone report, indicating description, serial no., date of purchase, original cost, present conditionand location of each item. Equipment purchased by the Grantee with funds supplied by UNOPS shall be used solely for the purposes indicated in Annex B throughout the duration of this Agreement. 
11.3 
Within 90 calendar days after the end of the Agreement, the Grantee will provide a list, for UNOPS’ review and approval, of each item that has an acquisition value of USD 500 or more, with a corresponding detailed proposal relating to the future status of that item, namely whether it is intended for sale, transfer or donation. Where the Grantee sells the property, or item, it will transfer the proceeds of the sale to UNOPS within 30 calendar days.

12. 
Anti-corruption

12.1 
The Grantee warrants that it has not and shall not offer any direct or indirect benefit arising from or related to the performance of this Agreement or the award thereof to any representative, official, employee, or other agent of UNOPS or any organization of the UN system.
12.2 
The Parties declare their commitment to counteract corrupt practices in the execution of this Agreement. Further, the Parties commit themselves not to accept, either directly or indirectly, as an inducement or reward in relation to the execution of this Agreement, any kind of offer, gift, payments or benefits, which would or could be construed as a corrupt practice.
	
13. 
Anti-terrorism

13.1 
The Grantee agrees to undertake all reasonable efforts to ensure that none of the UNOPS funds received pursuant to this Agreement are used to provide support to individuals or entities associated with terrorism and that the Grantee or any sub-grantees of any amounts provided by UNOPS hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/Docs/sc/committees/1267/1267ListEng.htm. This provision must be included in all sub-contracts or sub-agreements entered into under this Agreement.

14. 
Suspension

14.1 
Whenever UNOPS considers that the Grantee is not performing to a satisfactory standard, UNOPS may suspend, in whole or in part, the Activity under the Agreement in order to renegotiate and/or propose necessary amendments to the Agreement to redress the situation. When UNOPS suspends the Activity, in whole or in part, it must give immediate written notice to the Grantee, detailing the problems and the conditions required to reinstate the Activity.

14.2 
The suspension will take effect on the date the Grantee receives the notification.
14.3  Upon receipt of a suspension notice, the Grantee shall not incur any costs relating to the Activity, or part of the Activity, which has been suspended.
14.4 
The Activity, in whole or in part, which has been suspended, can be resumed once UNOPS and the Grantee have agreed on the terms of the continuation (including any extension of duration of the Activity). Any such agreement shall be in the form of a written amendment to the Agreement, pursuant to Article 16 of the General Conditions.
14.5 
Any portion of this Agreement not suspended shall remain in full effect.   

15. 
Termination

15.1 
UNOPS may terminate this Agreement at any time, in whole or in part, upon 14 calendar days’ written notice to the Grantee, whenever it is determined that the Grantee has failed to fulfil a substantial obligation incumbent on it, under the terms and conditions of the Agreement, or where sufficient funds have not been made available to UNOPS by its funding sources.
15.2 
This Agreement may be terminated at any time, in whole or in part, by UNOPS with the consent of the Grantee. Both parties shall agree upon termination conditions, including the effective date and, in the case of a partial termination, the portion of the Agreement to be terminated. The agreement to terminate shall be set forth in a letter from UNOPS to the Grantee.
15.3 
UNOPS may terminate this Agreement or portion of this Agreement with immediate effect upon written notice to the Grantee if it determines that corrupt, fraudulent or misrepresentative practices were engaged in by representatives of the Grantee during award or during the execution of this Agreement without the Grantee having taken timely and appropriate action satisfactory to UNOPS to remedy the situation.
15.4 
Upon receipt of and in accordance with a termination notice as specified above, the Grantee shall take immediate action to minimize all expenditures and obligations financed by this Agreement and shall cancel such unliquidated obligations whenever possible. Except as provided below, the Grantee shall not incur costs after the effective date of termination.
15.5 
The Grantee shall within 30 calendar days after the effective date of such termination repay to UNOPS all unexpended UNOPS funds which are not otherwise obligated by a legally binding transaction applicable to this Agreement. Should the funds paid by UNOPS to the Grantee prior to the effective date of the termination of this Agreement be insufficient to cover the Grantee's obligations in the legally binding transaction, the Grantee may submit to UNOPS within 90 calendar days after the effective date of such termination a written request for payment covering such obligations. UNOPS shall determine the amount(s) to be paid by UNOPS to the Grantee under such claim in accordance with this Agreement. This provision must be included in all sub-agreements.
15.6 
Any portion of this Agreement not terminated shall remain in full effect.

16. 
Amendment

No modification of or change in this Agreement, waiver of any of its provisions or additional contractual provisions shall be valid or enforceable unless previously approved in writing by the parties to this Agreement or their duly authorized representatives in the form of an amendment to this Agreement duly signed by the parties hereto.

17. 
Dispute Resolution

Any controversy or claim arising out of, or in accordance with this Agreement or any breach thereof, shall unless it is settled by direct negotiation, be settled in accordance with the UNCITRAL Arbitration Rules as at present in force. Where, in the course of such direct negotiation referred to above, the parties wish to seek an amicable settlement of such dispute, controversy or claim by conciliation, the conciliation shall take place in accordance with the UNCITRAL Conciliation Rules as at present in force. The parties shall be bound by any arbitration award rendered as a result of such arbitration as the final adjudication of any such controversy or claim.

18. 
Privileges and Immunities

Nothing in or relating to this Agreement shall be deemed a waiver of any privileges and immunities of the United Nations and/or UNOPS.
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