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THE REPUBLIC OF UGANDA
)
[bookmark: _GoBack]Invitation to bid for Procurement of a Rehabilitation Build Contractor to rehabilitate Anna - ANBAR, PHCC
  Procurement Reference No.: ASB1903/WORKS/2020/0001/2
	
Arbeiter-Samariter-Bund (ASB) has allocated funds from their donor partners to be used for the Procurement of a Rehabilitation Build Contractor to rehabilitate SAMSIEH- ANBAR, sub PHCC
1. ASB now invites written sealed bids from eligible bidders to undertake the execution of rehabilitate and build civil works as stipulated in the bidding documents. 
2. Bidding will be conducted in accordance with the Open Domestic Bidding procedures contained in the Arbeiter-Samariter-Bund (ASB) Procurement Policy, 2018.  Envelopes containing sealed bids must be marked with the above procurement reference number on the top right corner indicating the bid being submitted.
3. In order to be qualified for award of contract, bidders shall provide evidence satisfactory to ASB of their experience, technical and financial capability as well as availability of resources to execute the contract effectively. The minimum experience requirements for qualification for the contract are as indicated in the bidding document. 
4. Bidders may obtain further information from ASB and inspect the bidding documents at the address given below from 09:00am (Local time) to 5:00pm (Local time) during working days from Sundays to Thursdays.
5. Bidders are advised to visit and examine the site of works, its surroundings and obtain all information that may be necessary for preparing their bids and entering into contract for construction of the works. Site visit shall be done jointly on Monday February 3ed of 2020. The contact persons shall be Dr. Omar Rashid (Tel.: 0777689245) and Lawyer Hassan (Tel.: 0783003098). The cost of visiting the site shall be at the bidders’ own expense.
6. A complete set of Bidding Documents in English may be downloaded from the address below. 
Bids clearly marked “PROCUREMENT OF A REHABILITATE AND BUILD CONTRACTOR TO CONSTRUCT SAMSIEH SUB PHCC in ANBAR”
7.  Must be delivered to the address below by 11:30 AM local time on or before 15th   February 2020. 
8. (a) All Clarifications to this bid will be addressed to:
The Head, Procurement Division
Arbeiter-Samariter-Bund (ASB)
Physical Location: Baghdad – Mansour District, 14 Ramadan Street, 
              33.315556, 44.338385
Tel: 077508621375
Email: manageradminfinance@asb-me.org

(b) Biding documents may be inspected from: 
The Head, Procurement Division
Arbeiter-Samariter-Bund (ASB)
Physical Location: Baghdad – Mansour District, 14 Ramadan Street , 
              33.315556, 44.338385
Tel: 077508621375
Email: manageradminfinance@asb-me.org

(c) Biding documents will be issued from: 

Same as 9(b) above.

(i)  Address Bids must be delivered to: 

Same as 9(b) above.

(ii) Address of Bid Opening: 

Same as 9(b) above, 

9. The planned procurement schedule (subject to changes) is as follows:

	Activity
	Date

	a. Invitation to Bid 
	26th January, 2020

	c. Bid submission closing date 
	15th February, 2020

	d. Evaluation process 
	20th February, 2020

	e. Display and communication of best evaluated bidder notice 
	23rd February, 2020

	f. Contract Award and Signature
	1st March, 2020





"Any form of canvassing or lobbying for the tender shall lead to automatic disqualification."

Country Representative
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	[bookmark: _Toc42236628][bookmark: _Toc4180497]A. General

	[bookmark: _Toc42236629][bookmark: _Toc4180498]1. Scope of Bid

	1.1	The Employer, as defined in the Bid Data Sheet (BDS), invites bids for the rehabilitation and construction of Works, as described in the BDS. The name and procurement reference number of the Contract are provided in the BDS. The Instructions to Bidders (ITB) should be read in conjunction with the BDS.

	1.2	The successful Bidder will be expected to complete the rehabilitation and construction Works by the Completion Date specified in the Conditions of Contract (CC) Part II: Particular Conditions.

	1.3	Throughout this Bidding Document:
(a)	the “Employer” means the Employer; and
(b)	the “Contractor” means the provider
	As defined in the ASB Procurement Policy, 2018. 

	[bookmark: _Toc42236630][bookmark: _Toc4180499]2. Source of Funds

	2.1	The Employer has an approved budget from their donor partner funds towards the cost of the procurement named in the BDS. The Employer intends to use these funds to place a contract for which this Bidding Document is issued.

	2.2	Payments will be made directly by the Employer and will be subject in all respects to the terms and conditions of the resulting contract placed by the Employer.

	[bookmark: _Toc42236631][bookmark: _Toc4180500]3. Corrupt Practices

	3.1	It is ASB’s policy to require that Employers, as well as Bidders and Contractors, observe the highest standards of ethics during procurement and the execution of contracts. In pursuit of this policy, ASB represented by the Procurement Committee (herein referred to as the Authority);
(a)	defines, for the purposes of this provision, the terms set forth below as follows:
(i)	“corrupt practice” includes the offering, giving, receiving, or soliciting of anything of value to influence the action of a ASB staff in the procurement process or in contract execution; and
(ii)	“fraudulent practice” includes a misrepresentation of facts in order to influence a procurement process or the execution of a contract to the detriment of the Employer, and includes collusive practices among Bidders prior to or after bid submission designed to establish bid prices at artificial, non-competitive levels and to deprive the Employer of the benefits of free and open competition; 
(b)	will reject a recommendation for award if it determines that the Bidder recommended for award has engaged in corrupt or fraudulent practices in competing for the Contract; and
(c)	will suspend a Contractor from engaging in any procurement proceeding for a stated period of time, if it at any time determines that the Contractor has engaged in corrupt or fraudulent practices in competing for, or in executing, a contract.

	3.2	In pursuit of the policy defined in ITB Sub-Clause 3.1, the Employer may terminate a contract for Works if it at any time determines that corrupt or fraudulent practices were engaged in by representatives of the Employer or of a Bidder or Contractor during the procurement or the execution of that contract, without the Employer having taken timely and appropriate action satisfactory to the to remedy the situation.

	3.3	In pursuit of the policy defined in ITB Sub-Clause 3.1, ASB requires representatives of both the Employer and of Bidders and Contractors to adhere to the relevant codes of ethical conduct. The Code of Ethical Conduct for Bidders and Providers is available in the Procurement Policy are required to indicate their acceptance of this code through the declarations in the Bid Submission Sheet. 
3.4     Any communications between a Bidder and the Employer related to matters of alleged fraud or corruption must be made in writing and addressed to the Country Representative of ASB.

	[bookmark: _Toc42236632][bookmark: _Toc4180501]4. 	Eligible Bidders

	4.1	A Bidder, and all parties constituting the Bidder, shall meet the following criteria to be eligible to participate in public procurement:
(a)	the bidder has the legal capacity to enter into a contract;
(b)	the bidder is not:
(i)	insolvent;
(ii)	in receivership;
(iii)	bankrupt; or
(iv)	being wound up;
(c)	the bidder’s business activities have not been suspended;
(d)	the bidder is not the subject of legal proceedings for any of the circumstances in (b); and
(e)	The bidder has fulfilled his or her obligations to pay taxes. 

	4.2	A Bidder may be a natural person, private entity, government-owned entity—subject to ITB Sub-Clause 4.6—or any combination of them with a formal intent to enter into an agreement or under an existing agreement in the form of a joint venture, consortium, or association. Joint ventures, consortia and associations shall comply with the requirements of ITB Clause 6.

	4.3	A Bidder, and all parties constituting the Bidder including sub-contractors, shall have the nationality of Iraq, in accordance with Section 5, Eligible Countries. A Bidder shall be deemed to have the nationality of a country if the Bidder is a citizen or is constituted, incorporated, or registered and operates in conformity with the provisions of the laws of that country. This criterion shall also apply to the determination of the nationality of proposed subcontractors for any part of the Contract.

	4.4	A Bidder, and all parties constituting the Bidder including sub-contractors, shall not have a conflict of interest. All Bidders found to have a conflict of interest shall be disqualified. A Bidder may be considered to have a conflict of interest with one or more parties in this bidding process, if they: 
(a)	have controlling shareholders in common; or
(b)	receive or have received any direct or indirect subsidy from any of them; or
(c)	have the same legal representative for purposes of this bid; or

	(d)	have a relationship with each other, directly or through common third parties, that puts them in a position to have access to information about or influence on the bid of another Bidder, or influence the decisions of the Employer regarding this bidding process; or

	(e)	Submit more than one bid in this bidding process, except for alternative bids permitted under ITB Clause 19. However, this does not limit the participation of subcontractors in more than one bid, or as Bidders and subcontractors simultaneously; or 
(f)	is associated, or has been associated in the past, directly or indirectly, with the consultant or any other entity that has prepared the design, specifications, and other documents for the Project or being proposed as Project Manager for the Contract. A firm that has been engaged by the Employer to provide consulting services for the preparation or supervision of the Works, and any of its affiliates, shall not be eligible to bid.

	4.5	Government-owned enterprises shall be eligible only if they can establish that they are legally and financially autonomous and operate under commercial law.

	4.6	Bidders shall provide such evidence of their continued eligibility satisfactory to the Employer, as the Employer shall reasonably request.

	[bookmark: _Hlt438531784]4.7	To establish their eligibility in accordance with ITB Clause 4, Bidders shall complete the eligibility declarations in the Bid Submission Sheet, included in Section 4, Bidding Forms and submit the documents required in Section 3, Evaluation Methodology and Criteria.

	4.9	A Bidder whose circumstances in relation to eligibility change during a procurement process or during the execution of a contract shall immediately inform the Employer. 

	4.10	All materials, equipment and services to be used in the performance of the contract shall have as their country of origin an eligible country in accordance with Section 5, Eligible Countries. 

	[bookmark: _Toc42236633][bookmark: _Toc4180502]5. 	Qualification of the Bidder 

	5.1    To establish its qualifications to perform the Contract, the Bidder shall complete and submit:
(a)	the Qualification information in the formats provided in Section 4, Bidding Forms: Part B; and
(b)	the information and documents stated in Section 3, Evaluation Methodology and Criteria. 

	5.2	The qualifications of the Bidders will be assessed as part of a preliminary examination in accordance with ITB Clause 30.4.

	[bookmark: _Toc42236634][bookmark: _Toc4180503]6. 	Joint Ventures, Consortia and Associations

	6.1	If a Bidder considers that it does not have all the expertise for the assignment, it may obtain a full range of expertise by associating with other Bidder(s)/Consultant(s) or entities in a joint venture or by sub-contracting as appropriate. 

	6.2	Bids submitted by a joint venture, consortium or association of two or more firms as partners shall comply with the following requirements:

	(a)	the bid shall be signed so as to be legally binding on all partners;

	(b)	all partners shall be jointly and severally liable for the execution of the Contract in accordance with the Contract terms;

	(c)	one of the partners will be nominated as being in charge, authorized to incur liabilities, and receive instructions for and on behalf of any and all partners; and

	(d)	the execution of the entire Contract, including payment, shall be done exclusively with the partner in charge; and

	(e)	A copy of the agreement entered by the joint venture partners shall be submitted with the bid

	[bookmark: _Toc42236635][bookmark: _Toc4180504]7. 	One Bid per Bidder

	7.1	Each Bidder shall submit only one Bid, either individually or as a partner in a joint venture, consortium or association. A Bidder who submits or participates in more than one bid will cause all the bids with the Bidder’s participation to be rejected.

	[bookmark: _Toc42236636][bookmark: _Toc4180505]8. 	Cost of Bidding

	8.1	The Bidder shall bear all costs associated with the preparation and submission of his Bid, and the Employer shall not be responsible or liable for those costs, regardless of the conduct or outcome of the bidding process.

	[bookmark: _Toc42236637][bookmark: _Toc4180506]9. 	Site Visit

	9.1	The Bidder, at the Bidder’s own responsibility and risk, is encouraged to visit and examine the Site of Works and its surroundings and obtain all information that may be necessary for preparing the bid and entering into a contract for construction of the Works. The costs of visiting the Site shall be at the Bidder’s own expense.

	[bookmark: _Toc42236638][bookmark: _Toc4180507]B. Bidding Document

	[bookmark: _Toc42236639][bookmark: _Toc4180508]10. 	Content of Bidding Document

	10.1	The Bidding Document consists of Parts 1, 2, and 3, which includes all the Sections indicated below, and should be read in conjunction with any addenda issued in accordance with ITB Clause 12.

	PART 1:  Bidding Procedures
 Section 1. Instructions to Bidders (ITB)
 Section 2. Bid Data Sheet (BDS)
 Section 3. Evaluation Methodology and Criteria
 Section 4. Bidding Forms
 Section 5. Eligible Countries.

PART 2:  Employer’s Requirements
 Section 6. Employer’s Requirements

PART 3:  Contract
· Section 7. Part I: General Conditions of Contract (GCC) for the procurement of Rehabilitation and Construction works
· Section 8. Part II: Particular Conditions of Contract  (PCC)
 Section 9. Contract Forms

	10.2	The Bid Notice is not part of the Bidding Document.
10.3   Bidders can obtain the Bidding Document directly from the Employer, Employer’s address indicated in the BDS or from the following online site: https://www.ncciraq.org/en/opportunities/for-individuals/bids-tenders, bids will be rejected during evaluation. 
10.4	The Bidder is expected to examine all instructions, forms, terms, and requirements in the Bidding Document. Failure to furnish all information or documentation required by the Bidding Document may result in the rejection of the bid.

	[bookmark: _Toc42236640][bookmark: _Toc4180509]11. 	Clarification of Bidding Document

	11.1	A prospective Bidder requiring any clarification of the Bidding Document shall contact the Employer in writing at the Employer’s address indicated in the BDS. The Employer will respond in writing to any request for clarification, provided that such request is received no later than the number of days prior to the deadline for submission of bids indicated in the BDS. The Employer shall forward copies of its response to all Bidders who have acquired the Bidding Document directly from it, including a description of the inquiry but without identifying its source. Should the Employer deem it necessary to amend the Bidding Document as a result of a clarification, it shall do so following the procedure under ITB Clause 12 and ITB Sub-Clause 22.2.

	[bookmark: _Toc42236641][bookmark: _Toc4180510]12. 	Amendment of Bidding Document

	12.1	At any time prior to the deadline for submission of bids, the Employer may amend the Bidding Document by issuing addenda.
12.2	Any addendum issued shall be part of the Bidding Document and shall be communicated in writing to all who have obtained the Bidding Document directly from the Employer.
12.3	To give prospective Bidders reasonable time in which to take an addendum into account in preparing their bids, the Employer may, at its discretion, extend the deadline for the submission of bids, pursuant to ITB Sub-Clause 22.2.

	[bookmark: _Toc42236642][bookmark: _Toc4180511]C. Preparation of Bids

	[bookmark: _Toc42236643][bookmark: _Toc4180512]13. 	Language of Bid

	13.1	The medium of communication shall be in writing. 
13.2	The bid, as well as all correspondence and documents relating to the bid exchanged by the Bidder and the Employer, shall be written in English. 
13.3	Supporting documents and printed literature that are part of the bid may be in another language provided they are accompanied by an accurate translation of the relevant passages in English, in which case, for purposes of interpretation of the Bid, such translation shall govern.

	[bookmark: _Toc42236644][bookmark: _Toc4180513]14. 	Documents Comprising the Bid

	14.1	Bidders are required to prepare and submit separate technical and financial bids.  The bid submission method shall be a one stage-two envelope method.  The one stage- two envelope submission methods require a Bidder to submit a single envelope containing two separately sealed envelopes, labelled technical and financial bids which are opened on different dates at separate bid openings.  

	14.2	The Technical bid submitted shall provide the following:
(a)	Eligibility and Administrative Information provided in part A of section 4: Bidding Forms;
(b)      Qualification information provided in part B of section 4: Bidding Forms;
(c)      Technical information in part C of section 4 bidding forms 
(d)      Any other document specified in the data sheet

	14.3    The Financial bid shall contain the following information: 
(a)	 Financial Bids Submission Form, Form 4.2.1
(b)	Bid Price Breakdown, Form 4.2.2
(c)       Completed and properly executed Price schedules 1 – Breakdown of lump sum price for Design Services, Form 4.2.3
(d)       Completed and properly executed Price schedules 2 – Breakdown of lump sum price for construction Works, Form 4.2.4
e) Cash flow projections, Form 4.2.5
 

	[bookmark: _Toc42236645][bookmark: _Toc4180514]15. 	Bid Prices

	15.1	Bidders shall quote for the entire facilities on a “single responsibility" basis such that the total bid price covers all the Contractor's obligations mentioned in or to be reasonably inferred from the bidding documents in respect of the design, manufacture, including procurement and subcontracting (if any), delivery, construction, installation and completion of the facilities and performance of the services as shall be set out in the contract. 

	15.2	Bidders shall give a breakdown of the prices in the manner and detail called for in the Schedules of Prices.

	15.3	Prices quoted by the Bidder shall be fixed during the Bidder’s performance of the Contract and shall not be subject to change on any account. 

	[bookmark: _Toc42236646][bookmark: _Toc4180515]16. 	Currencies of Bid and Payment

	16.1	The prices shall be quoted by the Bidder in Unites State of American Dollars ( USD). 

	16.2	Bidders shall indicate details of their expected foreign currency requirements in the Bid. 

	[bookmark: _Toc42236647][bookmark: _Toc4180516]17. 	Bid Validity

	17.1	Bids shall remain valid for the period specified in the BDS after the date of the bid submission deadline prescribed by the Employer. A bid valid for a shorter period shall be rejected by the Employer as non-compliant.

	17.2	In exceptional circumstances, prior to the expiration of the bid validity period, the Employer may request Bidders to extend the period of validity of their bids. The request and the responses shall be made in writing. If a Bid Security is requested in accordance with ITB Clause 18, it shall also be extended for a corresponding period. A Bidder may refuse the request without forfeiting its Bid Security. A Bidder granting the request shall not be required or permitted to modify its bid.

	[bookmark: _Toc42236648][bookmark: _Toc4180517]18. 	Bid Security

	18.1	If so stated in the BDS, the Bidder shall furnish as part of its bid, a Bid Security in original form and in the amount and currency specified in the BDS.

	18.2	The Bid Security shall be, at the Bidder’s option, in any of the following forms:
(a)	a demand guarantee; 
(b)	an irrevocable letter of credit; 
(c)	a cashier’s or certified check; or
(d)	another security indicated in the BDS, 
	From a reputable source from an eligible country. The Bid Security shall be submitted either using the Bid Security Form included in Section 4, Bidding Forms, or in another substantially similar format. In either case, the form must include the complete name of the Bidder. The Bid Security shall be valid for twenty-eight days (28) beyond the end of the validity period of the bid. This shall also apply if the period for bid validity is extended.

	18.3	Any bid not accompanied by an acceptable Bid Security, if one is required, shall be rejected by the Employer as non-compliant. The Bid Security of a joint venture must define as “Bidder” all joint venture partners and list them in the following manner: a joint venture consisting of “1______,” “2______,” and “3______”.

	18.4	The Bid Security of all Bidders shall be returned as promptly as possible once the successful Bidder has signed the Contract and provided the required Performance Security or upon the request of a bidder after the expiry of the bid security.

	18.5	The Bid Security may be forfeited:

	[bookmark: _Toc438267890](a)	if a Bidder withdraws its bid during the period of bid validity specified by the Bidder on the Bid Submission Sheet, except as provided in ITB Sub-Clause 17.2; or
[bookmark: _Toc438267892](b)	if the successful Bidder fails to: 
(i)	sign the Contract in accordance with ITB Clause 40; 
[bookmark: _Toc438267893][bookmark: _Toc438267894](ii)	furnish a Performance Security in accordance with ITB Clause 41; or
(iii)	Accept the correction of its bid price pursuant to ITB Sub-Clause 29.5. 

	[bookmark: _Toc42236649][bookmark: _Toc4180518]19. 	Alternative Bids

	19.1	Bidders shall submit offers that comply with the requirements of the bidding documents, including the basic technical design as indicated in the drawings and specifications. Alternative bids shall not be considered unless otherwise indicated in the BDS.

	19.2	Where permitted, alternative bids do not need to conform precisely to the Statement of Requirements, but must -
(a)	meet the objectives and/or performance requirements prescribed in the Statement of Requirements; 
(b)	be substantially within any delivery or completion schedule, budget or other performance parameters stated in the solicitation document; 
(c)	provide all information necessary for a complete evaluation of the alternative by the Employer, including design calculations, technical specifications, breakdown of prices, proposed construction methods and other relevant details; and
(d)	Clearly state the benefits of the alternative bid over any solution which conforms precisely to the Statement of Requirements, in terms of technical performance, price, operating costs or any other benefit.
[bookmark: _Toc438438843][bookmark: _Toc438532612][bookmark: _Toc438733987][bookmark: _Toc438907026][bookmark: _Toc438907225][bookmark: _Toc43467135]20.	Format and Signing of Bid

	20.1	The Bidder shall prepare one original of each of the documents comprising the technical and the financial bid as described in ITB Clauses 14 and clearly mark both “ORIGINAL”.  In addition, the Bidder shall submit copies of both the technical and financial bids, in the number specified in the BDS and clearly mark each of them “COPY”.  In the event of any discrepancy between the original and the copies, the original shall prevail.

	20.2	The original and all copies of the bid shall be typed or written in indelible ink and shall be signed by a person duly authorised to sign on behalf of the Bidder.  This authorisation shall consist of a written confirmation as specified in the BDS and shall be attached to the bid.  The name and position held by each person signing the authorisation must be typed or printed below the signature.  All pages of the bid, except for un amended printed literature, shall be signed or initialled by the person signing the bid.

	20.3	Any interlineations, erasures, or overwriting shall be valid only if they are signed or initialled by the person signing the bid.

	20.4	The Bidder shall furnish information as described in the Financial Bid Submission Sheet on commission or gratuities, if any, paid or to be paid to agents relating to this Bid, and to contract execution if the Bidder is awarded the contract.

	[bookmark: _Toc42236651][bookmark: _Toc4180519]D. Submission and Opening of Bids

	[bookmark: _Toc42236652][bookmark: _Toc4180520]21. 	Sealing and Marking of Bids

	21.1	The original and all copies of the technical bid shall be placed in a sealed envelope clearly marked “Technical Bid,” and the original and all copies of the financial bid in a separate sealed envelope clearly marked “Financial Bid”.  The envelopes shall be securely sealed in such a manner that opening and resealing cannot be achieved undetected.

	21.2	   The envelopes containing the technical and financial bids shall:
   (a)	    bear the name and address of the Bidder;
   (b)	    be addressed to the Employer in accordance with ITB Clause 22.1; and
(c)	Bear the Procurement Reference Number of this bidding process.

	21.3	The financial bid shall also bear a warning “Do Not Open with the technical bid”.

	21.4	The two envelopes shall be placed in an outer envelope which shall be securely sealed in such a manner that opening and resealing cannot be achieved undetected. 

	21.5	The outer envelope shall:
(a)	bear the name and address of the Bidder;
(b)	be addressed to the Employer in accordance with ITB Sub-Clause 22.1;
(c)	bear the Procurement Reference number of this bidding process; and
(d)	Bear a warning not to open before the time and date for bid opening, in accordance with ITB Sub-Clause 25.1.

	21.6	If all envelopes are not sealed and marked as required, the Employer will assume no responsibility for the misplacement or premature opening of the bid.

	[bookmark: _Toc42236653][bookmark: _Toc4180521]22. 	Deadline for Submission of Bids

	22.1	Bids must be received by the Employer at the address and no later than the date and time indicated in the BDS.

	22.2	The Employer may, at its discretion, extend the deadline for the submission of bids by amending the Bidding Documents in accordance with ITB Clause 12, in which case all rights and obligations of the Employer and Bidders previously subject to the deadline shall thereafter be subject to the deadline as extended.

	[bookmark: _Toc42236654][bookmark: _Toc4180522]23. 	Late Bids

	23.1	The Employer shall not consider any bid that arrives after the deadline for submission of bids, in accordance with ITB Clause 22. Any bid received by the Employer after the deadline for submission of bids shall be declared late, rejected, and returned unopened to the Bidder.

	[bookmark: _Toc42236655][bookmark: _Toc4180523]24. 	Withdrawal and Replacement of Bids

	24.1	A Bidder may withdraw or replace its bid after it has been submitted at any time before the deadline for submission of bids by sending a written notice, duly signed by an authorized representative, which shall include a copy of the authorization in accordance with ITB Sub-Clause 20.2. Any corresponding replacement of the bid must accompany the respective written notice. All notices must be:
(a)	submitted in accordance with ITB Clauses 20 and 21 (except that withdrawals notices do not require copies), and in addition, the respective envelopes shall be clearly marked “Withdrawal,” or “REPLACEMENT,” and
(b)	Received by the Employer prior to the deadline prescribed for submission of bids, in accordance with ITB Clause 22.

	24.2	Bids requested to be withdrawn in accordance with ITB Sub-Clause 24.1 shall be returned unopened to the Bidder.

	24.3	No bid may be withdrawn or replaced in the interval between the deadline for submission of bids and the expiration of the period of bid validity specified by the Bidder on the Bid Submission Sheet or any extension thereof. 
24.4	Bids may only be modified by withdrawal of the original bid and submission of a replacement bid in accordance with ITB Sub-Clause 24.1. Modifications submitted in any other way shall not be taken into account in the evaluation of bids.

	24.5	Bidders may only offer discounts to, or otherwise modify the prices of their bids, by withdrawing and replacing their bid in accordance with this clause, or by including the discount in the original bid submission.

	[bookmark: _Toc42236656][bookmark: _Toc4180524]25. 	Bid Opening

	25.1	The Employer shall conduct the bid opening in the presence of Bidders` designated representatives who choose to attend, and at the address, date and time specified in the BDS.

	25.2	First, envelopes marked “WITHDRAWAL” shall be opened and read out and the envelope with the corresponding bid shall not be opened, but returned to the Bidder. No bid withdrawal shall be permitted unless the corresponding withdrawal notice contains a valid authorization to request the withdrawal and is read out at the bid opening. 
	All other envelopes including those marked “REPLACEMENT” shall be opened and the relevant details read out. Replacement bids shall be recorded as such on the record of the bid opening.	

	25.3	All technical bids shall be opened one at a time, reading out: the name of the Bidder; the presence of a Bid Security, if required; and any other details as the Employer may consider appropriate.  No bid shall be rejected at the bid opening except for late bids, in accordance with ITB Sub-Clause 23.1.

		Only envelopes that are opened and read out at the bid opening shall be considered further

	25.4	The financial bids shall remain sealed until the time and date notified for the opening of the financial bids. Evaluators of technical bids shall have no access to the financial bids until the technical evaluation is concluded and the result established.

	25.5	The Employer shall prepare a record of the bid opening that shall include, as a minimum: the name of the Bidder, whether there is a withdrawal and/or replacement and the presence or absence of a Bid Security, where required.  The Bidders’ representatives who are present shall be requested to sign the record.  The omission of a Bidder’s signature on the record shall not invalidate the contents and effect of the record.  A copy of the record shall be distributed to Bidders and displayed on the Employer’s Notice Board within one working day from the date of the bid Opening.




	[bookmark: _Toc42236657][bookmark: _Toc4180525]E. Evaluation of Bids

	[bookmark: _Toc42236658][bookmark: _Toc4180526]26. 	Confidentiality

	26.1	Information relating to the examination, evaluation, comparison, and post-qualification of bids, and recommendation of contract award, shall not be disclosed to bidders or any other persons not officially concerned with such process until information detailing the best evaluated Bidder is communicated to all Bidders.

	26.2	Any effort by a Bidder to influence the Employer in the examination, evaluation, comparison, and contract award decisions may result in the rejection of its bid.

	26.3	Notwithstanding ITB Sub-Clause 26.2, from the time of bid opening to the time of Contract award, if any Bidder wishes to contact the Employer on any matter related to the bidding process, it should do so in writing.

	[bookmark: _Toc42236659][bookmark: _Toc4180527]27. 	Clarification of Bids

	27.1	To assist in the examination, evaluation, comparison and post-qualification of the bids, the Employer may, at its discretion, ask any Bidder for a clarification of its bid.  Any clarification submitted by a Bidder that is not in response to a request by the Employer shall not be considered.  The Employer’s request for clarification and the response shall be in writing. The request for clarification shall be copied to all bidders for information purposes. No change in the price or substance of the bid shall be sought, offered, or permitted, except to confirm the correction of arithmetic errors discovered by the Employer in the evaluation of the financial bids, in accordance with ITB Clause 29.4.


	[bookmark: _Toc42236660][bookmark: _Toc4180528]28. 	Compliance and Responsiveness of Bids

	28.1	The Employer’s determination of a bid’s compliance and responsiveness is to be based on the contents of the bid itself. 

	28.2	A substantially compliant and responsive bid is one that conforms to all the terms, conditions, and requirements of the Bidding Document without material deviation, reservation, or omission.  A material deviation, reservation, or omission is one that:
(a)	affects in any substantial way the scope, quality, or performance of the Services specified in the Bidding Document; or

	(b)	limits in any substantial way, inconsistent with the Bidding Document, the Employer’s rights or the Bidder’s obligations under any resulting Contract; or
(c)	if rectified would unfairly affect the competitive position of other Bidders presenting substantially compliant and responsive bids.

	28.3	If a bid is not substantially compliant and responsive to the Bidding Document, it shall be rejected by the Employer and may not subsequently be made compliant and responsive by the Bidder by correction of the material deviation, reservation, or omission.

	[bookmark: _Toc42236661][bookmark: _Toc4180529]29. 	Nonconformities, Errors, and Omissions

	29.1	Provided that a bid is substantially compliant and responsive, the Employer may waive any non-conformity or omissions in the bid that does not constitute a material deviation.

	29.2	Provided that a bid is substantially compliant and responsive, the Employer may request that the Bidder submit the necessary information or documentation, within a reasonable period of time, to rectify nonmaterial nonconformities or omissions in the bid related to documentation requirements. Such omission shall not be related to any aspect of the price of the bid. Failure of the Bidder to comply with the request may result in the rejection of its bid.

	29.3	Provided that a bid is substantially compliant and responsive, the Employer shall rectify nonmaterial nonconformities or omissions. To this effect, the bid price shall be adjusted, for comparison purposes only, to reflect the price of the missing or non-conforming item or component. 

	29.4	Provided that the bid is substantially compliant and responsive, the Employer shall correct arithmetic errors on the following basis:
           (a)	if there is a discrepancy between the unit price and the total price that is obtained by multiplying the unit price and quantity, the unit price shall prevail and the total price shall be corrected, unless in the opinion of the Employer there is an obvious misplacement of the decimal point in the unit price, in which case the total price as quoted shall govern and the unit price shall be corrected;

	   (b)	if there is an error in a total corresponding to the addition or subtraction of subtotals, the subtotals shall prevail and the total shall be corrected; and
            (c)	if there is a discrepancy between words and figures, the amount in words shall prevail, unless the amount expressed in words is related to an arithmetic error, in which case the amount in figures shall prevail subject to (a) and (b) above.

		[bookmark: _Toc43357871][bookmark: _Toc4180530]30. 	Preliminary Examination of Bids – Eligibility and Administrative Compliance

	30.1	The Employer shall examine the legal documentation and other information submitted by Bidders to verify the eligibility of Bidders and any materials, equipment and services to be used in performance of the contract in accordance with ITB Clause 4.

	30.2	If after the examination of eligibility, the Employer determines that the Bidder, or the materials, equipment and services to be used in performance of the contract are not eligible, it shall reject the bid. 
30.3	The Employer shall examine the bids to confirm that all documents requested in ITB Clause 14 have been provided, and to determine the completeness of each document submitted.




	[bookmark: _Toc43357872][bookmark: _Toc4180531][bookmark: _Toc42236663]31. 	Detailed Commercial and Technical Evaluation
31.1 Commercial Evaluation 
31.1.1. The Employer shall examine the bid to confirm that all terms and conditions specified in the GCC and the SCC have been accepted by the Bidder without any material deviation or reservation.
31.1.2. If, after the examination of the terms and conditions, the Employer determines that the bid is not substantially responsive in accordance with ITB Clause 30, it shall reject the bid.
31.2   Qualification Evaluation 
31.2.1. The Employer shall determine whether the Bidder is qualified to perform the Contract satisfactorily. The determination shall be based upon an examination of the documentary evidence of the Bidder’s qualifications submitted by the Bidder, pursuant to ITB Clause 5, to clarifications in accordance with ITB Clause 27 and the qualification criteria indicated in Section 3, Evaluation Methodology and Criteria. A bid shall be rejected at this stage if it does not meet the specified qualifying criteria.
31.3 Technical Quality Evaluation 
[bookmark: _Toc4180532]31. 	Technical Evaluation

	31.1	The Employer will carry out a detailed evaluation of the technical aspects on the basis of the Bidder’s responsiveness to the Employer’s Requirements, applying the evaluation criteria, sub-criteria, and methodology specified in Section 3.  A bid shall be rejected at this stage if it does not respond to important aspects of the Employer’s Requirements or if it fails to achieve the minimum technical requirements indicated in Section 3
31.2	The bids proceeding to the financial evaluation shall be determined in accordance with the methodology and criteria specified in Section 3. 

	[bookmark: _Toc42236664][bookmark: _Toc4180533]32. 	Opening of Financial Bids

	32.1	 After the Technical evaluation is completed, the Employer shall notify those Bidders, whose bids will not pass to the financial comparison, indicating that their financial bids will be returned unopened after completing the evaluation process. The Employer shall simultaneously notify the Bidder(s) whose bids will proceed to the financial comparison indicating the date and time set for opening the financial bid(s).  The opening date shall not be sooner than one week after the notification date. The notification will be sent in writing.
32.2	The financial bid(s) shall be opened in the presence of the Bidders’ representatives who choose to attend.  The name of the Bidder and the bid price shall be read aloud and recorded when the financial bid(s) are opened. The Employer shall prepare minutes of the public opening.


	[bookmark: _Toc42236665][bookmark: _Toc4180534]33. 	Financial Evaluation

	33.1   The Employer will examine the price proposals to determine whether they are complete, whether the documents have been properly signed and whether the bids are substantially responsive to the requirements of the bidding documents. If a price proposal is not substantially responsive, it will be rejected by the Employer, and may not subsequently be made responsive by correction or withdrawal of the nonconforming deviation or reservation.

	33.2 Price Proposals determined to be substantially responsive will be checked by the Employer for any arithmetic errors. Arithmetic errors will be rectified on the following basis: If there is a discrepancy between the unit rate and the total cost that is obtained by multiplying the unit rate and quantity, the unit rate shall prevail and the total cost will be corrected unless in the opinion of the Employer there is an obvious misplacement of the decimal point in the unit rate, in which case the total cost as quoted will govern and the unit rate corrected. If there is a discrepancy between the total bid amount and the sum of total costs, the sum of the total costs shall prevail and the total bid amount will be corrected.

	33.3 The amount stated in the Financial Bid Submission Form will be adjusted by the Employer in accordance with the above procedure for the correction of errors and, shall be considered as binding upon the bidder. If the bidder does not accept the adjusted bid price, its bid will be rejected, and the bid security may be forfeited in accordance with Sub-Clause 18.5 b (iii).

	33.4 The bidder’s financial price will be determined in accordance with the methodology defined in Section 3 of the bidding documents. 

	[bookmark: _Toc42236667][bookmark: _Toc4180535]34. 	Determination of Best Evaluated Bid(s)
34.1	The Employer shall compare all substantially compliant and responsive bids to determine the best evaluated bid or bids, in accordance with Section 3, Evaluation Methodology and Criteria
[bookmark: _Toc31283195][bookmark: _Toc41998983][bookmark: _Toc43475392]35.     Post-qualification of the Bidder

	35.1	The Employer shall determine to its satisfaction whether the Bidder that is selected as having submitted the best evaluated bid is qualified to perform the Contract satisfactorily.

	35.2	The determination shall be based upon an examination of the documentary evidence of the Bidder’s qualifications submitted by the Bidder, pursuant to ITB Clause 5, to clarifications in accordance with ITB Clause 27 and the qualification criteria indicated in Section 3, Evaluation Methodology and Criteria.  Factors not included in Section 3 shall not be used in the evaluation of the Bidder’s qualifications.

	35.3	An affirmative determination shall be a prerequisite for award of the Contract to the Bidder.  A negative determination shall result in disqualification of the bid, in which event the Employer shall proceed to the next best evaluated bid to make a similar determination of that Bidder’s capabilities to perform satisfactorily.

	[bookmark: _Toc42236669][bookmark: _Toc4180536]F. Award of Contract

	[bookmark: _Toc42236670][bookmark: _Toc4180537]36. 	Award Procedure

	[bookmark: _Ref26243671]36.1	Negotiations may be undertaken with the best evaluated Bidder following the evaluation of bids to finalise minor issues of the bid or the logistical arrangements for the assignment. The cost of any negotiations shall be borne by the respective parties themselves.

	36.3	The Employer shall issue a Notice of Best Evaluated Bidder, in accordance with the ASB Procurement Policy, 2018, place such Notice on public display for a prescribed period and copy the Notice to all Bidders prior to proceeding with contract award.
36.4	The Employer shall award the Contract to the Bidder whose offer has been determined to be the best evaluated bid, provided that the Bidder is determined to be qualified to perform the Contract satisfactorily.

	[bookmark: _Toc42236671][bookmark: _Toc4180538]37. 	Employer’s Right to Accept any Bid and to Reject any or all Bids

	37.1	Notwithstanding ITB Clause 37, the Employer reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or Bidders or any obligation to inform the affected Bidder or Bidders of the grounds for the Employer’s action.

	[bookmark: _Toc42236672][bookmark: _Toc4180539]38. 	Notification of Award and Letter of Bid Acceptance

	38.1	Prior to the expiration of the period of bid validity and following the prescribed period in ITB Clause 37.1, the Employer shall notify the successful Bidder, in writing, that its bid has been accepted by issue of a Letter of Bid Acceptance. 
38.2	Until a formal contract is prepared and executed, the Letter of Bid Acceptance shall constitute a binding Contract.

	38.3	The Letter of Bid Acceptance (hereinafter and in the Contract called the “Letter of Acceptance”) will state the sum that the Employer will pay the Contractor in consideration of the execution, completion, and maintenance of the Works by the Contractor as prescribed by the Contract (hereinafter and in the Contract called the “Contract Price”).

	[bookmark: _Toc42236673][bookmark: _Toc4180540]39. 	Signing of Contract

	39.1	Promptly after notification of contract award by the issue of a Letter of Acceptance, the Employer shall send the successful Bidder the Agreement and the Special Conditions of Contract. 
39.2	Within four (4) days of receipt of the Agreement, the successful Bidder shall sign, date, and return it to the Employer.
39.3	The Agreement will incorporate all agreements between the Employer and the successful Bidder.

	[bookmark: _Toc42236674][bookmark: _Toc4180541]40. 	Performance Security

	40.1	Within 4 days after receipt of the Letter of Acceptance, the successful Bidder shall deliver to the Employer a Performance Security in the amount stipulated in the SCC and in the form of a Bank Guarantee as stipulated in Section 9, denominated in the type and proportions of currencies in the Letter of Acceptance and in accordance with the Contract.

	40.2	The Performance Security in the form of a Bank Guarantee shall be issued either (a) at the Bidder’s option, by a bank located in the country of the Employer or a foreign bank through a correspondent bank located in the country of the Employer, or (b) with the agreement of the Employer directly by a foreign bank acceptable to the Employer.

	40.3	Failure of the successful Bidder to submit the above-mentioned Performance Security or sign the Contract shall constitute sufficient grounds for the annulment of the contract award and forfeiture of the Bid Security. In that event, the Employer may award the Contract to the next best evaluated Bidder who is determined by the Employer to be qualified to perform the Contract satisfactorily.

	[bookmark: _Toc42236675][bookmark: _Toc4180542]41. 	Advance Payment and Security

	41.1	If so stated in the BDS, the Employer will provide an Advance Payment on the Contract Price, subject to a maximum amount, as stated in the BDS. This Payment shall be in the same currencies and proportions as the Contract Payment and shall be made in accordance with the GCC. 

	[bookmark: _Toc42236676][bookmark: _Toc4180543]42. 	Adjudicator

	42.1	The Employer proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at an hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. 



	Instructions to Bidders Reference
	Data relevant to the ITB

	ITB 1.1
	The Employer is: Arbeiter-Samariter-Bund (ASB)  

	ITB 1.1
	The Works consist of: REHABILITATE and Build to develop SAMSIEH sub PHCC in ANBAR”

	ITB 1.1
	The procurement reference number of the Contract is: ASB-1903/WORKS/2020/0001/2

	ITB 1.1
	The number and identification of lots comprising this Bidding Document is: N/A
The minimum and maximum number of Lots a Bidder may bid for is: N/A

	ITB 11.1
	For clarification purposes only, the Employer’s address is:
Procurement Unit
The Head, Procurement Division
Arbeiter-Samariter-Bund (ASB)
Physical Location: Baghdad – Mansour District , 14 Ramadan Street , 
              33.315556, 44.338385
Tel: 07508621375, 
Email: manageradminfinance@asb-me.org 

	ITB 11.1
	The Employer will respond to any request for clarification provided that such request is received no later than 5 working days prior to the submission of bids

	ITB 13.1
	The medium of communication shall be in writing. 

	ITB 13.2
	The bid shall be written in English. 

	ITB 14.1(i)
	The Bidder shall submit with its bid the following additional documents: N/A

	ITB 16.1
	The lump sum or unit rates and prices quoted by the Bidder shall be in United State Dollars - USD

	ITB 16.2
	The authority for specifying rates of exchange shall be the Bank of Baghdad. 

	ITB 16.3
	Foreign currency requirements shall be payable at the option of the Bidder. 

	ITB 17.1
	Bids must be valid until 30th May 2020

	ITB 17.3
	Bid price SHALL NOT be adjusted.

	ITB 18.1
	A Bid Security shall be required. 

	ITB 18.2
	The amount of Bid Security shall be 30,000 United State Dollars (USD)

	ITB 18.3
	The Bid Security shall be valid until 30th July 2020. The Bid Security shall be in form of an UNCONDITIONAL on demand Bank Guarantee using the format given in the bidding document and from a Bank acceptable to the Employer. Bidders who use Banks domiciled outside the Employers country must secure along with the bid security, a declaration from a correspondent Bank in Iraq that it will honour the Bid security on behalf of the issuing Bank.

	ITB 19.1
	Alternative bids to the requirements of the bidding documents: N/A

	ITB 20.1
	In addition to the original of the Bid, the number of copies required is: 02 (Two)

	ITB 20.2
	The written confirmation of authorization to sign on behalf of the Bidder shall be:
(a)A Power of Attorney which if signed in Iraq shall be registered; or
 (b) In the case of Bids submitted by an existing or intended JV, a Power of Attorney from each member of the JV nominating a Representative in the JV and a Power of Attorney from the JV nominating a representative who shall have the authority to conduct all business for and on behalf of any and all the parties of the JV during the bidding process and, in the event the JV is awarded the Contract, during contract execution.

	ITB 22.1
	For bid submission purposes only, the Employer’s address is:
Procurement Unit
The Head, Procurement Division
Arbeiter-Samariter-Bund (ASB)
Physical Location: Baghdad – Mansour District , 14 Ramadan Street , 
              33.315556, 44.338385
Tel: 07740918850 
Email: manageradminfinance@asb-me.org

The deadline for bid submission is: 
Date: February 15th 2020
Time (local time): 11:20 am

	ITB 25.1
	The bid opening shall take place at:
Procurement Unit
The Head, Procurement Division
Arbeiter-Samariter-Bund (ASB)
Physical Location: Baghdad – Mansour District , 14 Ramadan Street , 
              33.315556, 44.338385
Tel: 07740918850
Email: manageradminfinance@asb-me.org 
Date: 15th February 2020

	ITB 34.1
	A margin of preference shall not apply. 

	ITB 34.3
	N/A

	ITB 42.1
	The Advance Payment shall be not be granted.

	ITB 43.1
	The Adjudicator proposed by the Employer is: Hassan Mohamad Ali, Lawyer
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	Section 3.  Evaluation Methodology and Criteria

	Procurement Reference Number: ASB 1903/WORKS/2020/0001/2

	A	Evaluation Methodology

	1	Methodology Used 

	1.1	The evaluation methodology used for the evaluation of bids shall be the Technical Compliance Selection (TCS) methodology.

	2	Summary of Methodology

	2.1	The Technical Compliance Selection methodology recommends the lowest priced bid, which is eligible and substantially responsive to the technical and commercial requirements of the Bidding Document, provided that the Bidder is determined to be qualified to perform the contract satisfactorily. 
2.2	The evaluation shall be conducted in three sequential stages:
(a)	a preliminary examination to determine whether bidders are eligible and to determine administrative compliance with the basic instructions and requirements of the solicitation document;
(a)	a detailed evaluation to assess –
(i)	responsiveness to the terms and conditions of the solicitation document; 
(ii)	The Qualification and technical quality of a bid against set criteria on a pass and fail basis.
(c)	A financial comparison to determine the lowest priced bid which meets the Qualification and technical requirements.
2.3	Failure of a bid at any stage shall prevent further consideration of the bid at the next stage of evaluation.  Substantial responsiveness shall be considered a pass at the preliminary examination stage.

	B	Preliminary Examination Criteria

	3.0 Eligibility Criteria


3.1     The eligibility requirements shall be determined in accordance with ITB Clause 4

3.2	The documentation required to provide evidence of eligibility shall be: - 
 (a)	a copy of the Bidder’s Trading licence valid for 2020;
(b)	a copy of the Bidder’s Certificate of Registration or incorporation;
(c)	a copy of the Bidder’s income tax clearance certificate issued by the Tax Authority for at least 2019; 
(d)	a statement in the Bid Submission Sheet that the bidder meets the eligibility criteria stated in ITB 4.1;
(e)	a declaration in the Bid Submission Sheet of nationality of the Bidder;
(f)	a statement in the Bid Submission Sheet that the Bidder has no conflict of interest;
(g)	a declaration in the Bid Submission Sheet that the Bidder is not under suspension by the Public Procurement and Disposal of Public Assets Authority;
 (h)       Power of Attorney which if signed in Iraq shall be registered, or if signed outside Iraq shall be notarized authorizing signature of the bid on behalf of the bidder.
 (j)        Articles and Memorandum of Association.
 
3.3 For a Joint Venture, the documentation in paragraph 3.2 above shall be required for each member of the Joint Venture and the following additional documentation shall also be required:
(a) a certified copy of the Joint Venture Agreement, which is legally binding on all partners, showing that:
(i) All partners shall be jointly and severally liable for the execution of the Contract in accordance with the Contract terms;
(ii) one of the partners will be nominated as being in charge, authorized to incur liabilities, and receive instructions for and on behalf of any and all partners of the joint venture; and,
(iii) the execution of the entire Contract, including payment, shall be done exclusively with the partner in charge.
(b) Power of Attorney of the signatory (ies) of the bid authorizing signature of the bid on behalf of the joint venture 
(c) a certified copy of the Joint Deed of Undertaking in case of Sub-contractor/ Specialized Agency/Associate which is legally binding the Sub-contractor/ Specialized Agency/Associate and the Bidder/ Contractor. 

4.0 Administrative Compliance Criteria (Pass/fail requirements).
    The evaluation of Administrative Compliance criteria shall be conducted in         accordance with ITB Clause 30.3. Specifically, the criteria will include;
·     Submission of bid Submission Sheet in the format provided in the bidding document signed by a person with Powers of Attorney
·     Submission of the Bid Security in the format as presented in the bidding forms.
·     Submission of signed schedule of rates (BOQ)
·     Submission of dully completed bidding forms
·     Signed Ethical Code of Conduct issued.
	
C	Detailed Evaluation Criteria

	5.0 Commercial Criteria (Pass/ fail requirements).

	5.1	The commercial responsiveness of bids shall be evaluated in accordance with ITB Clause 31. 
5.2	The assessment of responsiveness will consider the following criteria:  
(a)	Acceptance of the conditions of the proposed contract; it should be stated in the Bid submission sheet.
(b)	Signed Schedule of rates for BoQ. 
(c)	Audited Accounts for the last 3 years (2016, 2017 and 2018) signed by Certified Accountant
(d)      Bid Security in amount of USD: 30,000 (USD) valid until 30th July 2020
(e)     Bid Validity expiry date is: 30 May, 2019 as stated in the Bid Submission Sheet 
(f)     acceptable completion schedule and 4 months of Defect liability period;
(g)    acceptability of the proposed program (work method and schedule), including relevant drawings and charts;
(h)   Manufacture’s Authorisation to supply and install key mechanical fixtures if proposed.


6.0 Qualification Criteria
Part 1:  Section 3	Evaluation Methodology and Criteria


6.1 Each bid will be evaluated on a pass/fail basis to meet the following qualification requirements  
6.2.	 Qualification Criteria 
	Sub-Factor
	Criteria
	Documentation Required

	
	Requirement
	 Bidder
	

	
	
	Single Entity
	Joint Venture, Consortium or Association 
	

	
	
	
	All partners combined
	Each partner
	At least one partner
	

	[bookmark: _Toc496968124]6.2.1 
History of non-performing contracts
	Non-performance of a contract did not occur within the last 5 (five) years prior to the deadline for bid submission, based on all information on fully settled disputes or litigation.  
	Must meet requirement by itself or as partner to past or existing JV
	N / A

	Must meet requirement by itself or  as partner to past or existing JV
	N / A
	Form B.4.1.7

	6.2.2 Litigation History
	A bidder shall not;
(i) Have persistently been involved in litigation with any PDE in Iraq (i.e. not more than 50% of its contracts in the last 5 years shall be subject of litigation) 
(ii) All pending litigation shall in total not represent more than twenty five percent (25%) of the Bidder’s net worth and shall be treated as resolved against the Bidder. 
Note: Failure to disclose any Litigation information in the bidder’s bid shall lead to disqualification of the bidder.

	Must meet requirement by itself or as partner to past or existing JVCA
	N / A

	Must meet requirement by itself or as partner to past or existing JVCA
	N / A
	Form B.4.1.8

	6.2.3 Historical Financial Performance
	Submission of audited balance sheets(financial statements) or if not required by the law of the bidder’s country, other financial statements acceptable to the Employer, for the last five (5) years to demonstrate the current soundness of the bidders financial position and its prospective long term profitability.
(a) Current Ratio (minimum 1.0)
(b) Net worth (+ve)
	Must meet requirement
	N / A
	Must meet requirement
	N / A
	Form B.4.1.9  with audited financial statements 
Bank Reference Letter showing the financial status of the firm and the Bank’s commitment to avail the particular amount in the line of credit when the bidder is awarded the contract (Form 6.1).


	6.2.4 Average Annual Turnover

	Minimum average annual construction turnover of 200,000 USD calculated as total certified payments received for contracts in progress or completed, within the last three (3) years. 

	Must meet requirement
	Must meet requirement
	Must meet 
25 percent of the requirement

	Must meet 
40 percent of the requirement
	Form B.4.1.11  

	6.2.5 Financial  Resources

	The Bidder must demonstrate access to, or availability of, financial resources such as liquid assets, unencumbered real assets, lines of credit, and other financial means, other than any contractual advance payments to meet: 
(i) the following cash-flow requirement: 400,000 (USD). 
(ii) The overall cash flow requirements for this contract and its current commitments.
	Must meet requirement
	Must meet requirement
	
NA


	NA
	Form B.4.1.10   and attach evidence

	6.2.6 General Experience 
	Experience under contracts in the role of contractor, subcontractor, or management contractor for at least the last 5 years prior to the bid submission deadline.  
	Must meet requirement

	N / A
	Must meet requirement

	N / A
	Form B.4.1.13

	6.2.7 Specific Experience
	(a)Participation as contractor, management contractor, or subcontractor, in at least 1 contract within the last 5 years each with a value of at least 200,000 (USD) that have been successfully and substantially completed and that are similar to the proposed Works. The similarity shall be based on the physical size, complexity, methods/technology or other characteristics as described in Section VI, Employer’s Requirements. This project should be substantially completed by 100%.
	Must meet requirement
	Must meet requirements  for all characteristics
	N / A
	Must meet requirement for one characteristic 
	Form B.4.1.14  




6.3 Technical Requirement

6.3.1 Pass/fail requirements

Each Bid shall meet the following minimum technical requirements   
	6.3.1.(a)Design 

	Item
	Minimum Requirement 
	Pass / Fail 

	1.0
	Understanding of the Design and Build scope 
	

	2.0
	Completeness of Submission including preliminary drawings, specifications, Calculations of geometric, structural and drainage aspects of the landing site and a design statement. 
	

	3.0
	Site assessment and interpretation of the site data
	

	4.0
	Acceptable design work plan, showing the activities and the staff deployment 
	

	5.0
	All designs and documentation shall be in accordance with the latest  (i)	Iraqi Ministry of Health Specifications (ii) Iraqi Construction Standards (iii) Ministry of Construction and Housing and Municipality and Public Work of Iraq
	

	6.0
	Scope of Design
· Complete and acceptable scoping of assignment for Design.
· Acceptable estimation of indicative quantities applied to the BOQ.
	

	6.3.1.(b)Construction Works 

	Item 
	Minimum Requirement
	Pass/Fail 

	1.0
	Proposed site organisational chart 
	

	2.0
	Construction standards: 
Compliance to  Ministry of Health Specification for PHCC construction works and Ministry of Construction and Housing and Municipality and Public Work of Iraq
	

	3.0
	Construction Schedule and sequencing:
•	Effectiveness and efficiency of construction schedule for timely completion (Maximum construction period of four (4) months 
•	Demonstration of practical steps to achieve the set construction timeline.
	

	4.0
	Durability of Materials selection & standards:
Durability of selected materials for the design life of the project where different options are available
	

	6.3.1.(c)Quality Control 

	1.0
	Proposed Quality Control and Quality Assurance Organogram
	

	2..0
	Proposed site laboratories and testing
	

	
	Procedure for Quality Control /Quality Assurance
	

	6.3.1.(d)Health and Safety 
	

	1.0
	Health and Safety Plan incl.  Risk assessment, Manpower proposed
	

	2.0
	Proposed Safety Infrastructure and Equipment at different work sites
	

	6.3.1.(e)Environment Protection 
	

	1.0
	Manpower proposed
	

	2.0
	Environment Mitigation Plan including Undertaking to comply with all statutory approved safeguards, in  environmental mitigation plan
	

	6.3.1.(f)Social-Economic Considerations
	

	1.0
	Social Mitigation Plan including undertaking to comply with all statutory approved safeguards, policies and guidelines on Environmental and Social Management
	

	6.3.1. (G) Minimum Staff Requirements as detailed in table 1 below. The bidder shall provide details of the proposed personnel and their experience records in Form C 4.1.10 included in section 4, Bidding Forms.

	6.3.1(h)The bidder shall provide minimum equipment as detailed in table 3. below

	

	
Table no. 1. Minimum Staff Requirements for Construction stage

	Item
	Staff 
	Qualification 
	Pass/Fail Basis

	1
	Construction manager
	Should have a Bachelor of Science in Architect Engineering degree from a recognized University, registered with requisite professional institutions, and having experience of at least 10 years of similar experience in supervision of similar work. The team leader shall also have experience in contract/project management and in Iraqis procurement guidelines and regulations.
	

	2
	Site engineer
	Should have Bachelor of Science in Civil Engineering degree from a recognized University, qualified and competent registered professional with practicing certificate, and having experience of at least 5 years of similar experience in supervision of similar work. 
	

	3
	one Superintendent of works (building works)
	Should have ordinary diploma in building and Civil Engineering from a recognized University/institution and having experience of at least 6 years of similar experience in the field under review, 3 years of which should be specific to buildings and structures. 
	

	5
	one health and safety officers.
	Should have a minimum of a diploma in engineering or any other field and a certificate in occupational health and safety.
	



Table No. 3. Minimum Equipment Requirements
The bidders shall demonstrate ownership, lease or hire of own construction equipment in good condition and sufficient for carrying out the work. Proposals for the timely acquisition (own, lease, hire, etc.) of the minimum essential equipment: (Attach evidence of ownership, lease agreements or any other relevant documents.


	Bidders that will have achieved a pass in all the criteria will proceed to the financial evaluation stage. 




	D	Financial Comparison Criteria

	7.	Costs to be included in the Bid Price
	

	7.1	The financial comparison shall be conducted in accordance with ITB Clause 33. It will include;
· Arithmetic corrections
· Adjustment for nonconformities
· Computing of unconditional discounts
· Comparing bid prices


	8.	Determination of Best Evaluated Bid or Bids

	8.1	The bid with the lowest evaluated price, from among those which are eligible, compliant and substantially responsive shall be the best evaluated bid.  

	


E  Post-qualification Criteria

Shall apply to the best evaluated bidder.



Section 4	 Bidding Forms
Table of Contents
4.1		TECHNICAL BID FORMS
PART A: 	Eligibility and Administrative Information
Form A 4.1.1		-	Technical Bid Submission Form
Form A 4.1.2		-	Appendix to Bid
Form A 4.1.3		-	Bid Security
Form A 4.1.4		-	Power of Attorney
Form A 4.1.5		-	Bidder Information
Form A 4.1.6		-	Bidder’s Party Information
Form A 4.1.7		-     Manufacturers Authorisation 

PART B: Qualification Information
Form B 4.1.7		-	Historical Contract Non Performance
Form B 4.1.8		-	Pending Litigation
Form B 4.1.9		-	Financial Situation
Form B 4.1.10	-	Financial Resources
Form B 4.1.11	-	Average Annual Construction Turnover
Form B 4.1.12	-	Current Contract Commitments / Work in Progress
Form CCC- Part B:  Contractor’s performance on current commitments
Form B 4.1.13	-	General Construction Experience
Form EXP – 4.1:		Contractor’s performance on previous contracts
Form B 4.1.14	-	Similar Construction Experience
Financial Identification Form
Local Content Compliance Form
PART C:	Technical Proposal
Form C 4.1.6       -     Design Proposal
Form C 4.1.7       -     Method Statement
Form C 4.1.8       -     Project Management Organisation
  Form C 4.1.9        -      Summary of staff Qualifications and Task Assignment.
Form C 4.1.9       -    Plant/ Equipment Proposed and Available for Performance of the contract
Form C 4.1.10     -      Curriculum Vitae for Key Staff
Form C 4.1.11     -     Program and Schedule
Form C 4.1.12     -     Work Plan
Form C 4.1.13     -    Health and Safety Plan
[bookmark: _Toc397501853][bookmark: _Toc12181988][bookmark: _Toc12261107]
4.2		FINANCIAL BID FORMS

PART D:  FINANCIAL PROPOSAL
Form D 4.2.1	 - Financial Bid Submission Form
Form D 4.2.2	 - Bid Price Breakdown 
Form D 4.2.3     - Price Schedule 2: Breakdown of the Lump Sum price for the     Construction Works.
Form D 4.2.5   - Cash flow projections


4.1	TECHNICAL BID


The bidders shall develop their technical bids using the following format

TECHNICAL BID FORMAT
	Section
	Contents

	1
	Eligibility and Administrative Information

	1.1
	All Eligibility and Administrative forms given under part A of section 4: Bidding Forms.

	2
	Qualification Information

	2.1
	All qualification forms given under part B of Section 4: Bidding Forms

	2
	Technical Proposal  

	2.1
	All Technical proposal forms given under Part C of section 4: Bidding Forms.




PART A - ELIGIBILITY AND ADMINISTRATIVE INFORMATION

[This Bid Submission Sheet should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder.  It should be included by the Bidder in its bid]
	
FORM A 4.1.1
Technical Bid Submission Form


Date: [-------/-----2020]
Procurement Reference No: ASB 1903/WORKS/2020/ 0001/2
To:  Arbeiter-Samariter-Bund (ASB)  
We, the undersigned, declare that: 
(a) We have examined and have no reservations to the Bidding Document, including Addenda No.: [as required by Arbeiter-Samariter-Bund (ASB)]; 
(b) We offer to provide the services in conformity with the Bidding Document for the [rehabilitation, construction and metal, fencing, floor work, electrical, installing, sewage system, wood work, metal work, painting, insulating ceiling, Air conditions, water heater]; 
(c) We hereby submit our bid which includes this technical bid, and a financial bid sealed under a separate envelope;
(d) Our bid shall be valid for a period of [10] days from the date fixed for the bid submission deadline in accordance with the Bidding Document, and it shall remain binding upon us and may be accepted at any time before the expiration of that period;
(e) We, including any associates, Joint Venture partners or Sub contractors for any part of the contract, have nationals from eligible countries . 
(f) We undertake to abide by the Code of Ethical Conduct for Bidders and Providers during the procurement process and the execution of any resulting contract;
(g) We are not participating, as Bidders, in more than one bid in this bidding process;
(h) We do not have any conflict of interest and have not participated in the preparation of the original project for the Employer;
(i) We, our affiliates or subsidiaries—including any subcontractors or Providers for any part of the contract—have not been suspended by the Public Procurement of Public Assets Authority in Iraq from participating in public procurement;
(j) Our Bid is binding upon us, subject to modifications agreed during any contract negotiations, and we undertake to negotiate on the basis of the staff proposed in our Bid;
(k) We understand that this Bid, together with your written acceptance thereof included in your Letter of Bid Acceptance, shall constitute a binding contract between us, until a formal contract is prepared and executed;
(l) We understand that you are not bound to accept the lowest bid or any other bid that you may receive;
(m) We, including any subcontractors or providers for any part of the contract resulting from this procurement process, are eligible to participate in public procurement in accordance with ITB Clause 4.1


Name: [insert complete name of person signing the Bid]	

In the capacity of [insert legal capacity of person signing the bid] 

Signed: [signature of person whose name and capacity are shown above]

Duly authorized to sign the bid for and on behalf of: [insert complete name of Bidder]

Dated on ________day of _______________, _______ [insert date of signing]

FORM A 4.1.2

Appendix to Bid

	Subject
	Sub-Clause
	Data

	Employer’s name and address
	1.1.2.2.& 1.3
	Arbeiter-Samariter-Bund (ASB)
Physical Location: Baghdad – Mansour District , 14 Ramadan Street , 
              33.315556, 44.338385
Tel: 07740918850
Email: countryrep@asb-me.org

	Contractor’s name and address
	1.1.2.3 & 1.3
	[To be inserted]

	Engineer’s name and address
	1.1.2.4 & 1.3
	To Be Nominated 

	Recipient’s name and address
	1.1.2.11 & 1.3
	The Head, Procurement Division
Arbeiter-Samariter-Bund (ASB)
Physical Location: Baghdad – Mansour District , 14 Ramadan Street , 
              33.315556, 44.338385
Tel: 07740918850
Email: manageradminfinance@asb-me.org


	Time for Completion of the Works
	1.1.3.3
	4 months Including design

	Defects Notification Period
	1.1.3.7
	4 months

	Electronic transmission systems
	1.3
	Facsimile transmission or e-mail

	Governing Law
	1.4
	The Laws of Republic of Iraq

	Ruling language
	1.4
	English

	Language for communications
	1.4
	English

	Time for access to the Site
	2.1
	Not later than the date of commencement

	Amount of performance security
	4.2
	The only acceptable form of performance security shall be unconditional on demand bank guarantee in the amount of 10% of the Accepted Contract Amount in United State of America Dollars (USD)

	Period for notifying unforeseeable errors, faults and defects in the Employer’s Requirements
	5.1
	60 Days after commencement works

	Normal working hours
	6.5
	Sunday to Friday 07:00 am Hours to 18:00 pm Hours

	Liquidated damages for the Works
	8.7
	0.05% of the Contract Price per day.

	Maximum amount of liquidated damages
	8.7
	5% of the final Contract Price

	Percentage for adjustment of Provisional Sums
	13.5(b)
	Non

	Total advance payment
	14.2
	Advance payment shall be paid as
follows:
_ 50% of advance paid upon
confirmation by the
Employer/Engineer, of evidence
of site establishment and
Compliance with the mobilization schedule up to 80% progress.
_ The Employer shall cash the advance
payment guarantee upon failure by
the contractor to adhere to the
mobilization schedule within the
mobilization period.

	Number and timing of installments
	14.2
	Two installments

	Currencies and proportions
	14.2
	United State of America Dollars (USD)

	Start repayment of advance payment
	14.2(a)
	Starting from the first Interim payment Certificate

	Repayment amortization of advance payment
	14.2 (b)
	Recovery of Advance Payment shall
start from the first Interim payment
Certificate and to be fully recovered
when 50% of the Accepted Contract
Sum, excluding any addenda, has
been certified for payment -The Contractor shall not charge the
Employer interest on delayed
Advance Payment.

	Percentage of retention
	14.3
	10% of each certified interim Payment Certificate

	Limit of Retention Money
[If Sub-Clause 14.5 applies]
	14.3
	10% of the Accepted Contract Amount

	Plant and Materials for payment when shipped en route to the Site
	14.5(b)
	Not Applicable

	Plant and Materials for payment when delivered to the Site
	14.5(c)
	Not Applicable

	Minimum amount of Interim Payment Certificates
	14.6
	As per payment schedule under PCC 14.3

	Currencies of Payment
	14.15
	Payments shall be in United State of America Dollars (USD).

	Periods for submission of insurance:
(a) Evidence of insurance
(b) Relevant policies
	
18.1
18.1
	
Date of the commencement
Date of the commencement 

	Maximum amount of deductibles for insurance of the Employer’s risks 
	18.2(d)
	Not applicable

	Minimum amount of third party insurance
	18.3
	USD: 200,000




Signature………… 
Date…
FORM A 4.1.3
 [This Bid Security should be on the letterhead of the issuing Financial Institution and should be signed by a person with the proper authority to sign the Bid Security.  It should be included by the Bidder in its bid, if so indicated in the BDS]
[bookmark: _Toc43358331]BID SECURITY
Date: [insert date (as day, month and year) of Bid Submission]
Procurement Reference No.: ASB 1903/WORKS/2020/0001/2


To:     Country Representative,
Arbeiter-Samariter-Bund (ASB)
Physical Location: Baghdad – Mansour District , 14 Ramadan Street , 
              33.315556, 44.338385
Tel:077508621375 
Email:  manageradminfinance@asb-me.org


Whereas, [insert complete names of Bidder] (hereinafter called “the Bidder”) has submitted its bid dated [insert date (as day, month and year) of bid submission] for Procurement Reference number [insert Procurement Reference number] for the (insert project name) ----------------------------------- (hereinafter called “the bid”).
KNOW ALL PEOPLE by these presents that We [insert complete name of institution issuing the Bid Security] of [insert city of domicile and country of nationality] having our registered office at [insert full address of the issuing institution] (hereinafter called “the Guarantor”) are bound unto [insert complete name of Employer] (hereinafter called “the Employer”) in the sum of [specify in words and figures the amount and currency of the Bid Security] for which payment well and truly to be made to the said Employer, the Guarantor binds itself, its successors or assignees by these presents.
Sealed with the Common Seal of the said Guarantor this [insert day in numbers] day of [insert month], [insert year].

THE CONDITIONS of this obligation are:
(1)	If the Bidder withdraws its bid during the period of bid validity specified in the bid submission sheet; except as provided in ITB Sub-Clause 17.2; or
(2)	If the Bidder having been notified of the acceptance of its bid by the Employer during the period of bid validity fails or refuses to:
(a)	sign the Contract in accordance with the ITB Clause 40, if required; or
(b)	furnish the Performance Security, in accordance with the ITB Clause 41; or
(c)	accept the correction of its bid price pursuant to ITB Clause 29.5,
we undertake to pay to the Employer up to the above amount upon receipt of its first written demand, without the Employer’s having to substantiate its demand, provided that in its demand the Employer states that the amount claimed by it is due to it, owing to the occurrence of one or more of the above conditions, specifying the occurred conditions.
This security shall remain in force up to and including twenty-eight (28) days after the period of bid validity, and any demand in respect thereof should be received by the Guarantor no later than the above date. 

Signed: [insert signature of person whose name and capacity are shown below]
Name: [insert complete name of person signing the Bid Security]
In the capacity of [insert legal capacity of person signing the Bid Security]
Duly authorised to sign the Bid Security for and on behalf of: [insert complete name of Financial Institution]
Dated on ________ day of __________________, _______ [insert date of signing]


FORM A 4.1.4
POWER OF ATTORNEY

Powers given to a person or persons after a resolution by the Board of Directors of a Company to authorize him/her/them to sign/commit the Company with respect to the Bid. Such a resolution has to be witnessed by an advocate/lawyer, signed by a Director of the company and registered with the Registrar of Companies.

The Bid must be signed by one duly authorized to do so.  A bid submitted by a Corporation must bear the seal of the Corporation and be attested by its Secretary.  A bid submitted by joint ventures of two or more firms must be accompanied by the Document of Formation of the joint venture or intended formation, The Joint venture agreement to be included in the contract in case of a successful bid  and shall be authenticated by a Notary Public or other official deputized to witness sworn statements, in which is defined precisely the conditions under which the joint venture will function, its period of duration, the persons authorized to represent and obligate it, the participation of the several firms forming the joint ventures, and any other information necessary to permit a full appraisal of its functioning.

Signatories for companies must establish their authority by enclosing a copy of the relevant resolution of the Board of Directors duly signed and dated, 




FORM A 4.1.5
[bookmark: _Toc108424563]BIDDER INFORMATION FORM
Date: [insert day, month, year]
Procurement Reference Number: 
Page [insert page number] of [insert total number] pages

	Bidder’s Information

	Bidder’s legal name 
	

	In case of JV, legal name of each partner
	

	Bidder’s country of constitution
	

	Bidder’s year of constitution
	

	Bidder’s legal address in country of constitution
	

	Bidder’s authorized representative
(name, address, telephone numbers, fax numbers, e-mail address)
	

	Attached are copies of the following original documents.
· 1. 	In case of single entity, articles of incorporation or constitution of the legal entity named above, in accordance with ITB 4.2 and 4.3.
· 2. 	Authorization to represent the firm or JV named above, in accordance with ITB 20.2.
· 3.	In case of JV, letter of intent to form JV or JV agreement, in accordance with ITB 6.2(e).
· 4.	In case of a government-owned entity, any additional documents not covered under 1 above required to comply with ITB 4.6.






FORM A 4.1.6
[bookmark: _Toc108424564]BIDDER'S PARTY INFORMATION FORM
[The following form shall be filled in for the Bidder's parties including partner(s) of a joint venture, subcontractors, suppliers and other parties]

Date: [insert day, month, year]
Procurement Reference Number: 
Page [insert page number] of [insert total number] pages
	JV / Specialist Subcontractor Information

	Bidder’s legal name
	

	JV Partner’s or Subcontractor’s legal name
	

	JV Partner’s or Subcontractor’s country of constitution
	

	JV Partner’s or Subcontractor’s year of constitution
	

	JV Partner’s or Subcontractor’s legal address in country of constitution
	

	JV Partner’s or Subcontractor’s authorized representative information
(name, address, telephone numbers, fax numbers, e-mail address)
	

	Attached are copies of the following original documents.     
· 1.	Articles of incorporation or constitution of the legal entity named above, in accordance with ITB 4.1 and 4.2.
· 2.	Authorization to represent the firm named above, in accordance with ITB 20.2.
· 3.	In the case of government-owned entity, documents establishing legal and financial autonomy and compliance with commercial law, in accordance with ITB 4.6.



[bookmark: _Toc27720058]






PART B: QUALIFICATION INFORMATION
FORM B 4.1.7
[bookmark: _Toc108424565]HISTORICAL CONTRACT NON-PERFORMANCE
[The following table shall be filled in for the Bidder and for each partner of a Joint Venture]
Bidder’s Legal Name: [insert full name]
Date: [insert day, month, year]
Joint Venture Party Legal Name:[insert full name]
Procurement Reference Number
Page [insert page number] of [insert total number] pages
		Contract non-performance did not occur during the 5 (five) years specified in section 6.2.1 of Section III (Evaluation Methodology and Criteria)
·  Contract(s) not performed during the 5 (five) years specified in section 6.2.1 of Section III (Evaluation Methodology and Criteria)


	Year
	Non performed portion of contract
	Contract Identification

	Total Contract Amount (current value, US$ equivalent)

	[insert year]
	[insert amount and percentage]
	Contract Identification: [indicate complete contract name/ number, and any other identification]
Name of Employer: [insert full name]
Address of Employer: [insert street/city/country]
Reason(s) for non performance: [indicate main reason(s)]
	[insert amount]




FORM B 4.1.8
PENDING LITIGATION
[The following table shall be filled in for the Bidder and for each partner of a Joint Venture]
Bidder’s Legal Name: [insert full name]
Date: [insert day, month, year]
Joint Venture Party Legal Name:[insert full name]
Procurement Reference Number: 
Page [insert page number] of [insert total number] pages
	Pending Litigation

	· No pending litigation in accordance with Criteria 6.2.2 of Section III (Evaluation Methodology and Criteria)
· Pending litigation in accordance with Criteria 6.2.2 of Section III (Evaluation Methodology and Criteria)

	Year
	Matter in Dispute 
	Value of Pending Claim in USD Equivalent
	Value of Pending Claim as a Percentage of Net Worth

	
	
	
	

	
	
	
	

	
	
	
	

	
	
	
	



FORM B 4.1.9
[bookmark: _Toc108424566]FINANCIAL SITUATION
[The following table shall be filled in for the Bidder and for each partner of a Joint Venture]

Bidder’s Legal Name: [insert full name]
Date: [insert day, month, year]
Bidder’s Party Legal Name:[insert full name]
Procurement Reference Number: 
Page [insert page number] of [insert total number] pages

	Financial information in USD equivalent
	Historic information for previous ______ (__) years
 (USD equivalent in 000s)

	
	Year 1
	Year 2
	Year 3
	Year …
	Year n
	Avg.
	Avg. Ratio

	Information from Balance Sheet

	Total Assets (TA)
	
	
	
	
	
	
	

	Total Liabilities (TL)
	
	
	
	
	
	
	

	Net Worth (NW)
	
	
	
	
	
	
	

	Current Assets (CA)
	
	
	
	
	
	
	

	Current Liabilities (CL)
	
	
	
	
	
	
	

	Information from Income Statement

	Total Revenue (TR)
	
	
	
	
	
	
	




	Profits Before Taxes (PBT)
	
	
	
	
	
	
	

	· Attached are copies of financial statements (balance sheets including all related notes, and income statements) for the last five years, as indicated above, complying with the following conditions.
· All such documents reflect the financial situation of the Bidder or partner to a JV, and not sister or parent companies.
· Historic financial statements must be audited by a certified accountant.
· Historic financial statements must be complete, including all notes to the financial statements.
Historic financial statements must correspond to accounting periods already completed and audited (no statements for partial periods shall be requested or accepted).




[bookmark: _Toc163975065]

























FORM B 4.1.10
FINANCIAL RESOURCES
(Specify proposed sources of financing, such as liquid assets, unencumbered real assets, lines of credit, and other financial means, net of current commitments, available to meet the total construction cash flow demands of the subject contract as indicated in Criteria 6.2.5 of Section III (Evaluation Methodology and Criteria)

	Financial Resources

	No.
	Source of financing
	Amount (US$ equivalent)

	1
	

	

	2
	

	

	3
	

	

	
	

	



FORM B 4.1.11
[bookmark: _Toc108424567]AVERAGE ANNUAL CONSTRUCTION TURNOVER
[The following table shall be filled in for the Bidder and for each partner of a Joint Venture]

Bidder's/Joint Venture Partner's Legal Name: [insert full name]
Date: [insert day, month, year]
Bidder's Party Legal Name: [insert full name]
Procurement Reference Number: 
Page [insert page number] of [insert total number] pages

	Annual Turnover Data for the Last 3 Years (Construction Only)

	Year
	Amount  Currency
	Exchange Rate
	USD
Equivalent

	2016 
	
	
	

	2015
	
	
	

	2014
	
	
	

		Average Annual Construction Turnover    
	



The information supplied should be the Annual Turnover of the Bidder or each member of a JV in terms of the amounts billed to clients for each year for work in progress or completed, converted to USD at the rate of exchange at the end of the period reported. 


[bookmark: _Toc163975066]
FORM B 4.1.12
CURRENT CONTRACT COMMITMENTS / WORKS IN PROGRESS
Bidders and each partner to a JV should provide information on their current commitments on all contracts that have been awarded, or for which a letter of intent or acceptance has been received, or for contracts approaching completion, but for which an unqualified, full completion certificate has yet to be issued.

Current Contract Commitments / Works in Progress
Each Applicant and each member of a joint venture or other consortium must fill in this form, providing information on their current commitments on all contracts that have been awarded, or for which a letter of intent or acceptance has been received, or for contracts approaching completion, but for which an unqualified, full completion certificate has yet to be issued.

	Name of Contract
	Employer, contact address/tel/fax[footnoteRef:1] [1:  The Employer reserves the right to contact this person or any other person for reference check.  It is in the best interest of the Applicant to seek that the contact person provided in this form responds within a maximum of [02] days when contacted by Employer.  A no response from the reference could be treated as a poor performance.  ] 

	Value of outstanding work (current USD equivalent) Rate of exchange if applicable
	Estimated completion date
	Cumulative physical progress to date (%)

	1.

	
	
	
	

	2.

	
	
	
	

	3.

	
	
	
	

	4.

	
	
	
	

	5.

	
	
	
	

	etc.

	
	
	
	





[bookmark: _Toc311106059][bookmark: _Toc311109454][bookmark: _Toc311109765][bookmark: _Toc311109922][bookmark: _Toc311110078][bookmark: _Toc311111718][bookmark: _Toc311112150][bookmark: _Toc311113047][bookmark: _Toc311113204][bookmark: _Toc344300325][bookmark: _Toc344366342][bookmark: _Toc344366912][bookmark: _Toc344367482][bookmark: _Toc344367767][bookmark: _Toc344368912][bookmark: _Toc344370047][bookmark: _Toc344370326][bookmark: _Toc344370886][bookmark: _Toc344371442][bookmark: _Toc344372264][bookmark: _Toc344372537][bookmark: _Toc344449947][bookmark: _Toc344636334][bookmark: _Toc344636488][bookmark: _Toc349190588]Form CCC – Part B: Contractor’s Performance on Current Commitments
[bookmark: _Toc349190589]Each member of a JV must fill in this form
	Contractor’s Performance on Current Commitments

	Contract/Project  Identification and Name]
	

	[Name and Address of Employer]
	

	[Brief Description of the Works Executed by the Bidder]
	


	Starting Month Year
	

	Ending Month Year
	

	Duration in Years
	

	Role of Bidder:
	

	

	Employer’s Report on Contractor’s Performance

	Mobilisation of Personnel Resources 
	Did the contractor mobilise the required key staff as per his bid and did not experience inability to mobilise staff?
 Yes	 No

	
	Comments:



	
	The contractor did not experience high staff turnover

 Yes	 No

	
	Comments:



	Mobilisation of Equipment Resources
	Did the contractor comply with the mobilisation schedule and timelines?
 Yes	 No

	
	Comments:


	Project Timelines
	Is the contractor meeting the project timelines?
 Yes	 No

	
	Comments:


	Compliance to Environmental and Social Safeguards
	Is the contractor complying with the environmental and social safeguards? 
 Yes	 No

	
	Comments:


	Public Safety and Traffic Management  
	Is the contractor complying with the approved public safety and traffic management plans?
 Yes	 No

	
	Comments:


	Co-operation and Coordination with Supervisor/Employer
	Is the contractor actively coordinating/communicating with supervisor/employer’s personnel and always attempting to minimize the impact of delays on the project?
 Yes	 No

	
	Comments:


	Quality of Works 
	Is the work executed acceptable with all corrective work items and noted deficiencies being addressed per specifications in a timely manner?
 Yes	 No

	
	Comments





This reference in respect of «Insert name of Bidder» is provided by: 
Signature: 	
Please print name: 	
On behalf of «insert name of Employer»
Designation: 
Telephone number: ………………………………….
Date: 


[bookmark: _Toc108424568]FORM B 4.1.13
GENERAL CONSTRUCTION EXPERIENCE

[The following table shall be filled in for the Bidder and for each partner of a Joint Venture]

Bidder's/Joint Venture Partner's Legal Name: [insert full name]
Date: [insert day, month, year]
Bidder JV Party Legal Name: [insert full name]
Procurement Reference Number: 
Page [insert page number] of [insert total number] pages

[Identify contracts that demonstrate continuous construction work over the past 10 (ten) years pursuant to Criteria 6.2.6 of Section III (Evaluation Methodology and Criteria). List contracts chronologically, according to their commencement (starting) dates.]
	General Construction History

	Starting
Month
Year
	Ending
Month
Year
	Years
	Contract Identification and Name
Name and Address of Employer
Brief Description of the Works Executed by the Bidder
	Role of Bidder

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	


[bookmark: _Toc108424569]
Form EXP – 4.1: Construction Experience
Each member of a JV must fill in this form
	Construction Experience

	Contract/Project  Identification and Name]
	

	[Name and Address of Employer]

	

	[Brief Description of the Works Executed by the Bidder]
	



	Starting Month Year
	

	Ending Month Year
	

	Duration in Years
	

	Role of Bidder:
	

	

	Employer’s Report on Contractor’s Performance

	Overall Contractor’s Performance

	Element
	Rating

	
	Poor
	Fair
	Good
	Very Good
	Excellent

	Quality of Works
	
	
	
	
	

	Meeting Contract Timelines
	
	
	
	
	

	Compliance to Environmental and Social Safeguards
	
	
	
	
	

	Public Safety and Traffic Management  
	
	
	
	
	

	Co-operation and Coordination with Supervisor/Employer 
	
	
	
	
	

	Compliance to UNRA Mandatory Requirements

	Mobilization of Personnel Resources 
	Did the contractor mobilize the required key staff as per the contract and/or there wasn’t high turnover of the contractor’s staff. Refer to Guidance note No.6
 Yes	 No

	
	Comments:


	Mobilization of Equipment Resources
	Did the contractor comply with the mobilization schedule and timelines? Refer to Guidance note No.7
 Yes	 No

	
	Comments:


	Project completed in Time
	Did the contractor complete the work on the original schedule and/or extended completion time? 
 Yes	 No

	
	Comments:




This reference in respect of insert name of Bidder » is provided by: 
Signature: 	
Please print name: 	
On behalf of «insert name of Employer»
Designation: ……………………………………………………….
Telephone number: 	
Date:

FORM B 4.1.14
SIMILAR CONSTRUCTION EXPERIENCE
[The following table shall be filled in for contracts performed by the Bidder, each partner of a Joint Venture, and specialist sub-contractors]
Bidder's/Joint Venture Partner's Legal Name: [insert full name]
Date: [insert day, month, year]
JV Party Name: [insert full name]
ICB No. and title: 
Page [insert page number] of [insert total number] pages
Fill up one (1) form per contract 
	Contract of Similar Size and Nature

	Contract  No . . .of  . . . . .
	Contract Identification
	

	Award Date
	
	Completion Date
	

	Role in Contract
	  Contractor
	   Management Contractor
	  Subcontractor

	Total Contract Amount
	USD

	If partner in a JV or subcontractor, specify participation of total contract amount
	Percent of Total
	Amount

	Employer’s Name
Address
Telephone/Fax Number
E-mail
	

	Description of the similarity in accordance with Criteria 6.2.7(a) Section III (Evaluation Methodology and Criteria)

	
	





	
 

PART C – TECHNICAL PROPOSAL
Form C: 4.1.6	Design Proposal
The proposed outline of the Design Proposal is as given in the outline below. It should be noted that the technical proposal shall include but not be limited to the information stated in the proposed outline. 
Appreciation of the Assignment 
Prepare a short report on the state of project site, identifying the key design issues and the challenges that are being faced at present. 
Describe your understanding of a Design and Construction contract and identify special issues or problems that are likely to be encountered. Illustrate clearly and concisely your understanding of the technical and institutional elements that must be addressed.
Comments and Suggestions on the Employer’s Requirements
Under this heading the bidder should:
Provide commentary on the Employer’s Requirements, including status of the information available and relevant design issues for the works, detailing how the critical requirements will be achieved;
Suggest any modifications to the Employer’s Requirements that the Employer may wish to consider to incorporate Value Engineering. 
Bidders should note that any errors noted in the Employer’s Requirements during the preparation of bids should be notified to the Employer under the provisions of ITB11 [Clarification of Bidding Documents].
Preliminary Design (Attach all the drawings in appropriate size and format).
Appropriate use of design standards, guides, manuals, and design methodology shall be evaluated. 
A description of the site data collected (or data from the information provided by the Employer, if any) and used for tender design, design assumptions, process and relevant calculations to design the proposed new intervention. This is to include design philosophy, reference to all design guides and standards used plus why the proposed design  is considered appropriate for Iraq.
Preliminary Design of all elements of the Works.  The Preliminary Design shall comprise drawings and technical specifications.  Drawings scales shall range from 1:100 to 1:500, or as otherwise specified in the Employer’s Requirements.
Discussion of how the Bidder proposes to develop the design at key stages, including a commentary on any necessary mapping and/or survey work and the proposed design methodology for key elements of the Works.
Discussion of how the Bidder proposes to incorporate environmental and social considerations, including the prevention of negative impacts, and inclusion of mitigation measures and health and safety concerns into the design, including proposed methods for coordinating design work with concurrent environmental management plan; 
The contractor to clearly show how the proposed design meets the performance criteria 
Name, qualifications, and particulars of the Design Company and designers in charge of the design for the Works.
Form C: 4.1.7 Method Statement 
This section shall include
A description of the proposed plan for furnishing the design work for the project. This methodology shall include at least the proposed location of the design office(s) and a description of the work, which the bidder anticipates will be performed, how it will be performed and by whom 
A description of how the bidder’s design personnel will interface with the construction personnel and client personnel.
Site investigation approach to be used to establish design data for all project sites  including borrow sites.
A description of the proposed plan for construction of the project. This description shall (i) indicate how the bidder intends to divide the project into work segments to enable optimum construction performance, (ii) define how the work will be executed, and (iii) outline the bidder’s plans and procedures to ensure timely delivery of resources to achieve the project schedule. (iv) include proposed production rates used in developing the programme and propose plant list that matches the rates and programme of works.
Land design QA/QC approach to ensure that the landing structures are constructed as designed and minimization of defects that may result during construction such that long-term performance is not jeopardized.  This should also include the location, site and laboratory testing equipment to be provided and how the materials laboratory will be set up and managed and in particular the QA/QC process to be used
Describe the proposed approach to managing Environment and Social(E&S) impacts during implementation of this project including a description of the mitigation measures that will be used and international E& S standards that maybe applicable; provide enough detail to demonstrate an understanding of the critical E & S issues related to the project. 
Demonstrate that it possesses a high level of Environmental and Social (“E&S”) management expertise and can successfully manage the E&S risks associated with the implementation of the proposed Rehabilitation and Construction Works. 
a) Describe the proposed approach to managing E&S impacts during implementation of this project, including a description of the mitigation measures that will be used and international E&S standards that may be applicable; provide enough detail to demonstrate an understanding of the critical E&S issues related to the project.
Describe how Safety will be implemented and coordinated among the various entities working on the project and the public.
Describe project cost and schedule control and compliance with environmental requirements; 
Outline of the arrangements which the Bidder proposes to adopt to manage coordination of Site access.
Commentary on the geotechnical and subsurface aspects of the Works including materials, material sources and any constraints.
Commentary on logistics and traffic management 
Outline of the arrangements which the Bidder proposes to adopt to ensure compliance with the Employer’s Requirements and for testing upon completion as called for in the Employer’s Requirements.
Outline of arrangements which the Bidder proposes for conducting training as specified in the Employer’s Requirements.
Outline of arrangements for handover, including completion of as-built drawings, preparation of operation and maintenance manuals, and any additional matters.
Strategy for compliance with (a) performance specifications, and (b) tests on and after completion, including equipment, staff, methods, etc to be used to check this compliance;
Strategy for control of work and materials during project execution.



Form C: 4.1.8 Project Management Organisation 
The bidder shall provide a description of the organizational structure and management methodology to be used by the bidder for completing the work and shall include the following:
a chart or charts indicating the basic structure of the Proposer's organization and the roles, responsibilities and functions of each sub-organization, including the interrelationships of project management, design, construction, and QC/QA. Chart(s) supplied shall identify key persons for the design, construction, and QC/QA management effort and also, describe the methods to be used to ensure necessary coordination among these organizations.
A description of the Proposer's management system to be used during all phases of the project to control and coordinate the cost and schedule of the work. 
The Proposer shall submit a comprehensive Quality Control/Quality Assurance Plan, which covers its responsibilities and actions for both the design and construction phases. 
A statement detailing the bidder’s philosophy and approach for disputes avoidance and/or issue resolution.





Form C: 4.1.9	 Summary of Staff Qualifications and Task Assignments 
For each of the key personnel, the proposal shall include a description of his or her function and responsibility relative to the project. The proposal shall indicate the time each key person will devote exclusively to the project. The Proposer's organization chart may indicate any additional positions considered key personnel and show their relationship to other key personnel.
The CVs of the proposed professional staff in the format presented under section 4, signed by both the staff member and the authorised representative of the firm submitting the proposal shall be submitted as part of the technical proposal.  
Include form 4.1.9(a): Summary of staff qualification and task assignment as well as estimated time inputs in form of a bar chart.
A:	 Technical/Managerial Staff
	Position/Name
	Education/
Professional Registration
	Experience in Similar Position (Years)
	Specialism and Assigned Tasks

	
	
	
	
	

	
	
	
	
	


B:	 	Support 
	Position/Name
	Education/
Professional Registration
	Experience in Similar Position (Years)
	Assigned Tasks

	
	
	
	
	

	
	
	
	
	


Signature………………………………… (A person or persons authorised to sign on behalf of the Bidder) Date:…………………..

4.1.9 Plant/Equipment Proposed and Available for Performance of the Contract
	
	Description
(Type/Make/Model)
	Power
/Capacity
	No of Units
	Year of 
Manufacture
	Owned (o) or Hired (H)
	Current Location
	Date 
Available

	A
	Construction Plant
	
	
	
	
	
	

	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	

	B.
	Vehicle/Trucks
	
	
	
	
	
	

	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	

	C.
	Other Plant
	
	
	
	
	
	

	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	


Signature…………………………………… (A person or persons authorised to sign on behalf of the Bidder) Date:

FORM C 4.1.10	CURRICULUM VITAE FOR KEY STAFF
	[The information requested is required in the format provided below and should be included by the Bidder in its bid]
Format of Curriculum Vitae for Proposed Key Staff
Proposed Position:  	
Name of Bidder:  		
Name of Staff:  		
Profession:  		
Date of Birth:  		
Years with Firm:  		Nationality:  	
Membership in Professional Societies:  	
	
Detailed Tasks Assigned:  	
	
Key Qualifications: (Relevant to the Assignment)
	
Education: (& Professional Qualifications)
	
Professional Experience:

Summarize professional experience over the last 20 years, in reverse chronological order. Indicate particular technical and managerial experience relevant to the project.
	From
	To
	Company / Project / Position / Relevant technical and management experience

	
	
	

	
	
	

	
	
	


	
Languages:
	
Certification:
I, the undersigned, certify that to the best of my knowledge and belief, these data correctly describe me, my qualifications, and my experience.

___________________________________________Date:  	
[Signature of staff member]	Day/Month/Year
Full name of staff member:______________________________________
____________________________________Date:  	
[Authorised representative of the firm]	Day/Month/Year
Full name of authorised representative: _________________________


FORM C: 4.1.11 PROGRAM AND SCHEDULE

Each Bidder shall set out a detailed Program and Schedule for design and construction of the Works to be undertaken, including estimated start and finish dates for individual components and identification of major milestones and critical path.  The proposed Program and Schedule shall be developed according to Employer’s Requirements and shall address the following:

(a)   Details of the proposed schedule for design of the Works, including the submission of design documents, review and approval of the design by the Engineer. a description of the Bidder’s Work Breakdown Structure (WBS), including project phases and major activities. Describe the inter-relationships between the WBS, phases, and major activities and how the breakdown facilitates coordination between design, review, and construction of the project. The proposal shall describe how the WBS is consistent with the Proposer’s organization and approach to management.

(b)  Details of the proposed schedule for permitting processes that may be necessary in order to commence the Works, including the preparation of required studies, supporting information, and applications.

(a)      Details of the proposed timeline for carrying out the Works within the Time for Completion, in the form of a bar chart showing notably the critical path.

(b)     Details of the proposed timeline for the testing, commissioning and handing over of the completed Works. The schedule shall show the activity relationships, duration, and timing of the phases, and activities for engineering, construction, and maintenance during construction. The schedule shall reflect major project milestones.















Form C: 4.1.12 Work Plan
	
Each Bidder shall set out a detailed Program and Schedule for design and construction of the Design and Construction Works to be undertaken, including estimated start and finish dates for individual components and identification of major milestones and critical path.  The proposed Program and Schedule shall be developed according to Employer’s Requirements and shall address the following:

(a) Details of the proposed schedule for design of the Design and Construction Works, including the submission of design documents, review and approval. 

(b) Details of the proposed timeline for carrying out the Design and Construction Works within the Time for Completion, in the form of a bar chart showing notably the critical path.

(c) Details of the proposed timeline for the testing, commissioning and handing over of the completed Design and Construction Works.

(d) [Other proposed measures as may be appropriate].
























	Form C: 4.1.13 Health & Safety Plan

The Bidder shall provide the documents to show that it has in place sufficient safety policy documents and safety awareness to be able to perform their responsibilities in a safe and secure manner. 

The Bidder shall demonstrate in a narrative section of its Technical Offer that its possesses a high level of Health and Safety (“H&S”) management expertise and can successfully manage the H&S risks related to the implementation of the Design and Construction Works.  To demonstrate this, the Bidder shall provide the following:

(a) Describe proposed H&S staffing, roles and responsibilities, and management structure; 

(b) Describe the proposed equipment and facilities for managing H&S impacts during implementation of the Design and Construction Works. 



































4.2	 FINANCIAL BID


The Bidder shall complete the price schedules attached indicating the lump sum prices for each of the parts of the works listed. 

The bidder is responsible for ensuring that he carries out sufficient investigatory and design work during the preparation of his bid to allow him to comprehensively assess the scope of work and price the lump sum offer. 

The items provided are intended to cover all the works that have been anticipated but bidders may add additional items or leave certain items blank if they so wish. However the minimum level of detail shown in the standard format must be adhered to.
























 Bid Submission Sheet should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder.  It should be included by the Bidder in its bid]
	Form D 4.2.1		Financial Bid Submission Sheet


Date: [insert date (as day, month and year) of bid submission]
Procurement Reference No: ASB 1903/WORKS/2020/ 0001/2
To:  The Head, Procurement Division
Arbeiter-Samariter-Bund (ASB)
Physical Location: Baghdad – Mansour District , 14 Ramadan Street , 
              33.315556, 44.338385
Tel: 07740918850
Email: manageradminfinance@asb-me.org

We, the undersigned, declare that: 
(a) The total price of our Bid is: [insert the total bid price in words and figures, indicating the various amounts and the respective currencies], inclusive of local taxes;
(b) The following commissions, gratuities, or fees have been paid or are to be paid with respect to the bidding process or execution of the Contract: [insert complete name of each Recipient, its full address, the reason for which each commission or gratuity was paid and the amount and currency of each such commission or gratuity. If none has been paid or is to be paid, indicate “none”];

	Name and address of Recipient
	Purpose Reason
	Currency and Amount

	

	

	


	

	

	


	

	

	




Name: _________________________[insert complete name of person signing the bid]	
In the capacity of _________________ [insert legal capacity of person signing the bid] 
Signed: __________[signature of person whose name and capacity are shown aboveDuly authorized to sign the bid for and on behalf of: ______[insert complete name of Bidder]Dated on _________day of _______________, _______ [insert date of signing]

Form D 4.2.2:  Bid Price Breakdown 

There shall be no currency split requirements and it will be:	USD United State Dollars - 100 %



Signature………………………………………………………. 
(A person or persons authorized to sign on behalf of the Bidder)
Date:……………………..

















Form D 4.2.3 Price Schedule 1: Design 
1. The lump sum prices to be provided in this schedule shall be for works executed in accordance with the Ministry of Health  General Specifications for Primary Health Care Centers , Dated January 2015. This shall be for the entire design period.



Signature………………………………………………………. 
(A person or persons authorized to sign on behalf of the Bidder)
Date:

Form D 4.2.4 Price Schedule 2 – Construction Build Works for the site 

	Bill of Quantity

	Reconstruction off SAMSIEH SUB Primary Health Care Center in Anna

	Anbar SAMSIEH City 



	General Obligations Included within the Contract Cost:
1- All required works are subjected to the Iraqi's Standard Specifications and attached specifications. The measurements of all quantities of the implemented works will be calculated based on the actual findings and dimensions according to the engineering specifications.
2- All used materials must be subjected to the necessary laboratory tests both inside and outside the country as required. ASB engineers have the right to re-test any materials in the project in a different laboratory for some cases. 
3- The contractor is required to obtain an official approval by the supervisory committee before supplying any required materials, devices, systems...etc. or starting the implementation of any new items; including the provision of samples, mockup, catalogues for testing/inspection required to obtain this official approval. 
4- The contractor is responsible for the safety of all activities in the site including the provision of all occupational safety requirements for all employees and workers (PPE). 
5- The contractor cannot demand all the quantities mentioned in the BOQ, if the final measurement will show less quantities. 
6- All the concrete works in the project should be provided by approved ready mix concrete batching plant which should be subjected to all quality control tests periodically and all its gauges and materials balances are calibrated by Central Organization for Standardization and Quality Control (COSQR). The calibration certificates must be in force and not-expired. 
7- The contractor is required to provide and Install a prefabricated office of two rooms at least including kitchen and toilet for the supervisory committee of the project with all required furniture, electrical, mechanical and communications services. Also, it is required to provide only a one means of transport with its driver for the following-up of the project implementation by the committee. 
8- The maintenance works of the defect liability period (4 months) includes all civil, sanitary, electrical and mechanical works.



	#
	Item
	Unit
	Quantity
	Price $
	Total $

	A : Site Preparation Works
	 
	 
	 
	 

	1
	Site preparation:
Supply materials, tools, heavy construction equipment and manpower to demolish and remove all concrete structure, walls, blocks and foundations which existing up and down the ground level and 25cm of the existing soil of project ground. All project area shall be cleared of grass and weeds to at least a depth of 30 cm. Cleared of structures, pavement, sidewalks, concrete or masonry debris, trees, logs, upturned stumps, loose boulders, and any other objectionable material of any kind which would interfere with the performance or completion of the work, create a hazard to safety, or impair the subsequent usefulness of the work, or obstruct its operation. The price should include withdrawal of surface, ground water and ponds within the area of the project (if any). In addition to remove trees and other natural vegetation outside and inside the actual lines of project area, and all debris from the site to a dump site approved by the relevant authority. leveling and compacting all the project area (after removal of 25 cm of the existing project soil) using heavy construction equipment - single drum sheep feet and vibratory road roller compactor, the natural ground compaction of the project should not be less than 90% of MDD to comply with the modified proctor test and marking and planning the buildings of the project. The work includes delivering all existing materials and furniture inside the project before demolishing the buildings to End User warehouses  and delivering them by official storage documents according to instruction of the supervisory committee, cleaning and washing all parts of the project after completing the construction works. All needed work to complete the job will be included within the price.
	M2
	900
	 
	 

	
	
	
	
	
	

	 
	Excavation Works:فقط للمواقع التي تحتاج
Excavation in all types of soil (even rock layers, existing asphalt, concrete foundations, etc..) for the project area starting at the existing ground level down to the required depth  approved by the engineering committee, removal of all material to a site approved by local authorities. The price include cleaning and leveling the bed of the excavation, compaction  using heavy construction equipment - single drum sheep feet and vibratory road roller compactor (the compaction of these areas should not be less than 90% of MDD to comply with the modified proctor test) and withdrawing the underground water if the groundwater level is high on a daily basis using water tank truck until the completion of the foundations and all the required works to complete the Job. All needed work to complete the job will be included within the price.
	M3
	 
	 
	 

	2
	Spreading Stone Layer: فقط للمواقع التي تحتاج
Supply materials, tools and manpower to spread and pave stone layer of class B regularly under the buildings areas, the stone layer thickness not less than 30 cm, the work includes excavating drainage channel to withdrawal the underground water if the groundwater level is high on a daily basis using water tank truck, compaction of the stone layer well using vibratory road roller compactor and all the required works to complete the Job.
	M2
	 
	 
	 

	3
	Spreading Sub-base Layers
Supply of materials, tools and manpower for filling (in layers not exceeding 25cm, including compaction up to 95% of MDD to comply with the modified proctor test ) with sub base (type B) up to the required levels for the area of project, with required treatment. All needed work to complete the job will be included within the price.
	M3
	510
	 
	 

	B: Civil Works
	 
	 
	 
	 

	B-1: Concrete Works    
	 
	 
	 
	 

	4
	Laying One Layer of Thick Nylon
Supply materials, tools and manpower for laying one layer of thick agricultural nylon of 1mm thick.  The nylon should lay before casting the concrete covering , with all the required works to complete the Job.
	M2
	150
	 
	 

	5
	Sulphate Resistant Plain Concrete
Supply materials, tools and manpower to cast  Sulphate resistant plain concrete with compressive strength  21 MPa , (Slump 5"), the work includes expansion joints every 20 m2 and according to the instructions of engineering committee,  and all the required works to complete the Job.as the following:
	 
	 
	 
	 

	A
	Minimum 10 cm thick Under foundations (Blinding) 
	M2
	140
	 
	 

	B
	Minimum 15 cm thick and 25cm width with using Sika proof for D.P.C  layer using heavy thickness steel frame of 15 cm height
	M.l
	215
	 
	 

	C
	Minimum 10 cm thick under marble tiles.
	M2
	360
	 
	 

	6
	Reinforced Concrete 
Supply materials, tools and manpower to cast reinforced concrete with compressive strength 26 Mpa for all concrete works , the work includes shuttering( formwork), reinforcement and all accessories as per the attached drawings and technical specification, the price should include using high yield strength of (420N/mm2) deformed steel reinforcement (Ukraine or Turkish origin which is available in the markets and conform to the required specifications), coating the buried foundations and any part of columns using the tar class II or III and emphasis on water spraying (Curing) not less than 7 days, the use of Jute Cloth in the curing process  with all the required works to complete the Job, as following:
	 
	 
	 
	 

	A
	Foundations using sulfur resistant cement  
	M3
	69
	 
	 

	B
	Roofs of 18 cm thick and parapets
	M3
	78
	 
	 

	C
	Columns 
	M3
	1
	 
	 

	D
	Drop beams (The prominent part of the ceiling is calculated) and 
	M3
	5
	 
	 

	E
	lintel beams above the openings of doors and windows 
	M3
	6
	 
	 

	F
	Steps, landings and flights (sulfur resistant cement is used for the part down D.P.C Layer). 
	M3
	5
	 
	 

	B-2: Building Works With bricks  
	 
	 
	 
	 

	7
	Build The Walls Under D.P.C Layer
Supply materials, tools and manpower to build the walls under D.P.C layer using red clay bricks type A of (24x 12x 7.5) cm and cement-sand mortar (1:3) as per the attached drawings, the required brand is ASO or Al-Hilal , the work includes filling joints and spaces by sulfur resistant cement-sand mortar (1:3) , plastering the walls with cement –sand mortar (1:3) and spreading for both sides of the walls with tar Class II or III  with all the required works to complete the Job.
	M3
	43
	 
	 

	8
	Build The Walls Above D.P.C Layer
Supply materials, tools and manpower to build the walls building and parapets walls of 24cm thick above D.P.C layer and 12 cm thick for the partitions using red clay bricks  type A of (24x 12x 7.5) cm and cement-sand mortar (1:3) as per attached drawings, the required brand is ASO or Al-Hilal with all the required works to complete the Job.
	M3
	183
	 
	 

	B-3:  Backfilling With River Sand Layers
	 
	 
	 
	 

	9
	Backfilling Works:
 Supply of materials, tools and manpower for filling in layers not exceeding 40cm thick for the one layer, including good compaction  using approved river sand up to D.P.C  layer level inside the building and in any area required within inside the building with all necessary works, with required treatment. All needed work to complete the job will be included within the price.
	M3
	370
	 
	 

	B-4: Tiling and False Ceiling Works
	 
	 
	 
	 

	10
	Marble Tiles for The Building Floors and Entrance

Supply materials, tools and manpower to finish the buildings floors and building entrance using marble tiles of (30X60) cm dimensions and 2 cm thick from a first-class of Turkish origin (original, not commercial or imitative) and cement sand mortar (1:3) , the tiles final faces should be flat and free from any ripples, the price includes steps of polishing and  glazing the marble tiles in site and not limited to fill the joints with white cement, use of pieces and strips of marble tiles (Different in terms of colors) to work decorations and geometric shapes in the floors according to the direction of the Engineering Committee, cleaning the concrete floors well before finishing the floor using the tiles and taking into consideration the make of joints which not exceeding the width it of 1.5 cm for each 8 to 12 M.l and it is subsequently filled with Sikaflex construction AP with Back up rod for joints tiles . The contractor must submit samples to the Engineering Committee for the approval of one of the sample and which must be subject to the full physical and chemical laboratory tests and according to Iraqi standard specifications, with all the required works to complete the work.
	M2
	285
	 
	 

	11
	Ceramic Tiles 
Supply materials, tools and manpower to finish the walls of sanitary units, kitchen, and 1.2 m height skirting for all the building walls and floors of the sanitary units and kitchen using ceramic tiles from a first-class and cement sand mortar (on two-layer of plastering of cement mortar (1: 2) and (1:3)), the tiles final faces should be flat and free from any ripples, solution of water and bonding agent. The contractor must submit samples to the Engineering Committee for the approval of one of the sample and which must be subject to the laboratory tests and according to Iraqi standard specifications, installation of aluminum ceramic corner tile trim at the corners and edges of the walls, with all the materials needed to install, filling the joints with white cement and polishing, with all the required works to complete the work.
	 
	 
	 
	 

	A
	Ceramic tiles for the walls of (30x60) cm dimensions  
	M2
	440
	 
	 

	B
	Ceramic tiles anti slip for the floors of (30x30) cm dimensions  
	M2
	40
	 
	 

	12
	Roofing Using Concrete Tiles 
Supply materials, tools and manpower for roofing works according to the technical specifications, the work includes the following:

A: Cleaning the roof well using air compressor and coating all the roof with two layers of liquid bitumen primer for waterproofing (flancote).

B: Spreading opposite layers of tar of (30/20) grade and laying between them a good quality of SBS modified bitumen waterproofing membrane (Saudi or Jordanian origin) of 3mm thick, the tar layers and bitumen waterproofing membranes level must be raised 20 cm height around water baffles for the building and overlapping between the bitumen waterproofing membrane pieces not less than 15 cm for both directions.

C:  Spreading high density and compressed corks layer of 5 cm thickness and laying one layer of thick agricultural nylon (polyphone sheets 1 mm).

D: Spreading clean river sand layer with 8 cm thickness at the lowest area and increase the thickness according to the required slope.

E: Finishing with concrete tiles of (80x80x4) cm thickness, taking into consideration the slope towards water drainage.

F: Casting the edges by plain concrete of 21 Mpa compressive strength.

G: Filling the joints with bitumen mastic with cautery 
with all required works to complete the job.
	M2
	357
	 
	 

	
	
	
	
	
	

	13
	Perforated Gypsum Board False Ceiling Tiles :
Supply and install perforated gypsum board false ceiling tiles of 60x60 cm dimension and 10 mm thickness which should be installed on the 3.0 m height from the ground level of the building, the work includes provision and installation of heavy thickness metal structure for false ceiling( L, T sections, hold down clips), galvanized steel rod 5mm (1.2x1.2m) for fixing it with the ceiling by screws "butterfly" type, and all installation and connection accessories with all works to complete the job.
	M2
	290
	 
	 

	14
	PVC False Ceiling :
Supply and install PVC false ceiling tiles of 60x60 cm dimension and 10mm thick which should be installed on the 3.0m height from ground level of the building for the sanitary units and kitchen, the work includes provision and installation of heavy thickness metal structure for false ceiling( L, T sections, hold down clips), galvanized steel rod 5mm (1.2x1.2m) for fixing it with the ceiling by screws "butterfly" type, and all installation and connection accessories with all works to complete the job.
	M2
	35
	 
	 

	B-5: Plastering, Exterior Cladding for The Building and Painting Works: Including all materials, scaffolds, workmanship, tools and anywhere else needed
	 
	 
	 

	15
	Smoothed Cement Plastering:  
Supply materials, tools and manpower to plaster the building external walls and some parts of the front entrance of the building as per shown in attached drawings using smooth-finished cement plastering of 20mm thick with cement sand mortar (1:3) using aluminum straight edges, plastering in two coats over, the work includes spreading one layer of cement splash dash, putting a layer of metal mesh on the area under the cement plastering which should be  installed at the linking area of the concrete beams and columns with the bricks walls with decoration works in the plastering according to supervisory committee directions, and all the required works to complete the work. 
	M2
	620
	 
	 

	16
	Gypsum Plastering  
Supply of materials, tools and manpower for gypsum plastering of the  two layers minimum 20mm of brown and white gypsum using aluminum straight edges for  the interior walls up to the concrete ceiling, the price includes one layer of cement splash dash under Gypsum plastering with cement-sand mortar, putting a layer of metal mesh on the area under the  gypsum plastering which should be installed between the linking area of concrete beams and columns with the bricks walls and all the required works to complete the work.
	M2
	510
	 
	 

	17
	Plastic Painting for Internal Walls:                   
Supply of materials, tools and manpower to paint the interior walls with 3 layers of plastic painting (Jotun, Betek, CAPAROL, Polisan, dyo). The job includes cleaning the walls and ceilings, removing the dirt and dust. All needed works to complete the job, shall be included within the price.
	M2
	510
	 
	 

	18
	Plastic Painting For External Walls:                                                    
 Supply of materials, tools and manpower to paint the exterior walls and ceiling, with three layers of plastic (silicon water proof) paint (Jotun- Jotashield, Betek, CAPAROL, Polisan, dyo).  The job includes cleaning the walls, removing the dirt and dust. All needed works to complete the job, shall be included within the price.
	M2
	600
	 
	 

	19
	Cladding External Walls of The Building Facade  
Supply materials, tools and manpower  for cladding the external walls for the facade of the building with limestone panels  type (Mosul - Ba'adhira) and and  first-class marble tiles of Turkish origin (approved sample) using mechanical method for the installation and using reinforcement steel layer (BRC) of (6 mm) diameter to install stone panels and marble tiles on the walls, price should include filling the spaces between the stone and marble tiles  and the walls by using cement mortar (1:3) and the joints between stone with white cement and crushed stone powder (1:1), using solid copper wire for the installation of stone, installation of the stones panel on the walls and above the openings of doors and windows and sunshades using steel angle section of 2 inch and 3 mm thick and polishing stone very well taking into account the special safety requirements, and according to the technical specifications and attached drawings  as follows (The contractor should be complied with all forms and types of stone and all other details referred to in the attached drawings and designs),and all the required works to complete the work. As following:
	 
	 
	 
	 

	A
	Stones panels with thickness of not less than 5 cm
	M2
	22
	 
	 

	B
	Stones Frame of 20 cm height ( Coplan- كوبلن صدر طير)
	M.l
	20
	 
	 

	C
	Stones Frame of 20 cm height and 5 cm thick ( Coplan)
	M.l
	20
	 
	 

	D
	Stones Frame of 15 cm height and 5 cm thick ( Coplan), which it is also used around all windows of a building.
	M.l
	126
	 
	 

	E
	Marble tiles of 2 cm thick   
	M2
	26
	 
	 

	B-6: Doors, Windows, Handrails and Sun Shed works
	 
	 
	 
	 

	20
	Teak (Saj) Wooden Doors:
Supply and install D1 teak (saj) leave wooden doors of 2.25x1 m dimensions with 6x3 inch red cedar (jawi) frame of 2.35x1.1 m dimensions (from outside to abroad) as per the attached drawings. Price of the work shall include the thickness of teak layer not less than 5 mm thick for each door face, installing geometric motifs on the exterior and interior faces for the door made of Jawi wood, Jawi wood frame around the door of 5 cm width and 1 cm thick, heavy duty door locks and handles from Italian or Turkish origin - first class, heavy duty Stainless Steel door hinges of 5 screws, fixing a stopper on the floor or wall, installing aluminum sheet of 25 cm height and 2 mm thick in the door end and from both the directions, painting  the door and frame with three layer of liquid teak paints, with all the required works to complete the work. As following:  
	Ea.
	13
	 
	 

	21
	Steel Doors:
Supply and install double face steel door, the  partitions inside the door included every 20cm  by steel Square hollow section (4cmX4cmx2mm), and covered with steel plate 1.5 mm thickness on both sides with the use of geometric engravings on the steel plates designed by CNC machines using  steel plate 2 mm thick for the doors mentioned in attached drawings, the frame shall be from steel C section of 3 inch and 3 mm thickness and steel angle section of 1 inch and 2 mm thickness ( double steel frame), the work  including all necessary fixings hinges, doors handles, locks with  key from Italian or Turkish origin - first class, hands locks and fixing a stopper on the floor or wall, glazing using stained glass of 6 mm thick , insulation foam, accessories, mastic, hardware and painting with anti-rust paint and 3 layers of oil paints type hammer finish, locks, connections accessories, as per attached drawings, and all the required works to complete the work. As following:
	 
	 
	 
	 

	A
	D3 Steel door of 2.75 x 2.75 m  dimensions (two leaves door)
	Ea.
	1
	 
	 

	B
	D4 Steel door of 2.75 x 1.4 m dimensions (two leaves door)
	Ea.
	1
	 
	 

	C
	D6  Steel door D6 of 3.00 x 2.1 m dimensions (two leaves door)
	Ea.
	1
	 
	 

	22
	PVC Door:
Supply and install PVC door with frame(D5) of 2.2 x 0.9  m dimensions (the door color should be dark brown) for sanitary unit, It is installed in the walls by frame of steel C Section of 3 inch dimension, 3mm thick and painting with three layers of oil based paints in addition to anti rust primer.  The PVC sections and panel lambrins should be wide section and from Turkish origin  - first class as per the attached drawings with all accessories and installation of heavy duty locks, hinges and handles from Turkish origin, with all the required works and accessories to complete the Job. 
	Ea.
	4
	 
	 

	23
	Steel Sliding Door For The Main Entrance and Parking
Supply and install steel sliding door of (D7) 3.25x 2.1 m dimensions , the  partitions inside the door included every 20cm by Square hollow section (4cmX4cmx2mm), the frame door ( the moving part ) from Square hollow section of 3 inch and 3 mm thick, and covered with steel plate 1.5mm thickness on back side with the use of steel plates of 2 mm thick designed by CNC machines from the front side, the main frame shall be from steel C section of 4 inch and 3 mm thickness and steel angle section of 4 inch and 3 mm thickness ( double steel frame) and the door's rail of A channel of 3 inch and 4 mm thick and mild steel round bar of 12mm diameter which should be installed by reinforced concrete base , the work  including all necessary fixings hinges, doors handles, locks with  key from Italian or Turkish origin  - first class and fixing a stopper on the floor or wall, insulation foam, accessories, mastic, hardware, and painting with anti-rust paint and 3 layers of oil paints type hammer finish, locks, connections accessories, as per attached drawings, with all the required works to complete the work.  
	Ea.
	1
	 
	 

	24
	Aluminum Window
Supply and install aluminum window with it is frame and installing by frame of steel C Section of 3 inch, 3mm thick and painting with three layers of oil based paints in addition to anti rust primer. Price of the work shall include using heavy thickness not less than 1.3mm and 7.5 cm width aluminum sections of Turkish origin - first class as per the drawings, installation of heavy duty locks and handles, installation of tinted glass of 6 mm thick, anti-insect netting mesh, steel guard frame (Steel Burglar frame) as per attached designs (The contractor should be complied with all details and design of steel guard frame referred to in the attached drawings) with painting the steel frame and guard frame with 3 layer of oil based paints “type hammer finish” in addition to anti rust prime coat, all the required works and accessories to complete the Job. The doors dimensions as followings:
	 
	 
	 
	 

	A
	W1 Aluminum window of 1.6 x 1.8 m dimension 
	Ea.
	13
	 
	 

	B
	W2 Aluminum window of 0.5x 0.75 m dimension 
	Ea.
	4
	 
	 

	C
	W3 Aluminum window of 1.4 x 0.8 m dimension 
	Ea.
	3
	 
	 

	D
	W4 Aluminum window of 1.2 x 1.4 m dimension 
	Ea.
	1
	 
	 

	25
	Roller Curtains
Supply and install roller curtains (Zebra Curtains) of high thickness for windows, it should be of good quality of Turkish and approved by engineering committee. For more details please see compliance sheet. The curtains dimensions as followings:
	 
	 
	 
	 

	A
	 Roller Curtains of 1.7 x 1.9 m dimension
	Ea.
	13
	 
	 

	B
	 Roller Curtains of 1.4 x 1.9 m dimension
	Ea.
	4
	 
	 

	26
	Steel Handrail:
Supply of materials, tools and manpower to install steel handrail of 90cm height for external stairs using steel tubes and sections as per attached the drawings. The price includes painting with 3 layer of oil based paints “type hammer finish” in addition to anti rust prime coat. All needed work to complete the job will be included within the price. 
	M.l
	14
	 
	 

	27
	K- span Sun Shed works :
Supply of materials, tools and manpower to install K- span sun shed which should be installed  in the main front entrance for the project. The price includes:
A- Excavation for the columns footing (60x60x60cm).
B- Providing and installing (4) anchor bolts of Ø16mm and length of (40cm) for each column.
C- Providing and installing base plate of (200x200x10mm) for each column.
D- Casting column footing (60x60x60cm) using (C21MPa) concrete and sulphate resistance cement for each columns.
E- Providing and installing columns of Steel hollow square section of 100x100x3mm with height 3 m, the distance between columns shall not exceed 3 m
F-Providing and installing steel drain trench using steel plate of 2 mm
G-Providing and installing K- span sunshade, using plate of 0.8 mm thick,.
H-Painting the steel structure with one layer of anti rust and three layers of oil paint. 
All needed work to complete the job will be included within the price. 
	M2
	50
	 
	 

	B-7:  Billboard, Room Title Board and Portable Fire Extinguisher 
	 
	 
	 
	 

	28
	Aluminum Composite letters 
Supply and install the PHCC name in the building facade  in the form of composite letters  that should be cut by CNC cutting machine by using aluminum panels with the panels thickness not less than 5 mm and its bases from PVC panels of 1 cm thick as per the colors determined by the engineering committee. The letters structure should be flat surfaces and free of metal impurities and should be installed on the wall using silicone adhesive glue and plastic fisher screw wall plug, with all the required works to complete the Job.
	M2
	6
	 
	 

	29
	Room Title Boards:
Supply and install room title name made of thick plastic sheet of 15x35 cm dimensions, the price should include printing the required titles on it, using plastic fisher screw wall plug to fix it in the walls. All needed work to complete the job will be included within the price.
	Ea.
	14
	 
	 

	30
	Portable Fire Extinguisher Powder 
Supply and install portable fire extinguisher powder of 12 Kg  capacity-(A.B.C) type which should be installed in the locations determined by supervisory committee. The installation shall be complete with brackets and it should be usable for at least three years from the date of receipt all in accordance with the Civil Defense specification, with training candidates from the end user on how to use them.
	Ea.
	7
	 
	 

	B-8: Passageway and The External Corridors Works
	 
	 
	 
	 

	31
	Supply materials, tools and manpower to cast the new passageways around the building and the external corridors which lead to the building of 1.5 m width according to the follow items: 
	 
	 
	 
	 

	A
	Spreading thick agricultural nylon layer- polyphone sheets of 1 mm thick before casting concrete ( under foundation and passageway floor)
	M2
	40
	 
	 

	B
	Casting Sulphate resistant plain concrete of 20 cm thickness and 30 cm width for passageway foundation with compressive strength 21 MPa, (Slump 5”) , all the required works to complete the Job
	M3
	8
	 
	 

	C
	Build the passageway walls using red clay bricks type A of (24x 12x 7.5) cm and cement-sand mortar (1:3), the required brand is ASO or Al-Hilal with height 80 cm and 24 cm width, the work includes smoothed plastering for the external and internal wall with cement-sand (1:3) and spreading the internal wall with tar Class II or III.
	M3
	26
	 
	 

	D
	Spreading well compacted river sand layer with thickness not more than 40 cm for each layer under passageways floor.  river sand layers shall be watered, leveled and compacted well. With required treatment
	M3
	185
	 
	 

	E
	Casting smooth  Sulphate resistant plain concrete for passageway floor with compressive strength 21 MPa, (Slump 5”) and 10 cm thickness, the work includes expansion joints every 20 m2  and it is subsequently filled with Sikaflex construction AP with Back up rod, and all the required works to complete the Job.
	M2
	170
	 
	 

	F
	Finishing the front, side walkways and entrance to the buildings floors using Polished cement mosaic tiles (approved samples by supervisory committee) of (40X40) cm dimensions best quality and cement sand mortar (1:3) , the tiles final faces should be flat and free from any ripples, the price includes steps of polishing and  glazing the mosaic tiles in site and not limited to fill the joints with white cement, the work includes casting sulphate resistant plain concrete with compressive strength  21 MPa , (Slump 5") under mosaic tiles with all required work to complete the job.
	M2
	100
	 
	 

	G
	Painting the Brick walls from outside with three layers of plastic (silicon waterproof) paint (Jotun, Betek, CAPAROL, Polisan, dyo)
	M2
	150
	 
	 

	B-9:  Parking Works
	 
	 
	 
	 

	32
	Parking of the Project
: Supply materials, tools and manpower to cast the parking, the work includes leveling the ground, compaction of existing ground (which should not be less than 90% of MDD to comply with the modified proctor test), filling in layers not exceeding 25cm, including compaction up to 95% of MDD to comply with the modified proctor test with sub base (type B)up to the required levels (the required levels of the parking floors is 40 cm under the passageway concrete floor ) and according to the supervisory committee directions, the price should include spreading thick nylon layer of 1 mm thick and casting with compressive strength 21 Mpa reinforcement sulphate resistance concrete with BRC layer of 6 mm thick, smooth surface and 15 cm thick using Helicopter for leveling concrete surface, working expansion joints every 20 m2and subsequently filled with bitumen mastic with cautery, and all the required works to complete the Job.
	M2
	120
	 
	 

	33
	Metal Sunshade Works
supply materials, tools and manpower to install metal sunshade roof of 3m height which should be installed in the  parking, according to details below: 

A- Steel square column of 3x3 inch and 4 mm thick and the distance from column and another should not be more than 3 m.

B- Base plate of 25x25 cm dimension10 mm thick to install the sunshade steel structure with floors using rot bolts of 18 mm diameter with all required works 

C- Steel hollow square section for beams of roof structure of 3x3 inch dimensions and 4 mm thick.

D- Steel hollow rectangular section for sub beam 1.5x3 inch and 3 mm thick.
            
E-  0.8mm thick corrugated plates for the roof, fixed by screws and overlapped in order to prevent water leakage.

The work includes all cutting and welding works, painting with anti-rust and three layers of oil paint for all steel structure with all the required works to complete the Job.
	M2
	60
	 
	 

	B-10: Fence Wall Works
	 
	 
	 
	 

	34
	 Laying one Layer of Thick Nylon
Supply materials, tools and manpower to spread thick agricultural nylon layer (polyphone sheets 1 mm thick) over the sub base layer
	M2
	60
	 
	 

	35
	Sulphate Resistant Plain Concrete for Blinding
Supply materials, tools and manpower to cast the Blinding of 10 cm thick and 21Mpa compressive strength, with all the required works to complete the Job. 
	M2
	60
	 
	 

	36
	Reinforced Concrete for Foundation
Supply materials, tools and manpower to cast 26 MPa sulphate resistance reinforced concrete of (30x50) cm the price should include, high yield (420N/mm2) deformed steel reinforcement  (Ukraine or Turkish origin which is available in the markets and conform to the required specifications), timber formwork and shuttering. For more details, please see attached drawings.  
	M3
	18
	 
	 

	37
	Reinforced Concrete for The Columns
Supply materials, tools and manpower to cast reinforced concrete for the columns of (30x40) cm dimensions, 2m height above the D.P.C and 26 MPA compressive strength every 6m distance, with installation of expansion joints each 12m (double columns), use of cork layers in the joints, with all the required works to complete the Job. Please see attached drawings
	M3
	9
	 
	 

	38
	Build The Walls Under D.P.C Layer
Supply materials, tools and manpower to build the walls under D.P.C level with stone and cement-sand mortar (1:3) of 30 cm height the work includes smooth plastering the walls with cement –sand mortar (1:3), coating the buried foundations for both sides using the tar type II or III and backfilling the foundations sides with sub-base ''class C''. For more details, please see attached drawings. 
	M3
	15
	 
	 

	39
	Sulphate Resistant plain Concrete for D.P.C Layer
Supply materials, tools and manpower to cast the D.P.C  layer of 10 cm thick and 21Mpa compressive strength, with all the required works to complete the Job. 
	M.l
	120
	 
	 

	40
	Build The Walls Above D.P.C Layer
Supply materials, tools and manpower to build the block wall fence using hollow concrete block of (40x20x20) cm and cement –sand mortar (1:3), 2m height above the D.P.C, with all the required works to complete the Job. For more details, please see attached drawings.
	M3
	48
	 
	 

	41
	Plain Concrete for Cover Along The Wall
Supply materials, tools and manpower to cast concrete cover of 10 cm thick, 40 cm width and 21 Mpa compressive strength along the block wall fence, with all the required works to complete the Job. For more details, please see attached drawings.
	M3
	5
	 
	 

	42
	Reinforced Concrete for Columns Doors
Supply materials, tools and manpower to cast reinforced concrete columns of (40x60) cm with foundation of 1x 1 m, 0.5m depth and 24Mpa compressive strength for the doors.  
	M3
	2
	 
	 

	43
	Smoothed Cement Plastering for The all Fence Walls
Supply materials, tools and manpower for cement plastering with 20mm thickness smooth-finished for the fence wall, columns and concrete cover above the fence walls using aluminum straight edges. The price includes three layers as follows: one layer of cement splash dash, one layer of rough (kafmal) and finally smooth finished cement plastering with cement-sand mortar(1:3), putting a layer of metal mesh on the area under the cement plastering which should be  installed  at the linking area of the concrete columns with the block walls and all the required works to complete the work.
	M2
	650
	 
	 

	44
	Plastic Painting for The Fence Wall:                                                 Supply of materials, tools and manpower to paint the fence walls and concrete cover above the fence walls with three layers of external plastic (silicon water proof) paint (Jotun- Jotashield, Betek, CAPAROL, Polisan, dyo).  The job includes cleaning the walls, removing the dirt and dust. All needed works to complete the job, shall be included within the price.
	M2
	650
	 
	 

	45
	Wrought Iron Wall Railings for The Front Fence Wall:                          Supply and install steel wrought iron wall railing of 80 cm high for the front fence only that consist of steel square section for external frame for railing of 2 inch and 3 mm thick, steel square section frame around the steel plates sheets of 3/4 inch and 2 mm thick and steel plate sheet of 3 mm thick with the use of geometric engravings on the steel plates designed by CNC machines as per attached drawings, the work includes installing it between two concrete columns using steel base plate of 10 mm thick which should be installed in the concrete columns using rawl bolts, painting iron wall railings  and base plate with 3 layers of oil based paints type hammer finish in addition to anti-rust primer and all the required works to complete the Job
	M2
	28
	 
	 

	46
	Cladding The Concrete Columns for The Front Fence Wall:  
Supply materials, tools and manpower for cladding the concrete columns for the front fence wall only with limestone panels  type (Mosul - Ba'adhira) , price should include filling the spaces between the stone and the walls by using cement mortar (1:3) and the joints between stone with white cement and crushed stone powder (1:1), using solid copper wire for the installation of stone, polishing stone very well taking into account the special safety requirements, and according to the technical specifications and attached drawings  as follows (The contractor should be complied with all forms and types of stone and all other details referred to in the attached drawings and designs) ,and all the required works to complete the works. As the following:
	 
	 
	 
	 

	A
	Stones panels with thickness of not less than 5 cm
	M2
	7
	 
	 

	B
	Stones Frame of 20 cm height ( Coplan- كوبلن صدر طير)
	M.l
	8
	 
	 

	C
	Stones Frame of 20 cm height and 5 cm thick ( Coplan)
	M.l
	8
	 
	 

	D
	Stones Frame of 15 cm height and 5 cm thick ( Coplan)
	M.l
	70
	 
	 

	E
	Marble tiles of 2 cm thick and 30 cm height.
	M2
	11
	 
	 

	C: Sanitary Works
	 
	 
	 
	 

	 
	Notes:
The items prices below should be included the following:

1-   provision, installation, connection, operation and inspection of all the materials in their locations according instructions of the engineering committee, then testing the networks sanitary works, with all requirements to complete the job.

2-   The work shall be according to the technical specifications and the materials shall be of high quality after submitting samples (at least 3 of Egyptian, Turkish or Saudi origin) for all materials of pipes and fittings to engineering committee.

3- All materials should be subjected to laboratory tests and may not use any material not tested.

4-  When the PVC sewage pipes networks are established for a sanitary unit, they should be examined under appropriate pressure as per technical specifications.

5-  The 35 cm height of the sanitary unit walls and floor should be Spread with two layers of tar and one layer of SBS modified bitumen waterproofing membrane of (Saudi or Jordanian origin) of 3mm thick.

6- Dumping of all debris to a site approved by local authorities.

7-  All the requirements and accessories of the pipes feeder and fitting, connecting the building networks (pure water and sewage) with the source of water and drainage network. Sanitary works include the following:
	 
	 
	 
	 

	
	
	
	
	
	

	47
	Septic Tank
Supply of materials, tools and manpower to build septic tank of (L=3.0m, W=5.0m and H=2.0m) dimension as per attached drawings. The price also includes soil excavations, casting the reinforced concrete foundation using (C21Mpa) Concrete, 20 cm thick and 40cm width using sulphate resistant cement, build  the walls of 20 cm width with solid concrete  block (15x20x30cm) and cement mortar (1:3), casting reinforced concrete slab (20cm) with two layers of 12mmØ spaced @20cm both directions and installation of two manhole hard plastic manhole covers of (60 x 60 ) cm . All needed work to complete the job will be included within the price.  
	Ea.
	1
	 
	 

	48
	Installation and Connection of PVC pipes:
 Supply, install, connect, testing and commissioning PVC pipes of SN8 drainage 6 bar from Egyptian origin , starting from fixtures down to manholes and septic tank, The work includes excavation (40x60cm), backfill, covering the pipes at the joints with concrete 10 cm from all sides using sulphate resistant cement with all installations and connections accessories and fittings, Elbows, Tees, PVC p trap, gully trap .. etc.), with all the required works to complete the Job. As following:
	 
	 
	 
	 

	A
	PVC Pipe of 6 inch diameter.
	M.l
	30
	 
	 

	B
	PVC Pipe of 4 inch diameter.
	M.l
	40
	 
	 

	C
	PVC Pipe of 3 inch diameter.
	M.l
	12
	 
	 

	49
	Cast Iron Ventilation Pipe for Septic Tank
Supply materials, tools and manpower to install new cast iron ventilation pipe of 3-inch diameter for Septic tank, the works includes all required civil works and installation accessories, with all works to complete the job.
	M.l
	5
	 
	 

	50
	Concrete Manholes:
Supply materials, tools and manpower to construct a fair faced concrete manholes using steel frame as below dimensions with plain concrete of 21 Mpa compressive strength and 10 cm thick for all works (Floor and walls) using sulphate resistant cement, the work includes soil excavations to any required depth, spreading two layer of sub-base layer “Class B”  shall be applied in layers of 25 cm thick, watered, leveled and well compacted, with manhole hard plastic manhole covers, with all requirements to complete the job. As per below dimensions:
	 
	 
	 
	 

	A
	Manholes of 60 x 60 cm
	Ea.
	6
	 
	 

	B
	Manholes of 40 x 40 cm
	Ea.
	2
	 
	 

	51
	Floor Drain:
Supply and install 4” PVC floor gully trap of 100mm diameter. Price to includes (15x15) double chrome plated cover, all required pipes and fitting to connect it with the main sewage pipes, excavation, concreting around pipes and gullies, which should be distributed according to the directives of the Engineering Committee and the attached drawings. All needed work to complete the job will be included within the price.
	Ea.
	6
	 
	 

	52
	Roof Drain pipes:
Supply, installation, testing and commissioning 4" PVC pipe of 10 bar of Egyptian origin, properly fixed with brackets to the wall and the slab, complete with all fittings and accessories for draining rain water from the roof. With all required hanging accessories, fittings and vent caps and all the required works to complete the Job.  
	M.l
	40
	 
	 

	53
	Eastern style toilet:
Supply and Install ceramic eastern toilet of Turkish or Iranian origin of (50 x 60) cm dimension, White, complete with flush tank "kahramana type", fitting, stop, valve side tap and with water toilet mixer (hot & cool) with handheld shower of Turkish origin, all sewage and  potable water pipes to connect it with networks, installing and connecting gully trap of 100mm diameter, toilet brush and holder and all the required works to complete the Job.
	Ea.
	2
	 
	 

	54
	Western style toilet:
Supply, install, connect and test western ceramic toilet of Turkish or Iranian origin, price should include fitting, stop, valve side tap and with water toilet mixer (hot & cool) with handheld shower of Turkish origin, all sewage and  potable water pipes to connecting it with networks, with toilet brush and holder and all the required works to complete the Job.
	Ea.
	1
	 
	 

	55
	Ceramic wash basin:
Supply, install, connect and test white ceramic wash basin with stand of western, Turkish or Iranian origin, size (60 X 50) cm complete with all fittings, valves, gully-trap, all sewage and  potable water pipes to connecting it with networks, the price also includes the water mixer- first class of Turkish origin with all connections and installations accessories, stainless steel toilet accessories ( soap basket,  wall toilet paper holder, mirror of 35x50 cm dimension and any other necessary parts with all the required works to complete the Job.
	Ea.
	4
	 
	 

	56
	Galvanized Water Tank:
Supply and install galvanized steel gage 16 water tank of 2000 Lit. capacity and Cylindrical shape. Price to include concrete stand and, supported by steel base made with 50mm (2") angle shape, float ball valve, valves, fittings, vents, check valves, connecting the tanks with the water distribution network of building and main water, and all necessary works to complete job.
	Ea.
	2
	 
	 

	57
	PPR pipes:
Supply materials, tools and manpower to install, connect and test (PPR) pipes of Yugoslav or Serb origin for the distribution water network (cold and hot water pipes)with isolate all hot water pipes by using arm flex and thermal tape and concreting 10cm around the pipes and the pipes from and to the water heater and the pipe which connecting the water network of the building and the source of main water network , price should include all connection and installations accessories and fitting as 90 elbow, tee and valve...etc., the work include connecting the project portable water network with water main source of the region which the PHCC is located, installing the pipe in walls, roofs and floor, testing the water pipes network for the building as per technical specifications with all the required works to complete the Job. As shown below:
	 
	 
	 
	 

	A
	PPR pipes of 1 inch diameter
	M.l
	100
	 
	 

	B
	PPR pipes of 3/4 inch diameter
	M.l
	65
	 
	 

	58
	Galvanized iron water pipes
Supply, install and test galvanized water pipes "class A" SCH40 of 1 inch diameter to connect and transfer water from and to water tanks which should be installed on the building roof. The price includes all fittings and accessories such as 90 elbow, tee and valve...etc., the work include installing the pipe in walls, roofs and floors, excavation, backfilling, painting the pipes using 3 layers of anti-rust then isolate all hot water pipes by using arm flex and thermal tape and Teflon seal for connections of cold and hot water pipes and concreting 10cm around the pipes, all needed work to complete the job will be included within the price. As shown below: 
	M.l
	50
	 
	 

	59
	Taps: 
Supply and connect chrome water taps 3/4". Price of the work shall include all water connections, all pipes and fitting to connecting it with water distribution network and the taps locations should be determined by the engineering committee inside and outside the building. All needed work to complete the job will be included within the price. 
	Ea.
	6
	 
	 

	60
	Stainless Steel Double Bowl Sink:
Supply of materials, tools and manpower to install and commission of stainless steel double bowl sink (150x60cm). Complete with: chrome mixer for sinks of Turkish origin, waste outlet, tail piece, P-trap chrome, chrome plated 14mm and all required parts, gully –trap, fittings, valves, in addition to aluminum sink cabinet storage (Aluminum Countertop) which consist of aluminum frame, heavy section of 1.3 mm and width not less than 5.0 cm aluminum sections and aluminum panel lambri of Turkish origin, each aluminum countertop piece containing 3 doors with aluminum shelves inside. The work includes, connecting it with networks of sewage and potable water, all needed work to complete the job will be included within the price.
	Ea.
	1
	 
	 

	D: Electrical Works
	 
	 
	 
	 

	 
	Notes:
The items prices below should be included the following:

1- The works should be included the provision, installation, connection, operation and inspection of all the materials in their locations according instructions of the engineering committee, then testing the electrical network of the building, with all requirements to complete the job.

2- The work shall be according to the technical specifications and the materials shall be first class and original not commercial or imitative. The required brand for electrical cables, wires, electrical PVC conduits to pull the wires, fittings, galvanized steel electrical boxes for sockets and electrical switch of Gulf or Jordanian origin. Lighting fixtures (ceiling or walls), bulbs, electrical lamp holders, LED projects and flood lights, celling fans, electrical sockets, metal distribution board box and switches of English, French origin or equivalent. Main and sub distribution boards, MCCB and MCB circuit backers and MCB Distribution Boards with all their accessories of ABB, Schneider, Siemens or equivalent.

3- The electrical PVC conduits which will use to pull the wires of lighting fixtures and electrical sockets and switches..etc. should be installed inside the concrete roofs not on their outer surface.

4-  The contractor shall submit samples of all materials before providing to be approved or rejected them by engineering committee.
5- All electrical works should be subjected technical specifications (please see attached).
	 
	 
	 
	 

	
	
	
	
	
	

	61
	One Gang Switched Socket of 13 Amp Capacity 
Supply, install, connect, test and commission electrical point with electrical Plug switch one gang of 13 Amp capacity using single copper wires of  4 mm2 and (1x2.5) mm2 for earthing which must be installed in the walls according to the heights mentioned in the attached drawings, the work includes supplying and installing galvanized steel electrical box, pulling wires inside PVC conduits  and connecting it to MCB distribution board with all installation and connection accessories, and all the required works to complete the Job . Please see attached drawings.
	Ea.
	58
	 
	 

	62
	Two Gang Switched Socket of 13 Amp Capacity 
Supply, install, connect, test and commission electrical point with electrical Plug switch two gang of 13 Amp capacity using single copper wires of 4 mm2 and (1x2.5) mm2 for earthing which must be installed in the walls according to the heights mentioned in the attached drawings, the work includes supplying and installing galvanized steel electrical box, pulling wires inside PVC conduits  and connecting it to MCB distribution board with all installation and connection accessories, and all the required works to complete the Job . Please see attached drawings.
	Ea.
	18
	 
	 

	63
	Waterproof one Gang Switched Socket of 13 Amp Capacity and IP54
Supply, install, connect, test and commission electrical point with electrical waterproof Plug switch one gang of 13 Amp capacity and IP54 using single copper wires of  4 mm2 and (1x2.5) mm2 for earthing which must be installed in the walls according to the heights mentioned in the attached drawings, the work includes supplying and installing galvanized steel electrical box, pulling wires inside PVC conduits  and connecting it to MCB distribution board with all installation and connection accessories, and all the required works to complete the Job . Please see attached drawings.
	Ea.
	5
	 
	 

	64
	One Gang Switched Socket of 15 Amp Capacity 
Supply, install, connect, test and commission electrical point with electrical Plug switch one gang of 15 Amp capacity using single copper wires of  4 mm2 and (1x2.5) mm2 for earthing which must be installed in the walls according to the heights mentioned in the attached drawings, the work includes supplying and installing galvanized steel electrical box, pulling wires inside PVC conduits  and connecting it to MCB distribution board with all installation and connection accessories, and all the required works to complete the Job . Please see attached drawings.
	Ea.
	8
	 
	 

	65
	Double Pole Switch of 45 Amp with Neon
Supply, install, connect, test and commission electrical point with double pole socket of 45 Amp capacity and IP54 with neon for air conditioning devices and water heaters using single copper wires of 4 mm2 and (1x2.5) mm2 for earthing which must be installed in the walls according to the heights mentioned in the attached drawings, the work includes supplying and installing galvanized steel electrical box, pulling wires inside PVC conduits  and connecting it to MCB distribution board with all installation and connection accessories, and all the required works to complete the Job . Please see attached drawings.
	Ea.
	15
	 
	 

	66
	Triple Pole MCB of 63 Amp Capacity
Supply, install, connect, test and commission electrical point with triple pole MCB of 63 Amp capacity for three phase air conditioning devices using single copper wires of 6 mm2 and (1*2.5) mm2 for earthing which should be installed in the walls according to the heights mentioned in the attached drawings, the work includes supplying and installing  MCB plastic cover, pulling wires inside PVC conduits of 25 mm diameter and connecting it to MCB distribution board with all installation and connection accessories, and all the required works to complete the Job. Please see attached drawings. 
	Ea.
	2
	 
	 

	67
	Electric bell
Supply, install, connect, test and commission electric bell 220VAC/5 W, Wall Mounting and the sound level to be  ISO 9001:2000 , for voltage 230VAC to be 68 dB to 108 dB sound level at 2 ft. & 2900 Hz operating frequency with electrical switches of 10 Amp capacity(bell push switch), using single copper wires of 2.5 mm2 and (1*1.5) mm2 for earthing , the work includes supplying and installing galvanized steel electrical box, pulling wires inside PVC conduits and connecting it to MCB distribution board with all installation and connection accessories, and all the required works to complete the Job.    
	Ea.
	4
	 
	 

	68
	Ceiling Fan and Exhaust Fan
Supply, install, connect, test and commission electrical installations with electrical switches of 10 Amp capacity according to the kind of gangs and ways for electrical switches which mentioned in the attached drawings, the electrical switches should be installed on the 120 cm height from ground level of the building using single copper wires of 2.5 mm2 and (1*1.5) mm2 for earthing , the work includes supplying and installing galvanized steel electrical box, pulling wires inside PVC conduits and connecting it to MCB distribution board with all installation and connection accessories, and all the required works to complete the Job. The electrical installations are as following:  
	 
	 
	 
	 

	A
	Ceiling fan of 56 inch with Fan Speed Control Switch
	Ea.
	16
	 
	 

	B
	Exhaust fan of 8 inch diameter with electrical switch of 10 Amp capacity
	Ea.
	12
	 
	 

	C
	Exhaust fan of 12 inch diameter with electrical switch of 10 Amp capacity
	Ea.
	3
	 
	 

	69
	Lighting Fixtures
: Supply, install, connect, test and operate lighting fixtures with electrical switches of 10 Amp capacity according to the kind of gangs and ways for electrical switches which mentioned in the attached drawings, the electrical switches should be installed on the 120 cm height from ground level of the building using single copper wires of 2.5 mm2 for main wires from MCB Distribution Boards and single wires 1.5 mm2 for sub wires which feeding the lighting fixtures and earthing wires , the work includes supplying and installing galvanized steel electrical box, pulling wires inside PVC conduits and connecting it to MCB distribution board with all installation and connection accessories, and all the required works to complete the Job. The lighting fixtures are as following:  
	 
	 
	 
	 

	A
	LED Ceiling Tiles Lights (LED Surface Lights) of 42 Watt, 6500K, 4200 Lumens and 60 x 60 cm dimensions
	Ea.
	64
	 
	 

	B
	Waterproof LED Ceiling Light (LED Surface Lights) outdoor of 24 Watt, IP65, 6500K and 4200 Lumens
	Ea.
	11
	 
	 

	C
	Waterproof LED Ceiling Light (LED Surface Lights) of 24 Watt, IP65, 6500K and 4200 Lumens  for sanitary units
	Ea.
	5
	 
	 

	D
	Modern waterproof outdoor wall lighting fixtures (Lantern) with Led bulb lights ( Economic Bulb) of 20 watt  
	Ea.
	23
	 
	 

	E
	Big modern outdoor wall lighting fixtures (Lantern) with Led bulb lights ( Economic Bulb) of 40 watt which should be installed on the  columns of front fence wall with all installations and connections accessories
	Ea.
	6
	 
	 

	F
	 Outdoor LED flood light (Waterproof) of 200 Watt,  It should be installed  in the rooftop of the building .
	Ea.
	6
	 
	 

	70
	COB LED Street Light Fixture of 100 Watt 
Supply, install, connect, test and commission COB LED street light fixture of 100 Watt, 2 COB and 12000 lm Lamp Luminous Flux with all installations and connections accessories which should be installed on the back and side walls for the fence, the work includes, supplying and installing galvanized pipe of 2-inch diameter that should be installed in the concrete columns during casting the columns consist of columns of 1.2 m and two arms of 1 m for each arm, and all the required works to complete the Job.
	Ea.
	6
	 
	 

	71
	Cables
Supply, Install, connect, test and commission cables, the price should include supplying, installing, testing, commissioning materials, workmanship, equipment, machinery, trenching, all installation and connection accessories, the work includes pulling the cables that will come out from distribution boards to out side the buildings  underground with  excavation of trench  cables path  not less than 70 cm depth, spreading 30 cm river sand bedding around the cables, spreading the rest of trench depth with sub-base layers " Class B"with well compaction in layers so that the thickness of each layer does not exceed 20 cm, putting Underground Warning Tape along cables path, pulling the cables  inside the PVC pipe of 10 bar in areas that intersect with the cars crossing areas and covering the pipe with 0.3 m plain concrete cover and pulling the cables that must feed the distribution boards inside the PVC pipes which should be installed in the walls well with excavation works for the pipe trench in the wall with plain concrete cover. The cables must be one length from the electric feeding sources to the electrical distribution boards, ie, it is not permissible to make joints when laying the cables,  with all the required works to complete the Job.This items includes the cables shown below
	 
	 
	 
	 

	A
	Armored cable of (4x95) mm²+(1x50) mm² to feed the main distribution board for the project from the ATS, in addition to feed the ATS from electrical distribution board of the transformer and from the generator to ATS 
	M.l
	40
	 
	 

	B
	Unarmored cable of (4x25) mm²+(1x16) mm² to feed the MCB Distribution Boards P1, P2 and SP3 which are shown in attached drawings from the main distribution board of the project.
	M.l
	60
	 
	 

	C
	Armed 4x6 mm2 to feed the sub distribution boards of the external lighting which should be installed outside the building in the area determined by the supervisory committee from main distribution board of the treatment unit.
	M.l
	30
	 
	 

	D
	Flexible cable of 2x6 mm2   to feed the outdoor lighting Fixtures distributed around fence wall and from sub distribution boards of the external lighting.  
	M.l
	150
	 
	 

	72
	Galvanized Cable Trays  
Supply, install galvanized cable tray of the dimensions are shown below and plate thickness not less than 1.0 mm, which should be installed above false ceiling of the building using rawl polts to install and lay all cables on smoothly which feeding building parts as per attached drawings and according to the supervisory committee directions, with all the required works to complete the Job. As following:
	 
	 
	 
	 

	A
	Galvanized cable tray of W20 x h5 cm
	M.l
	25
	 
	 

	B
	Galvanized cable tray of W10 x h5 cm
	M.l
	12
	 
	 

	73
	Manhole 
Supply materials, tools and manpower to build manhole of (30x30x30)cm dimension using bricks and cement mortar (1:3) the work includes  plastering using cement- sand mortar (1:3) and installation of hard plastic cover of 40x40 cm with all the required works to complete the Job.
	Ea.
	3
	 
	 

	74
	24 Ways MCB Distribution Boards
Supply, install, connect, test and commission of 24 ways, TP + N bus bar type distribution board Combination bus bar and Din Rail, 2 row, 24 ways. of modules (distance between rows 150mm), contain of earth leakage circuit breakers for water heaters, with single door complete with accessories and separate neutral strip to accommodate incoming miniature circuit breaker (MCB) triple pole and 100 Amp capacity with bus bar of 150 Amp and outgoing SP MCBs, with all installations and connections accessories and all the required works to complete the Job.
	Ea.
	3
	 
	 

	75
	Main Distribution Board (MDB)
Supply, install, connect, test and commission prefabricated metal Main distribution board (MDB) of 120 cm x 80 cmx 40cm dimensions with metal stand, the work includes installing and connecting the digital screens for Ammeter, voltage and frequency meters with labels and all internal and external connection and installations accessories (connections, cables, fuses, phase, neutral and earthing bars, Isolators...etc.), and all the required works to complete the Job, which consist of:
A-1 Main circuit breaker of three phase and 250 Amp , 380 Vol ;
B- 3 MCCB 3PH 380 Vol, 100 Amp;
C-1 MCCB 3PH 380 Vol, 63 Amp;
D- 2 MCCB 3PH 380 Vol, 100 Amp (spare parts);
E- Set bus bar 3 PH 380 Vol,400 Amp and sub-busbar strips with different capacities according to the circuit breakers capacities in the MDB;
F-1 Three pole, LED Digital Voltage, frequency and Amperage meter with CT;
G-3 Indicator lamp 220VAC for each phase;
H- 2 Timer 
I- 1 Phase failure  
 
	Ea.
	1
	 
	 

	76
	Sub Distribution Boards of the External Lighting:  
Supply, install, connect, test and commission prefabricated metal sub distribution board 50 cmx 40cm dimensions which is used to control the external lighting of the fence wall and which should be installed outside the building in the area determined by the supervisory committee, consist of main (MCCB) 3PH380 Vol, and 40 Amp, contactor of 40 Amp, selector switch Auto- Manual (M-O-A), photocell  with all its accessories and four circuit breakers single phase  (MCB) of 30 Amp capacity. All connection and installation accessories, labels and indicator lamps with all the required works to complete the Job.

	Ea.
	1
	 
	 

	77
	Three Phase Electric Meter
Supply, install, connect, test and commission three phase electric meter of German origin which must be subjected to the specifications of the Iraqi Ministry of Electricity, the price should include, installing it inside a waterproof metal board of suitable size for the size of the meter and in the place determined by the supervisory committee, all required cables, wires, fittings, terminal, all installation and connection accessories according to the supervisory committee directions, and all the required works to complete the work.
	Ea.
	1
	 
	 

	E: Mechanical Works
	 
	 
	 
	 

	78
	 Air-Conditioning Split Units 
Supply, install, connect and test air-conditioning split units as per capacities shown below, heating and cooling, the compressor type T3 rotary compressor and gas type "Freon gas R410A", and wall type, the work includes, supplying, installing and connecting drain pipes inside the walls using PPR pipe of 3/4 inch with all required fittings to the nearest drain point,  all required sleeve pipes from PVC pipe of 3 Inch diameter with all required fittings which should be installed in the walls and during cast the slab to connect the all the refrigerant piping to the condensing unit from indoor unit to outdoor unit which should be installed on the roof. The price should include, all the refrigerant piping to the condensing unit (from indoor unit to outdoor unit), all wiring, electrical controls, a steel base stand and steel sunshade for the outdoor unit, protection devices and all installation and connection accessories required, the required brand is Tosot or York.  For more details, please see attached the Compliance sheet.
	 
	 
	 
	 

	A
	Air-Conditioning split units of 1.5 Ton capacity
	Ea.
	5
	 
	 

	B
	Air-Conditioning split units of 2 Ton capacity
	Ea.
	7
	 
	 

	79
	Air-Conditioning Split Units of 3 Ton Capacity
Supply, install, connect and test air-conditioning split units of 3 Ton capacity, heating and cooling, the compressor type T3 rotary compressor and gas type "Freon gas R410A", floor standing type, the work includes, supplying, installing and connecting drain pipes inside the walls using PPR pipe of 3/4 inch with all required fittings to the nearest drain point. The price should include, all the refrigerant piping to the condensing unit (from indoor unit to outdoor unit), all wiring, electrical controls, a steel base stand for the outdoor unit, protection devices and all installation and connection accessories required, the required brand is Tosot or York.  For more details, please see attached the Compliance sheet.
	Ea.
	1
	 
	 

	80
	Air-Conditioning Split Units of 4 Ton Capacity
Supply, install, connect and test air-conditioning split units of 4 Ton capacity, heating and cooling, floor standing type and three phase, the compressor type T3 rotary compressor and gas type "Freon gas R410A", the work includes, supplying, installing and connecting drain pipes inside the walls using PPR pipe of 3/4 inch with all required fittings to the nearest drain point. The price should include, all the refrigerant piping to the condensing unit (from indoor unit to outdoor unit), all wiring, electrical controls, a steel base stand  for the outdoor unit, protection devices and all installation and connection accessories required, the required brand is Tosot or York.  For more details, please see attached the Compliance sheet.
	Ea.
	2
	 
	 

	81
	Electrical Water Heater 
Supply, install, connect, and commission electrical heater of 160 Liter capacity. The price includes supplying, installing, connecting, laying and commissioning drilling, cutting, all pipes, fitting, valves, check valves, relief valves and steel base and connect it with the electrical source using cable (3*2.5) mm2, with all the required works to complete the Job.
	Ea.
	2
	 
	 

	82
	Water Pump:
Supply, install and  connect water pump  with motor(1.1 kW, 220 V, 50 Hz ), Q=3 m3/Hr@ H=15 m.  check valve and strainer for connecting the pump suction pipe to the main water source pipe and connecting the discharge of the pump with pipe going up to the tanks, also the pump should have pressure switch on the pump for shut down the pump when the tank is filled . The work includes all connection and installation accessories, pipes, fitting and the electrical connection using 1.0 kV grade PVC insulated copper cable 2x2.5 mm² with main cable with all  accessories  to complete work as required.


	Ea.
	1
	 
	 

	F:  Systems of Fire Detection and Alarm, Telephone, TV, CCTV and Earthing
	 
	 

	83
	Fire Detection and Alarm System.
Supply, Install, connect, test and commission an analogue addressable fire-alarm control panel included of all equipment and accessories, batteries, battery charger, internal conductors and/or cables, switches, spare parts and warranty for 3 years, the Fire alarm detector point, Complete with steel conduits, boxes, junctions, FPLR fire resistance cable (2X1.5 mm2+0.8mm) and all accessories, from fire alarm panel to addressable detector or break glass fire call point, the required brand is English, German or French origin. Certificate of origin or BV inspection are required, as specified according to technical specification, please see attached drawings.
	 
	 
	 
	 

	A
	Main Fire Alarm Control and Annunciator Cabinet ( 1 Loop) 
	Ea.
	1
	 
	 

	B
	Smoke Detector
	Ea.
	16
	 
	 

	C
	Flasher with Siren
	Ea.
	2
	 
	 

	D
	 Break glass pushbutton switch or manual call point. 
	Ea.
	2
	 
	 

	84
	Telephone Central System 
Supply, Install, connect, test and commission telephone central system for the telephone communication as specified according to technical specification. Please see attached drawings, which including the following:
	 
	 
	 
	 

	A
	 Supply, Install, connect, test and commission automatic electronic telephone central system of 20 internal lines and 2 external lines which must include all required telephone cables from MDF with it, all accessories, necessary connections and installations, with wooden desk of 180cm length and UPS of 3000VA capacity. The required brand is English, French or  Japanese origin, with all the required works to complete the Job
	Ea.
	1
	 
	 

	B
	 Supply, install, connect and test high quality main telephone destitution board (MDF) of 32 lines which should be installed in the walls, with all installation and connection accessories, with all the required works to complete the Job. 
	Ea.
	1
	 
	 

	C
	 Supply, install, connect, test and operate 1 Gang RJ11 Phone Socket which should be installed on the 45 cm height from ground level of the building using telephone wire of 2 pair. The work includes all wires (from sockets until the MDF), supplying and installing galvanized steel box (J- box), PVC conduits which should be installed above false ceiling of the building  pulling wires inside PVC conduits in the walls with all installation and connection accessories, and all the required works to complete the Job.  
	Ea.
	12
	 
	 

	D
	Telephone desktop set of Japanese origin with LCD display and Caller ID display facility with wooden table of 78 cm height and 50x 50 dimensions , the required brand Sonny
	Ea.
	12
	 
	 

	85
	TV System
Supply, Install, test and commission TV system, the required brand is English, French, Japanese or equivalent, as specified according to technical specification:  
	 
	 
	 
	 

	A
	Satellite Socket   
Supply, install, connect, test and operate single satellite socket wall plate which should be installed on the 45 cm height from ground level of the building using high quality RG6 coaxial cable. The work includes all cables (from socket to the dish), laying the cables, supplying and installing galvanized steel box (J- box), pulling wires inside PVC conduits in the walls with all installation and connection accessories, and all the required works to complete the Job.  
	Ea.
	4
	 
	 

	B
	Receiver Dish Satellite 
Supply, install, connect and test high quality receiver dish satellite of 1.5m diameter with quad LNB of four outputs ASWAR Type, dish steel stand and all its accessories, and all the required works to complete the Job
	Ea.
	1
	 
	 

	86
	CCTV System Points
Supply materials, tools and manpower to install CCTV system points which will be distributed on site as per attached drawings and supervisory committee directions to cover the project areas, the work include supplying, installing and connecting thick waterproof PVC square junction box for CCTV cameras of IP65 and12 x12 cm dimensions , RG59 coaxial CCTV cable with VDE power cable which should pull in PVC conduits from determined camera point to the metal board inside the reception or any room determined by the supervisory committee ( this PVC conduits should be installed above false ceiling) and metal board of 50 x 50 cm, single airtight door with lock which should be installed inside the wall to be assembled all cables inside it, the cables must be one length from the camera box to the metal board, i.e., it is not permissible to make joints when laying the cables. The price should include, marking or number each cable with its camera box, all installation and connection accessories, all required fittings. All needed work to complete the job will be included within the price. 
	Ea.
	12
	 
	 

	87
	Earthing system:
Supply, install and connect earthing system for the building consists of three copper rods( each length 1.5 m, 16 mm dia), connected together by copper wire of (1 x25) m² to form triangle shape ( on the surface/ground with each side length of 3 m from each other  and copper wire buried at 2 m deep). work include the excavation of three earthing pit ( depth of 2m each) .The price includes supplying, installing, connecting, laying and commissioning drilling, cutting, digging/excavating and backfilling with mixture of layers (sand, salt and charcoal) and all the required works to complete the Job.  
	Ea.
	1
	 
	 

	G: Supplying The PHCC with an Electrical Current from Main Electrical Source
	 

	88
	Electrical Transformer of 250 kVA capacity
Supply, install, connect, test and commission electrical transformer of 11/0.416 kV and 250 kVA capacity, Turkish or KSA origin, compatible with the Ministry of Electricity specifications- transformer technical specification IEC-60076 with all electrical connection and installation accessories. certificate of origin and inspection documents are required. For more details, please see Annex A (D-26).
	Ea.
	1
	 
	 

	89
	Electrical Distribution Board
Supply, install, connect, test and commission low voltage electrical distribution board of 400V capacity consist of metal box, circuit breaker of 3 phases and  250 Amp capacity, busbars, voltage/amperage meters, clands and all accessories, preferred brand is ABB, Schneider or Siemens; the  metal box must be suitable to be fixed on tubular pole, waterproofing. The electrical distribution board and its accessories should be suitabled to operate under heavy load and short circuit system. For more details, please see Annex A (D-09).
	Ea.
	1
	 
	 

	90
	Galvanized Tubular Steel Pole of 11m height
Supply and install galvanized tubular steel pole of Turkish origin and 11m height, the work includes excavation in any soil type, spreading two layer of sub-base layer “Class B”  shall be applied in layers of 25 cm thick, watered, leveled and compacted and one layer of thick agricultural nylon of 1 mm, casting the concrete base of the pole of 40 x 40 x 210 cm dimensions with plain concrete of 21 Mpa compressive strength using steel mold, coating the concrete base from all sides with two layers of liquid bitumen primer for waterproofing (flancote), filling the sides of the excavation using compacted sub-base layers class B, with all connection and installation accessories and all the required works to complete the work. For more details, please see Annex A (D-22).
	Ea.
	2 
	 
	 

	91
	Galvanized Lattice Steel Pole of 11m height
Supply and install galvanized Lattice steel pole of Turkish origin and 11m height, the work includes excavation in any soil type, spreading two layer of sub-base layer “Class B”  shall be applied in layers of 25 cm thick, watered, leveled and compacted and one layer of thick agricultural nylon of 1 mm, casting the concrete base of the pole of 40 x 80 x 210 cm dimensions with plain concrete of 21 Mpa compressive strength using steel mold, coating the concrete base from all sides with two layers of liquid bitumen primer for waterproofing (flancote), filling the sides of the excavation using compacted sub-base layers class B, with all connection and installation accessories and all the required works to complete the work. For more details, please see Annex A (D-46).
	Ea.
	0 
	 
	 

	92
	Steel Channel of  220 cm length
Supply, install and connect heavy steel channel of  220 cm length (for transformer base and expulsion fuse cutout fixation) with clamps and screws, the channel must have suitable holes and be painted with two layers of  anticorrosion paint and two layers of silver oily paint and as per the specifications of the Ministry of Electricity.
	Ea.
	3
	 
	 

	93
	Expulsion Fuse Cutout of 11 KVa
Supply, install, connect, test and commission expulsion fuse cutout of Turkish origin and 11kVa capacity, with all connection and installation accessories and all the required works to complete the work. For more details, please see Annex A (D-25).
	Set
	1 
	 
	 

	94
	Earth Rod Copper Bar
Supply, install and connect earth rod copper bar of 1/2 inch diameter and 1.5m length with clamp, with all connection and installation accessories and all the required works to complete the work and as per the specifications of the Ministry of Electricity.
	Ea.
	1
	 
	 

	95
	Copper Conductor of 70 mm
Supply, install and connect copper conductor of 70 mm2 to connect between transformer and earth rod copper bar, with all connection and installation accessories, cable terminals (lugs) and all the required works to complete the work. For more details, please see Annex A (D-47).
	M.l
	20
	 
	 

	96
	Surge Arrester of 11 kV capacity
Supply, install and connect surge arrester of Turkish origin and 11 kV capacity, with all connection and installation accessories and all the required works to complete the work.  For more details, please see Annex A and as per the specifications of the Ministry of Electricity.
	Set
	1
	 
	 

	97
	PVC insulated Single Core LV Cu Cable of 1x120 mm2
Supply, install and connect PVC insulated single core LV Cu cable of 1x120 mm2 of Turkish origin to connect between the transformer and the electrical distribution board under the transformer, with all connection and installation accessories, cable terminals (lugs) and all the required works to complete the work. For more details, please see Annex A.
	M.l
	22
	 
	 

	98
	Pin Insulator with Spindle of 11kVA Capacity
Supply, install and connect pin insulator with spindle of Turkish origin and 11kVa capacity, with all connection and installation accessories, bolts and all the required works to complete the work. For more details, please see Annex A (D-24).
	Ea.
	2
	 
	 

	99
	Disk Insulator of 11kVA Capacity
Supply, install and connect disk insulator of Turkish origin and 11kVA capacity with its accessories (couple disks of 11kVA with the ring, socket A, A and U bolt),with all connection and installation accessories, and all the required works to complete the work. For more details, please see Annex A  and as per the specifications of the Ministry of Electricity.
	Ea.
	10
	 
	 

	100
	AAC Conductor of (95) mm2
Supply, install, connect, test and commission all aluminum conductor (AAC) of (95)mm2, with all connection and installation accessories, terminals and all the required works to complete the work. For more details, please see Annex A (D-47).
	M.l
	150
	 
	 

	H: Supply, Installation and Connection of New Generators for PHCC
	 
	 

	101
	Generator of 150 kVA Capacity 
Supply, install, connect, test and operate generator of 150 kVA capacity (50Hz/400V) silent type and 6 cylinders, the required brand is Perkins or caterpillar, the work includes supplying, installing and connecting  galvanized fuel tank(Cylindrical shape) of 3,000 ltr capacity to be installed on concrete base with all the required accessories and connectors, with all requirements to complete the job. Certificate of origin and inspection documents are required. For more details, please see attached the technical specifications and compliance sheet.
	Ea.
	1
	 
	 

	102
	Automatic Transfer Switch (ATS) of 630 Amp Capacity
Supply, install, connect, test and operate automatic transfer switch (ATS) of three phase and 630 Amp capacity with the metal board of 80x40x30 cm size, pass bars, timers, relays, cables, control switchboard and multi digit screens (V, A, Hz). Preferred brands are ABB, Schneider, Siemens, with steel frame to install the metal board, all electrical installation and connection accessories, and all the required works to complete the Job.  
	Ea.
	1
	 
	 

	103
	Concrete with BRC for Generator Base Floor
Supply materials, tools and manpower to cast the generator floor, the work includes leveling the ground, compaction of existing soil, spreading sub-base layer compacted with 95% degree of compaction and 25 cm thick, spreading thick agriculture nylon layer and casting with compressive strength 21 Mpa reinforcement sulphate resistance concrete with BRC layer of 6 mm thick, smooth surface and 15 cm thick using Helicopter for leveling concrete surface, the price should include making expansion joints every 4m both directions , according to the mentioned places in the attached drawings  and all the required works to complete the work.
	M2
	16
	 
	 

	104
	Generator Metal Sunshade Works
supply materials, tools and manpower to install metal sunshade roof above the generator of 2.5m height, according to details below: 

- Steel square column of 3x3 inch and 4 mm thick and the distance from column and another should not be more than 3 m.

- Base plate of 25x25 cm dimension10 mm thick to install the sunshade steel structure with concrete base floor using rot bolts of 18 mm diameter with all required works 

- Steel hollow square section for beams of roof structure of 3x3 inch dimensions and 4 mm thick.

- Steel hollow rectangular section for sub beam 1.5x3 inch and 3 mm thick.
            
-  0.8mm thick corrugated plates for the roof, fixed by screws and overlapped in order to prevent water leakage.

The work includes all cutting and welding works, painting with anti-rust and three layers of oil paint for all steel structure with all the required works to complete the Job.
	M2
	16
	 
	 

	I: Gardens Works 
	 
	 
	 
	 

	105
	Supply materials, tools and manpower to backfill the garden with clean soil and planting it as per the supervisory committee directions, the work includes the following: 
	 
	 
	 
	 

	A
	Backfilling with clean, blended and screened Loam soil layer in addition to free of impurities and salts of 40 cm thick.
	M3
	100
	 
	 

	B
	Supply and install concrete garden edge for the front garden of (75 cm) length and (35 cm) height with well installation using cement- sand mortar, the work includes painting using one layer of plastic based paint and three layers of oil based paints, and all the related accessories required to complete the Job
	M.l
	100
	 
	 

	C
	Supplying and planting American natural grass, It should be supplied in the form of pieces of 35x35 cm dimensions, each 2 pieces are divided into small pieces to cover 1m2 area
	Piece
	100
	 
	 

	D
	Supplying and planting the palm trees with not less than 2m length.
	E.a
	10
	 
	 

	E
	Supplying and planting the ficus tree with not less than 1.5m length.
	E.a
	10
	 
	 

	F
	Supplying and planting Rose flowers with not less than 1.m length.
	E.a
	30
	 
	 

	Total Cost $
	 
	 
	 
	 


1. The Bidder shall separately attach a breakdown of the Lump Sum amounts for the various activities for each landing site as shown below. 
Detailed Price Breakdown:  Construction of SUB- PHCC site
(i) PHCC/ facilities
(ii) General Works
(iii) Landscape and Protection works

(iv) Other Facilities







Signature………………………………………………………. 
(A person or persons authorized to sign on behalf of the Bidder)
Date: ……………………..


4.2.5 Cash Flow Projections

Each Bidder shall set out details of the Cash Flow Projection indicating quarterly projected expenditure throughout the duration of the Contract, both the percent of the Accepted Contract Amount and the cumulative percentage of the Accepted Contract Amount by quarter.  The Cash Flow Projections shall address the following, taking into consideration payment of the Advance Payment, amortization of the Advance Payment, withholding of the Retention, and release of the Retention:

(a) The periodic payments by milestones for the design and construction of the Design and Construction Works.

(b) The periodic payments based on measurement for the construction of the Design and Construction Works, as applicable.




[bookmark: _Toc6892699]
































PART 2 – EMPLOYER’S REQUIREMENTS
[bookmark: _Toc43358639]1.	Scope of Works
EMPLOYER’S REQUIREMENTS
1. [bookmark: _Toc478493531][bookmark: _Toc492910174]BACKGROUND
The requirement is to rehabilitate and construct SAMSIEH- Anbar sub PHCC. 
1.1 [bookmark: _Toc478493532][bookmark: _Toc492910175]LOCATION OF THE PROPOSED PHCC site: 
The project is located SAMSIEH.
2. [bookmark: _Toc478493533][bookmark: _Toc492910176]PROJECT OBJECTIVE
The overall objective of this project is to reconstruct and rehabilitate the PHCC in SAMSIEH by 30 May 2020 and with 4 months Defects Liability Period. The SAMSIEH sub PHCC  shall be designed and constructed as per the requirement of Ministry of Health  manuals, and other good industry practices and relevant codes and references. 
3. [bookmark: _Toc478493534][bookmark: _Toc492910177]SCOPE OF WORK 
The works to be completed by this contractor shall include design and execution of the construction and rehabilitation work as per each item in the BoQ.
4. [bookmark: _Toc478493536][bookmark: _Toc492910179]TECHNICAL REQUIREMENTS
4.1 [bookmark: _Toc492910182]Design Requirements for Civil/Structural 
All designs and documentation for the Construction/Structural works shall be in accordance with acceptable international standards with specific reference to the Euro code Standard (EC0-EC10) and Ministry of Health Design Manual and Latest British Standards;
(i) Euro code Standard (EC0, EC1,EC2,-EC10) and Latest BS EN for checking design
(ii) Drainage Design Manual
In addition the Contractor shall follow the requirements of the following documents in carrying out the services:
The Contractor shall undertake the detailed engineering design of the PHCC, SAMSIEH as per DOH Anbar Engineering Department.
4.2 [bookmark: _Toc492910184]Detailed Design
The safety and performance of all structural elements/parts shall be verified by structural and foundation engineering analysis (for computer-based calculations the type of programmers used shall be mentioned) using Euro code Standard or LATEST British Standard or any other current internationally recognized code of practice for which prior approval of the Client shall be required.  The loadings must, in any case, be identical with those regularly applied for the respective types of works and structures in Iraq the loading to be as per Euro code loading criteria. 
The PHCC shall be designed to the above requirements and detailed calculations  furnished to verify structural design and members sizing and specifications in accordance with the relevant parts of the Codes in use to ensure the ultimate and serviceability states of the structural parts during its life span is met.
Substructure elements shall be designed to comply with standard acceptable limit state requirements for stability with respect to sliding, overturning, bearing, settlement e.t.c, using codes applicable to substructure systems of this kind with appropriate safety factors applied.  
The Detailed Construction shall entail the preparation of detailed working drawings, project specifications and the appropriate documentation for construction purposes. The Detailed report of the SAMSIEH PHCC facility shall include, but will not be limited to, the following:

· All working drawings, schedules and designs required for the Construction Works in accordance with the applicable standards and codes of procedure listed herein;
1. Project specifications and other provisions required for the Construction Works;
2. Design changes to the drawings, to comply with the Engineering Requirements or as agreed by the Engineer/DOH- Anbar where applicable;
3. Plan and profile of the verified PHCC Facilities sites.
4. Design drawing(s) for the site consisting of a general arrangement drawing shall be submitted for approval prior to the commencement of the Detail Design. All approval requirements of other relevant authorities shall be adhered to;
4.3 [bookmark: _Toc492910185]Cost Estimates
Together with submission of their tender, the contractor shall furnish (separately sealed) their tender price for the undertaking the design and construction of the works in accordance to the agreed formats. Accordingly, the Estimate Bill of Principal Quantities for the intervention works based on unit prices in USD shall be issued. The estimates prepared at tender are not subject to change more than +5%unless expressly authorized by the Client.  The Client reserves the right to omit or alter items based on the available resources. 

4.4 [bookmark: _Toc492910186]Detailed Engineering Design Report
The Contractor shall submit a draft detailed design report complete and accompanied by all necessary documents within an agreed period after commencement.  Submission and approval of all reports will follow the process cycle shown below: 
The Contractor shall prepare at least three (3) copies of the Detailed Design that will be submitted to the client for review and concurrence.  These submissions to the Client shall be done simultaneously and in accordance with the agreed Detailed Design procedure.  The copies of the document shall comply with the following requirements: -
(a) Contract specifications and other documents printed on A4 size, 80 gms paper suitably bound in book format;
(b). Drawings reduced to A3 size and printed on 80 gms paper, suitably bound in book format.
ASB shall be provided with a set of drawings, in the agreed electronic format and as amended from time to time, within two (2) weeks after approval of the Detailed Design Drawings.





 
5. [bookmark: _Toc478493537][bookmark: _Toc492910187]REPORTING REQUIREMENTS 
The successful bidder shall be required to prepare the following technical reports 

	Report
	Timing
	Description

	Inception Report
	2 Weeks after start 
	Confirm methodology and work plan, implementation plan in MS Project, task assignment, project team and staff schedule Log-Frame indicators, project control plan, quality standards for design and construction etc. (02 Hard Copies and 01 Soft Copy)

	Design Criteria/ Statement  
	2 Weeks after start
	This shall articulate the design standards and options to be adopted for the PHCC Facility. The Statement shall encompass all relevant components of the design cycle and propose the standards to be adopted. (02 Hard Copies and 01 Soft Copy

	Draft Detailed Design Report
	2 Weeks after start
	The Report shall include a concise Design Statement that provides a summary of all design standards, criteria and assumptions used to prepare the design, and shall include the detailed design narrative, (03 Hard Copies and 02 Soft Copies)

	Construction Program and Scheduling Report 
	4 weeks after start date
	Schedule of Construction works indicating Camp establishment, Mobilization, materials supply, construction and scheduling of various works components etc. Cash flow for the construction works, methodology of execution, work progress report template etc. (02 Hard Copies and 01 Soft Copies)

	Works Commencement Report
	6 weeks after start date
	Status of mobilization, approvals to commence, site access, procurement of suppliers etc.

	Works Progress Reports
	Every 5th day of the month for the reporting of the previous month. 
	As above, updated for monthly activities completed and progress look ahead. (02 Hard Copies and 01 Soft Copies)

	Project Completion  Report 
	4 months After Start 
	Report shall explicitly document on all activities executed including surveys, investigations, design standards, construction work challenges, value engineering adopted, departures from standards, status of payments, materials specifications applied, as built drawings, operations and maintenance recommendations  etc. 

	Project Handover Report 
	8 months After start 
	Same as above but with Final accounts statement, report on defects liability period 



(a) Meetings of the Contractor and the Client

The Contractor will ensure that regular meetings and interfaces with the Client are held during the assignment.  It is expected that at least the contractor shall be proactive in seeking for and organizing such meeting to clarify on aspects of the assignment as and when required in a timely fashion.  This shall also include interfacing with other stakeholders of the project.



(b) Meetings of the Contractor and stakeholders or end users

The Contractor shall propose a regular schedule for such meetings/interface and proceed to arrange, convene and meet the arising cost. The end users are DOH Anbar and DOH Anna and or their official delegates.

(c) Particular requirements for reporting and approvals

· Form and language of reports: The Contractor shall submit written reports in the English Language, in addition to drawings and other pertinent technical illustrations, at the end of each stage.
· The Contractor shall take into account all comments received from concerned parties and modify or cause to be modified the reports, drawings and documents accordingly.
· All data shall be in units of the metric system and all prices shall be quoted in Iraqi dinar (USD).
· The general paper format for the presentation of reports shall be size A4 (210 x 297mm) with A4 multiples folded down to that size, except for drawing where appropriate paper sizes shall be used.
· The Contractor shall bear the cost of printing and reproduction of all reports and documents under this assignment as well as all associated cost of submissions and obtaining of approvals/Comments as appropriate.
· Reports shall be submitted both in soft copy (on a CD) as well as in hard. The form and number of copies is scheduled in the next table.
· Contact Person: for purposes of managing the assignment and receiving communications/issuing notices, there shall be an appointed ASB’s Contract Manager to coordinate all related contract issues for the contract period. 
· Cost of making changes to reports and documents: In the event that the Contractor’s reports or designs and documents are found unacceptable/not meeting the contract requirement at any stage of the project, the Contractor will resubmit revised reports or documents or designs at no additional cost.  Any revisions required by ASB following submissions for approval will be completed by the Contractor within the lump sum cost for the project.
· Return of documents, Soft Copies and Software to the Client: At the end of the assignment, the Contractor shall return to ASB, documents, reports and all written communications originating from both parties and put at the disposal of the Contractor for the purpose of the project, together with an inventory.
· Neither the Contractor nor any of their staff shall claim a right of authorship or design patent on the contents of any of the reports and documents submitted during the project.
· The Contractor shall submit reports and documents to ASB and in the numbers indicated in Table below and at the relevant stage for the necessary review, comments and approval of ASB.
Reports detailing the progress and the technical information/design of each activity schedule will be submitted for approval. The submission of these reports will conform to the timeliness indicated in the activity schedules submitted.

(d) Submission of Drawings
The Design and Build Contractor shall prepare and submit contract drawings as specified below.  For bidding purposes the drawings shall be reduced as appropriate.   The Design and Build Contractor is to submit and agree the layout of all drawings prior to preparation of any drawings.

	Drawing Type
	Scale

	Key Plan
	1:20,000

	Typical Cross Sections for the Building on Site.
	Hor:1:1000, Vert:1:1000

	Architectural designs (including layouts, sections, and Elevations etc.)
	To suitable scale

	Electrical / Mechanical Engineering drawings (including layouts and sections)
	To suitable scale

	Civil/Structural Design drawings including bending schedules (if applicable)
	To suitable scale



6. [bookmark: _Toc478493538][bookmark: _Toc492910188]AS BUILT DRAWINGS
Within one (1) month after the completion of each phase of the Construction Works the Contractor shall provide the Engineer/ASB with a Construction Completion Report, a schedule of fixed assets and as-built drawings, in hard copy as well as in the agreed electronic format, and as amended from time to time and all such other records as may be required and agreed upon.  Material as-built records shall be submitted in the same manner as the as-built drawings within six weeks of each section being completed.
7. [bookmark: _Toc478493539][bookmark: _Toc492910189]QUALITY ASSURANCE
The Contractor shall operate a quality management system complying with ISO 9001: 2001 for the duration of the Contract. The quality management system shall describe the management, organization, responsibilities, procedures, processes, resources and programme for the Works and shall cover all stages of the Contract including design, execution, construction, completion, testing, commissioning and activities during the Defects Notification Period. The quality management system shall be contained in the Design quality plan; and the Construction quality plan.
Where a quality plan refers to or relies on the Contractor’s quality manual or procedures the relevant part of that manual or procedure shall be reproduced in the relevant Quality Plan.

7.1 Construction Quality Plan 
The construction quality plan shall contain (as a minimum): -
· Definition of standard specifications to be used in the execution of the assignment;
· Identification of key personnel, with CV's;
· A list of Subcontractors to be employed;
· A list of quality procedures and method statements to be provided (paying particular attention to control of Subcontractors' Work);
· Description of specialist activities and personnel;
· Description of arrangements for quality control of purchased products and materials;
· Description of control of workmanship;
· The Contractor’s designer's key personnel for examination of the Works, with CV's.
· The Contractor shall provide an organizational chart showing the interrelationship between these staff, design office staff and the Contractor’s staff for construction.

7.2 Quality Audits
The Contractor shall afford full opportunity for the Engineer to examine and audit the quality management system and quality plans and those of its Subcontractors and suppliers to ensure that the requirements of the Contract are being met. These quality audits will be undertaken on a regular basis but reasonable notice shall be given to the Contractor by the Engineer of the date of any such audit.
The Contractor shall rectify all non-compliances notified as a result of the audit by the Engineer within the timescale set for such notification.
In the event of specific problems arising, special audits, over and above the stated routine audits may also be performed.

8. [bookmark: _Toc478493541][bookmark: _Toc492910191]EQUIPMENT CAPABILITY
The contractor shall include in his bid a list of equipment that he proposes to use to execute the project he plans to implement and demonstrate that he has sufficient equipment to execute the assignment(s). The contractor should further indicate whether he owns, or has assured access to (through hire, lease, purchase agreement, availability of manufacturing capacity, or other means), the equipment indicated. In allocating various equipment for these projects,

9. [bookmark: _Toc478493542][bookmark: _Toc492910192]PROJECT PERFORMANCE SPECIFICATIONS
[bookmark: _Toc483335145][bookmark: _Toc492910193]Contract Time
The entire project should be implemented within 4 months’ period 
[bookmark: _Toc483335146][bookmark: _Toc492910194]Quality/Condition at Delivery (Project Completion)
Should an element of the PHCC facility be classified as failed, the failures must be repaired as specified if one of the following conditions appears by the end of the defects liability period before handover by the Contractor to ASB: –
· Defective concrete or steel surfaces exhibiting any form of structural or none structural deficiency, 
· Excessive deflection beyond acceptable limits, which are required under the relevant codes/good industry practices applied.
· Collapse of any part or the whole of the designed and constructed facility except in event of Force Majeure (that occasioned by Acts of God or as provided under the ensuing contract);
· Sub base saturation resulting in loss of strength and stability making the structure susceptible to breakup or deform excessively 
· Differential settlement;
· Joint failures.

It should be noted that causes of any of the above defects must first be identified before any corrective intervention is agreed and implemented by the contractor engineers. 
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[bookmark: _Toc478493544][bookmark: _Toc492910196]Work Plan
Each Bidder shall set out a detailed Work Program, CVs of experienced personnel and Schedule for design and construction of the Design and Build Works to be undertaken, risk management plan including estimated start and finish dates for individual components and identification of major milestones and critical path.  The proposed Program and Schedule shall be developed according to Employer’s Requirements and shall address the following:

(a) Details of the proposed schedule for design of the Design and Build Works, including the submission of design documents, review and approval. 

(b) CVs of the following registered personnel with relevant experience:

	 Construction manager: Should have a Bachelor of Science in Architect Engineering degree from a recognized University, registered with requisite professional institutions, and having experience of at least 5 years of similar experience in supervision of similar work, 5 years of which should be specific to Factory infrastructure 
 The team leader shall also have experience in contract/project management and knowledge in Iraq procurement guidelines and regulations. 
 Site engineer: Should have Bachelor of Science in Architect Engineering degree from a recognized University, qualified and competent registered professional with practicing certificate, and having experience of at least 5 years of similar experience in supervision of similar work, 3 years of which should be specific to Factory infrastructure 
 1 numbers, Superintendent of works (building works): Should have ordinary diploma in building and Civil Engineering from a recognized University/institution, and having experience of at least 5 years of similar experience in the field under review, 3 years of which should be specific to buildings and structures.
 1 Number, health and safety officer. Should have a minimum of a diploma in engineering or any other field and a certificate in occupational health and safety. 



(c) Details of the proposed timeline for carrying out the Design and Build Works within the Time for Completion, in the form of a Ghantt Chart (in MS Project) showing clearly the critical path activities.

(d) Details of the proposed timeline for the testing, commissioning and handing over of the completed Design and Build Works.

(e) [Other proposed measures as may be appropriate].

[bookmark: _Toc478493545][bookmark: _Toc492910197]Cash Flow Projections
Each Bidder shall set out details of the Cash Flow Projection indicating monthly projected expenditure throughout the duration of the Contract, both the percent of the Accepted Contract Amount and the cumulative percentage of the Accepted Contract Amount by month.  The Cash Flow Projections shall address the following, taking into consideration payment of the Advance Payment, amortization of the Advance Payment, withholding of the Retention, and release of the Retention:
(c) The periodic payments by milestones for the design and construction of the Design and Build Works.

(d) [The periodic payments based on measurement for the construction of the Design and Build Works, as applicable.]

 
(e) [If there are multiple lots or sections, add as may be appropriate.]







[bookmark: _Toc478493546][bookmark: _Toc492910198]Environmental Considerations 
The Bidder shall provide the documents to show that it has in place sufficient environmental awareness to be able to perform responsibilities in accordance with the Iraqi environmental laws. 
The Bidder shall demonstrate in a narrative section of its Technical Offer that it possesses a high level of Environmental and Social (“E&S”) management expertise and can successfully manage the E&S risks associated with the implementation of the proposed Design and Build Works, as follows: 

(a) Describe the proposed approach to managing E&S impacts during implementation of this projects, including a description of the mitigation measures that will be used and international E&S standards that may be applicable; provide enough detail to demonstrate an understanding of the critical E&S issues related to the projects that are in three distinct location with different site conditions; and 









[bookmark: _Toc478493547][bookmark: _Toc492910199]Health & Safety Plan
The Bidder shall provide the documents to show that it has in place sufficient safety policy documents and safety awareness to be able to perform their responsibilities in a safe and secure manner, considering the sensitive of the factory projects
The Bidder shall demonstrate in a narrative section of its Technical Offer that its possesses a high level of Health and Safety (“H&S”) management expertise and can successfully manage the H&S risks related to the implementation of the Design and Build Works.  To demonstrate this, the Bidder shall provide the following:
(a) Describe proposed H&S staffing, roles and responsibilities, and management structure; 

(b) Describe the proposed equipment and facilities for managing H&S impacts during implementation of the Design and Build Works. 

(c) Indicates in his proposal the rescue facilities he intends to employ during the implementation stage.



[bookmark: _Toc422725301][bookmark: _Toc427641277][bookmark: _Toc438907060][bookmark: _Toc438907259]3.	Drawings
Refer to Annexes 1 and 2

4.	Bills of Quantities

Activity Schedule/ Bills of Quantities
	Item
	Description
	Amount USD

	1.1
	Remuneration Cost
	 

	1.1.1
	Team Leader / structural Engineer
	 

	1.1.2
	Architect 
	 

	1.1.3
	Environmentalist
	 

	1.1.4
	Superintendent
	 

	1.3.5
	Report production
	 

	Total Carried to General Summary
	 






Signature………………………………………………………. 
(A person or persons authorized to sign on behalf of the Bidder)
Date…

Form D 4.2.4 Price Schedule 2 – Construction Works for the Proposed PHCC
 The lump sum prices to be provided in this schedule shall be for works executed in accordance with the Ministry of Health Specifications for PHCC , and or any other special specification as provided or approved by the client.
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Section 7
Part I: General conditions of contract for procurement of design and construction works.
The Conditions of Contract comprise the General Conditions, which form part of the “Conditions of Contract for Plant and Design-Build” First Edition 1999 published by the F´édération International des Ingénieurs-Conseils  (FIDIC), and the following Particular Conditions, which include amendments and additions to such General Conditions.

	Copies of the FIDIC Conditions of Contract can be obtained from:

FIDIC Secretariat
P.O. Box 86
1000 Lausanne 12
Switzerland
Facsimile: +41 21 653 5432
Telephone: +41 21 653 5003


The Proposed Design and Construction of SAMSIEH PHCC

Part 3: Section 6-Statement of Requirements	



Section 8
Part –II: Particular Conditions of Contract 
Conditions of Contract for “Conditions of Contract for Design-Construct-Build”

PARTICULAR CONDITIONS OF CONTRACT
	Subject
	Sub-Clause

	Definitions
	1.1
	Replace the definition in sub-paragraph 1.1.2.2 with:
“Employer” means the person who takes over the completed Works and who is named as employer in the Appendix to Bid and the legal successors in title to this person and “Recipient” the person to whom the Works are simultaneously transferred and who is named as recipient in the Appendix to Bid and the legal successors in title to this person.

1.1.1.4 The “Letter of Tender” shall be read as “ Bid submission sheet”
1.1.6.10 “Eligible Countries” means any ineligible countries named in the Appendix to Bid.

	Interpretation
	1.2
	Insert new paragraphs:
Wherever these Conditions require the Contractor to indemnify the Employer from any matter, the Contractor shall also indemnify the Engineer from the same matter.

	Communications 
	1.3
	At the end of this Sub-Clause, insert:
When issuing a Taking-Over Certificate or the Performance Certificate, the Engineer shall send a copy to the Employer.

	
	Insert new Sub-Clause 1.15:

	Details to be Confidential
	1.15
	The Contractor shall treat the details of the Contract as private and confidential, except to the extent necessary to carry out obligations under it or as agreed by the Employer.  The Contractor shall not publish, permit to be published, or disclose any particulars of the Works in any trade or technical paper or elsewhere without the previous agreement of the Employer and the Recipient.

	Engineer’s Duties and Authority
	3.1
	At the end of this Sub-Clause, insert:
The Engineer shall obtain the specific approval of the Employer before taking action under the following Sub-Clause of these Conditions:
(a) Sub-Clause 3.5: agreeing or determining any matter which will increase the Contract Price by more than the limit stated in the Appendix to Bid.
(b) Sub-Clause 4.4: giving consent to a Subcontractor for a subcontract for which a different subcontractor is named in the Contract.
(c) Sub-Clause 8.4: agreeing or determining an extension of the Time for completion.
(d) Clause 13: instructing a Variation which is expected to increase the Contract Price by more than the limit stated in the Appendix to Bid.
(e) Sub-Clause 21.2: giving notice of a “Permitted Resource” if the Cost of the proposed subcontract, Plant or Materials is expected to exceed the limit stated in the Appendix to Bid.
(f) Sub-clause 10.1 Issuance of Taking Over Certificate
(g) Sub-clause 11.9 issuance of performance Certificate

	Performance Security
	4.2
	At the end of the second paragraph, insert:
Such entity shall be incorporated in an eligible country as defined in sub-Clause 1.1.6.10 as a bank or an insurance company.

	Subcontractors
	4.4
	At the end of this Sub-Clause, insert:
Prior consent shall not be required if the value of the subcontract is less than 0.1% of the Accepted Contract Amount.  

	Rates of Wages and Conditions of Labor
	6.2
	At the end of this Sub-Clause, insert the following paragraph:
The Contract shall ensure that no one under 18 years of age or the age of the end of compulsory schooling in that area, whichever is higher, is engaged on the Works.  The Contractor shall respect the rights of freedom of association, right to freedom from forced labour, right to freedom from discrimination on the basis of race, colour, sex, religion, political opinion and the social origin as these principles are defined in the relevant Conventions of the International Labour Organization.

	Persons in the Service of Employer
	6.3
	This Sub-Clause shall not apply to Employer’s Personnel who are not involved in any activities related to the Contract or works, and shall not apply after the Performance Certificate has been issued.”

	Health and Safety
	6.7
	At the end of the first paragraph, insert the following sentence:
For avoidance of doubt, “epidemics” include (among other things) those attributable to human immunodeficiency virus (HIV)/AIDS.

	Contractor’s Personnel
	6.9
	At the end of this Sub-Clause, insert the following paragraph:
A majority of the Contractor’s office-based professional personnel employed on the Site for the performance of the Contract, and a majority of such personnel employed off site and involved in the performance of the Contract, shall be directly employed by the Contractor or, if Sub-Clause 1.14 applies, by the companies participating in the joint venture.

	
	Insert new Sub-Clause 6.12:

	Country Requirements
	6.12
	The Contractor shall respect the Country’s recognized festivals, days of rest and religious or other customs.
The Contractor may import any personnel who are necessary for the execution of the Works.  The Contractor must ensure that these personnel are provided with the required residence visas and work permits.
The Contractor shall be responsible for the return to the place where they were recruited or to their domicile of imported Contractor’s Personnel.  In the event of the death in the Country of any of these personnel or members of their families, the Contractor shall similarly be responsible for making the appropriate arrangements for their return or burial.

	Adjustments for Changes in Costs
	13.8
	Price adjustment is not applicable.

	Advance Payment
	14.2
	At the end of the third paragraph, insert:
Such entity shall be incorporated in an “Eligible Country” as defined in Sub-Clause 1.1.6.10 as a bank or an insurance company.

	
	
	

	Subject
	Sub-Clause
	Prior to commencing construction of the Permanent Works, the Contractor shall submit an updated bill of principal quantities of the Permanent Works (the “BPQPW”), together with any supporting information and calculations reasonably required by the Engineer.  The BPQPW shall include the anticipated final quantities of the principal items of Permanent Works, which shall have been priced using all-in rates such that the total amount equals the Contract Price as agreed in the contract. 

The BPQPW shall not contain priced items for Temporary Works.  The value of each element of this work, and of any other work element not described in the BPQPW, shall each be included in the rates for Permanent Works which are to be constructed after the element is carried out.
The BPQPW shall be subjected to the approval of the Engineer, which may at any time be withdrawn, and shall be without prejudice to the final amount due under the Contract.  The BPQPW shall be revised and reissued if it appears at any time before Taking-Over that it will not fully represent the Permanent Works when complete.

During the Time for Completion, the contract value for the purpose of sub-paragraph (a) of Sub-Clause 14.4 shall not exceed the amount calculated from the current BPQPW, based on the quantities of Permanent Works which have been constructed in accordance with the Contract.  Each Statement shall:
(a) Be in the same form as that of the current BPQPW,
(b) Include a signed statement that its current BPQPW (including anticipated final quantities) and the as-constructed quantities are all correct, and 
(c) Be accompanied by a certificate signed by the Contractor’s Representative, certifying that the part of the Works constructed to date complies with the Contract.




	
	Insert new Sub-Clause 15.6:

	Anti-Corruption 
	15.6
	No offer, payment, consideration, or benefit of any kind, which constitutes illegal or corrupt practices, shall be made, either directly or indirectly, as an inducement or reward in relation to the Bidding, award or execution of the Contract.
Any such practice will be grounds for the immediate termination under Sub-Clause 15.2 and for such additional actions (civil and/or criminal) as may be appropriate.  At the discretion of the PPDA, a further consequence of any such practice can be the definite exclusion from any tendering for public-funded projects.

	Dispute Adjudication Board
	20.2 to 20.4
	Delete Sub-Clauses 20.2, 20.3 and 20.4. Any dispute shall be adjudicated by an adjudicator to be appointed by the agreement of the Contractor and Employer or in case of disagreement by Iraqi Institution of Professional Engineers (UIPE).  

	Arbitration
	20.6
	Delete the first  paragraph and substitute:
Unless settled amicably, any dispute in respect of which the adjudicator’s decision (if any) has not become final and binding shall be finally settled by arbitration in accordance with the law of arbitration of Iraq. Arbitration shall take place at Baghdad.
















The Proposed Design and Construction of HEET PHCC 

Part 3:  Section 8-Particular Conditions of Contract


SECTION 9 - CONTRACT FORMS


I. Form of Agreement
II. Performance Bank Guarantee
III. Bank Guarantee for Advance Payment




[bookmark: _Toc147154037]Form of Agreement

THIS AGREEMENT made the 
between 
of ----------------------------------- (hereinafter called “the Employer”) of the one part,

and 	
of (hereinafter called “the Contractor”) of the other part .------------------------------

WHEREAS the Employer is desires that Works known as REHABILITATE AND BUILD CONTRACTOR TO DEVELOP SAMSIEH SUB PHCC in ANBAR

Should be executed by the Contractor, and has accepted a Bid by the Contractor for the execution and completion of these Works and the remedying of any defects therein.

The Employer and the Contractor agree as follows:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Conditions of Contract hereinafter referred to.

1. The following documents shall be deemed to form and be read and construed as part of this Agreement, and the priority of the documents shall be as follows:
a. the contract agreement 
b. the letter of acceptance 
c. bid submission sheet
d. the Conditions of Contract (Part II) – Particular Conditions
e. the Conditions of Contract (Part I) – General Conditions
f. the Employer’s Requirements
g. the schedules
h. the Contractor’s proposal                       
i. Any other documents forming part of the contract.

3.	In consideration of the payments to be made by the Employer to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Employer to design, execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

4.	The Employer hereby covenants to pay the Contractor, in consideration of the execution and completion of the Works and the remedying of defects therein, the Contract Price of -------------------------------- USD United State Dollars at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties hereto have caused this Agreement to be executed the day and year first before written.

SIGNED
	For and on behalf of the Employer

	
	For and on behalf of the Contractor

	                                    

	
	

	In the presence of:                                 
Name 
	
	In the presence of:
Name: 

	
Signature:
	
	
Signature:





























Performance Bank Guarantee
____________________________ [Bank’s Name, and Address of Issuing Branch or Office]

Beneficiary:	
Arbeiter-Samariter-Bund (ASB)
Physical Location: Baghdad – Mansour District , 14 Ramadan Street. 
Tel: 07740918850
Email: manageradminfinance@asb-me.org
 Date:	________________

PERFORMANCE GUARANTEE No.:	_________________

We have been informed that [name of Contractor] (hereinafter called "the Contractor") has entered into Contract No. ………..dated with you, for the execution of…………………………………………………………, (hereinafter called "the Contract"). 

Furthermore, we understand that, according to the conditions of the Contract, a performance guarantee is required.

At the request of the Contractor, we [name of Bank] hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of [amount in figures] (                    ) [amount in words],[footnoteRef:2] such sum being payable in the types and proportions of currencies in which the Contract Price is payable, upon receipt by us of your first demand in writing accompanied by a written statement stating that the Contractor is in breach of its obligation(s) under the Contract, without your needing to prove or to show grounds for your demand or the sum specified therein.  [2:  	The Guarantor shall insert an amount representing the percentage of the Contract Price specified in the Contract and denominated either in the currency (ies) of the Contract or a freely convertible currency acceptable to the Employer.] 


This guarantee shall expire no later than twenty-eight days from the date of issuance of the Taking-Over Certificate, calculated based on a copy of such Certificate which shall be provided to us, or on the ___ day of ______, 2___,[footnoteRef:3] whichever occurs first.   Consequently, any demand for payment under this guarantee must be received by us at this office on or before that date.   [3:  	Insert the date twenty-eight days after the expected completion date. The Employer should note that in the event of an extension of the time for completion of the Contract, the Employer would need to request an extension of this guarantee from the Guarantor.  Such request must be in writing and must be made prior to the expiration date established in the guarantee. In preparing this guarantee, the Employer might consider adding the following text to the form, at the end of the penultimate paragraph:  “The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [\one year], in response to the Employer’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee.”] 


_____________________ 
[signature(s)] 
Bank Guarantee for Advance Payment

___________________ [Bank’s Name, and Address of Issuing Branch or Office]


Beneficiary:			
Arbeiter-Samariter-Bund (ASB)
Physical Location: Baghdad – Mansour District , 14 Ramadan Street 
Tel: 07740918850
Email: manageradminfinance@asb-me.org

Date:	________________

ADVANCE PAYMENT GUARANTEE No.:	_________________

We have been informed that [name of Contractor] (hereinafter called "the Contractor") has entered into Contract No. ………………. dated ______ with you, for the execution of ………………………………………………………  (Hereinafter called "the Contract"). 

Furthermore, we understand that, according to the conditions of the Contract, an advance payment in the sum [amount in figures] (       ) [amount in words]  is to be made against an advance payment guarantee.
At the request of the Contractor, we [name of Bank] hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of [amount in figures] (                    ) [amount in words][footnoteRef:4] upon receipt by us of your first demand in writing accompanied by a written statement stating that the Contractor is in breach of its obligation under the Contract because the Contractor used the advance payment for purposes other than the costs of mobilization in respect of the Works.  [4:  	The Guarantor shall insert an amount representing the amount of the advance payment and denominated either in the currency(ies) of the advance payment as specified in the Contract, or in a freely convertible currency acceptable to the Employer.] 

It is a condition for any claim and payment under this guarantee to be made that the advance payment referred to above must have been received by the Contractor on its account number ___________ at _________________ [name and address of Bank].
The maximum amount of this guarantee shall be progressively reduced by the amount of the advance payment repaid by the Contractor as indicated in copies of interim statements or payment certificates which shall be presented to us.  This guarantee shall expire, at the latest, upon our receipt of a copy of the interim payment certificate indicating that eighty (80) percent of the Contract Price has been certified for payment, or on the ___ day of _____, 2___,[footnoteRef:5] whichever is earlier.  Consequently, any demand for payment under this guarantee must be received by us at this office on or before that date. [5:  	Insert the expected expiration date of the Time for Completion.  The Employer should note that in the event of an extension of the time for completion of the Contract, the Employer would need to request an extension of this guarantee from the Guarantor.  Such request must be in writing and must be made prior to the expiration date established in the guarantee. In preparing this guarantee, the Employer might consider adding the following text to the form, at the end of the penultimate paragraph:  “The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [one year], in response to the Employer’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee.”
] 

_____________________ 
[signature(s)] 
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