## Agricultural Unit Building
Detailed WORK PLAN Agricultural Training Center
Activity No. | Activity Description | Plan Start | Plan End | Duration (Days) | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month6 |  |  |  | Month 7 |  |  |  | Month 8 |  |  |  | Month 9
Activity: | Anbar Sub-Directorate Reconsturction |  |  |  | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4
A-1-1 | Mobilization:
A-1-2 | Site preparation:
A-2-1 | Sub Base Type (B):
A-2-2 | Excavation
A-3-1 | Foundation concrete
A-3-2 | Masonry works under DPC
A-3-3 | Columns Concrete
A-3-4 | DPC Concrete
A-3-5 | Masonry works of walls over DPC
A-3-6 | Slab Concrete
A-3-7 | Slab Concrete Ground floor (under tiles)
A-3-8 | Elevator foundations
A-3-9 | Elevator Wall
A-3-10 | Outdoor footage and walk ways
A-3-11 | Garage and Main Entrance
A-3-12 | Natural Stone (Halan)
A-3-13 | Natural Stone (Halan) koplen
A-3-14 | Cement plastering (outside)
A-3-15 | Gypsum plastering
A-3-16 | Roof protection paving by (styger)
A-3-17 | Mosaic Tiles (ground and first floor)
A-3-18 | Ceramic Tiles (floors )
A-3-19 | Ceramic works (walls)
A-3-20 | Skirting
A-3-21 | Granite for stairs
A-3-22 | Granite for stair landing
A-3-23 | Inside Emulsion painting
A-3-24 | Oil painting works
A-3-25 | Outside Emulsion painting
A-3-26 | Acoustic false ceiling (60*60 cm)
A-3-27 | Plastic false ceiling (in WCs)
A-3-28 | Wooden Doors, Interior
A-3-29 | Outside Steel Doors (fence gate) (5.0x2.5 m)
A-3-30 | Outside Steel Door (for roof exit)
A-3-31 | Outside Steel Doors (for the entrances)
A-3-32 | Steel interior Doors (fire protection door ground floor and upper floor)
A-3-33 | PVC Doors
A-3-34 | PVC Windows
A-3-35 | Stair hand rail and misc. hand rails according to drawings supplied
A-3-36 | Window protection, on ground floor only
A-3-37 | Ramp
A-3-38 | Septic Tank
B-1-1 | Excavation of trench
B-1-2 | Delivery and create an inspection shaft
B-1-3 | PVC sewerage pipes DN 100 (4) ”diameter
B-2-1 | PVC or PP sewerage pipes DN 50
B-2-2 | PVC or PP sewerage pipes DN 100 (4)”
B-2-3 | Floor drains,
B-2-4 | Vent-pipe inlet louvers
B-3-1 | Rainwater downpipes
B-4-1 | Supply and install pump(2 hp)
B-4-2 | PPR Inclined seated shut valve DN 25/ 1"
B-4-3 | PPR Inclined seated shut valve 3/4"
B-4-4 | Inclined seated no return shut valve 1" with drain tap.
B-4-5 | Ball valve drain taps 1/2" with hose connection
B-4-6 | Taps 1/2":
B-4-7 | Stand Electric warm water heater in European quality 120 liter.
B-4-8 | Polypropylene PPR cold/warm water supply pipes DN 20/3/4":
B-4-9 | Polypropylene PPR cold/warm water supply pipes DN 25/1"
B-4-10 | Water tank (2 m3)
B-5-1 | Wall mounted hand wash basin
B-5-2 | One lever mixer faucet in chrome
B-5-3 | Eastern WC existing out of
B-5-4 | Western seat toilet
B-5-5 | Disabled Toilet
B-5-6 | Hand Bidet shower for hygienic in toilets existing of
B-5-7 | WC- paper holder with lid, made out of stainless steel
B-5-8 | WC- Toilet brush set wall mounted stainless steel
B-5-9 | Wall Mount Shower Systems
B-5-10 | Kitchen sink- two wings
B-6-1 | Powder type fire extinguisher
B-6-2 | CO2 type fire extinguisher
C-1-1 | Armored Jordanian Editha Cable
C-1-2 | Automatic transfer unit (ATS) 400 KVA
C-1-3 | Main Switch Board (M.S.B.)
C-1-4 | Sub-Distribution-Board for Main building
C-1-5 | Final- Distribution 24 lines for flush mounted for the rooms in the corridors
C-1-6 | Final- Distribution 18 lines for flush mounted for the rooms in the corridors
C-2-1 | Lighting Fixture Led 45 Watt
C-2-2 | Lighting Fixture Led 18 Watt
C-2-3 | Lighting Fixture Led 18 Watt
C-2-4 | Out door wall lamp fixtures
C-2-5 | Illuminated signs Wall-or ceiling mounted luminaire
C-2-6 | Ceiling Fan
C-2-7 | Exhaust fan for mounting in window pane
C-2-8 | Switch Socket, 13 A, 230 V AC
C-2-9 | Moisture-proof sockets IP66 for wet rooms and outdoor use, 13 A, 230 V AC IP 66
C-2-10 | Double switch socket, 13 A, 230 V AC
C-2-11 | CEE-Power-Sockets 16 A, 400 V
C-3-1 | HES-Plastic coated- copper-wire NYM-J 5 x 25mm²
C-3-2 | HES-Plastic coated- copper-wire NYM-J 5 x 35mm2
C-3-3 | HES-Plastic coated- copper-wire NYM-J 4 x 70mm2
C-3-4 | Galvan. Steel cable channel
C-3-5 | Cable laying systems
C-4-1 | Supply & install materials for lightning protection
C-5-1 | Single Earthing system
C-5-2 | Main building
C-6-1 | Smoke detector point
C-6-2 | Heat detector point
C-6-3 | Break glass point
C-6-4 | Fire alarm Bell outlet
C-6-5 | Addressable Fire alarm control panel
C-6-6 | Commissioning of entire fire alarm system
C-7-1 | Single Split Air Condition T3 36,000 BTU (3 Ton)
C-7-2 | Single Split Air Condition T3 24,000 BTU (2 Ton)
C-7-3 | AC condensate dewatering: PVC or PPR pipes, DN 25
C-8-1 | Camera System
C-9-1 | Supply and installation of cable driven lift
C-10-1 | Telephone socket
C-10-2 | Electronic telephone sets
C-10-3 | Telephone distribution box PTT mark
C-10-4 | Telefone exchange 2*16 lines
C-10-5 | 20 pair (0,6 mm2) cable
C-11-1 | Concrete Base
C-11-2 | Generator House
C-11-3 | Generator
C-11-4 | Fuel Tank
C-11-5 | Cable