## Anbar Sub-Directorate
ANNEX G : Detailed WORK PLAN Anbar Sub-Directorate Reconsturction
Activity No. | Activity Description | Plan Start | Plan End | Duration (Days) | Resources (Man power) | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 7 |  |  |  | Month 8 |  |  |  | Month 9 |  |  |  | Month 10
Activity: | Anbar Sub-Directorate Reconsturction |  |  |  |  | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4
1 | Civil works
1.1 | Caravan Provision and installation (6*4)
1.2 | Land Leveling/settlement
1.3 | Excavation works
1.4 | Compaction works - Sub Base Type (B)
1.5 | Lean Concrete
1.6 | Foundation concrete
1.7 | Masonry works under DPC
1.8 | Filling works-clean soil
1.9 | Damp Roof Course (DPC)
1.1 | Columns Concrete
1.11 | Masonry works of walls over DPC
1.12 | Slab Concrete, Beams, lintels, Parapet and cantilever
1.13 | Slab Concrete Ground floor (under tiles)
1.14 | Outdoor footage and walk ways
1.15 | Ramp for handicapped
1.16 | Main Entrance and inside road concrete
1.17 | Natural Stone (Halan)
1.18 | Natural Stone (Halan) for Windows frame
1.19 | Cement plastering (outside)
1.2 | Gypsum plastering
1.21 | Internal and external Plasting Painting
1.22 | Roof protection paving by (shtaygar) Cement plates
1.23 | Granite Tiles (ground and first floor)
1.24 | Ceramic Tiles (floors )
1.25 | Ceramic works (walls)
1.26 | Skirting (DPC Ceramic Cladding)
1.27 | Granite for stairs
1.28 | Granite for stair landing
1.29 | Acoustic Gypsum false ceiling (60*60 cm)
1.3 | Plastic false ceiling (in WCs)
1.31 | Wooden Doors, Interior
1.32 | Outside Steel Doors (for roof exit and roof)(1*2.10 m)
1.33 | Outside Steel Doors (for the entrances)(2*2.5 m)
1.34 | Outside Steel Doors (fence gate) (3.0x2.5 m)
1.35 | Outside Slide Steel Doors (fence gate) (5.0x2.5 m)
1.36 | PVC Doors
1.37 | PVC Windows
1.38 | Stairs handrail
1.39 | Window protection, on ground floor only
1.4 | Fence Foundation
1.41 | Solid block work for fence
1.42 | outside paving tiles (Shtiger)
1.43 | Green Area
1.44 | Septic Tank
1.45 | Emergency Iron Ladder
1.46 | Shading Area
2 | PLUMBING WORK
2.1 | Trench excavation and PVC sewerage pipes DN 100 (4) ”diameter connection
2.2 | PVC reinforced Manhole
2.3 | PVC reinforced Manhole
2.4 | PVC or PP sewerage pipes DN 100 (4)” diameter
2.5 | Floor drains
2.6 | Vent-pipe inlet louvers
2.7 | Roof/Floor drain for balcony dewatering
2.8 | Rainwater downpipes
2.9 | Water Pump
2.1 | Ball valve drain taps 1/2" with hose connection
2.11 | butterfly 1" with hose connection
2.12 | Taps 1/2"
2.13 | Stand Electric warm water heater 120 liter
2.14 | Wall mounted warm water heater 45 liter
2.15 | Polypropylene PPR cold/warm water supply pipes Dia. 3/4"
2.16 | Polypropylene PPR cold/warm water supply pipes Dia. 1"
2.17 | Water Tank
2.18 | Installing wall-mounted handwash basins with water mixer
2.19 | Installing eastern toilet
2.2 | Installing wall-mounted western toilet
2.21 | WC- Toilet brush
3 | Fire Fighting extinguishers
3.1 | Powder type fire extinguisher
3.2 | CO2 type fire extinguisher
4 | Electrical Works
4.1 | Exterior Transformer 100 KVA (11/0.416)KV
4.2 | Automatic transfer unit (ATS) 400 KVA
4.3 | Main Switch Board (M.S.B.)
4.4 | Electrical Caples
4.5 | Final- Distribution 24 lines
4.6 | Lighting Fixture Led 45 Watt (false ceiling)
4.7 | Lighting Fixture Led 18 Watt for WCs
4.8 | Out door wall lamp fixtures- Lighting Fixture Led 50 Watt
4.9 | Ceiling Fan 60 x 60
4.1 | Electric air ventilator
4.11 | Exhaust Fans wall mounted
4.12 | Switch Socket, 13 A, 230 V AC
4.13 | Moisture-proof sockets 13 A, 230 V AC
4.14 | Earth system
4.15 | Air cooler device 2 Ton Capacity
4.16 | Air cooler device (3 Ton)
5 | Fire Alarm System
5.1 | Smoke detector point
5.2 | Heat detector point
5.3 | Break glass point
5.4 | Fire alarm Bell outlet
5.5 | Addressable Fire alarm control panel
5.6 | Commissioning of entire fire alarm system
6 | Telephone (Communication) System
6.1 | Telephone socket
6.2 | Electronic telephone sets
6.3 | Telephone distribution box PTT mark
6.4 | Telefone exchange 1*16 lines
6.5 | 12 pair (0,6 mm2) cable
Camera System
7.1 | Camera System
8 | Generator
8.1 | Concrete Base
8.2 | Generator House
8.3 | 100 KVA Generator
8.4 | Fuel Tank