## Agriculture Refrigerated Storag
ANNEX G : Detailed WORK PLAN Agriculture Refrigerated Storage in Ramadi / Anbar
Activity No. | Activity Description | Plan Start | Plan End | Duration (Days) | Resources (Man power) | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6 |  |  |  | Month 7 |  |  |  | Month 8 |  |  |  | Month 9 |  |  |  | Month 10 |  |  |  | Month 11 |  |  |  | Month 12
Activity: | Agriculture Refrigerated Storage Compund in Ramadi / Anbar |  |  |  |  | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4
Agriculture Refrigerated Storages/Part 1) Civil works
1.1 | Excavation works
1.2 | Columns Concrete casting
1.3 | Tie Beam Casting
1.4 | Steel structure imstallation Total external axis dimensions - 20.00 x 50.00 m
1.5 | Sandwich Panel covering for Refrigerated Rooms and Corridor
1.6 | Sandwich Panel covering for external walls and roof
1.7 | Compaction works - Sub Base Type B
1.8 | Slab Concrete Ground floor
1.9 | External Door Installation
1.1 | Refrigrated Rooms Sliding doors 2.5*3 M
1.11 | Collision protection
Agriculture Refrigerated Storages/Part Part 2) Refrigrated System
1.12 | Edgings for cooling chambers
1.13 | integrated Cooling and ventilation System for 5 chambers
1.14 | Humidification units (HUMI Master 10K or equivalent)
Agriculture Refrigerated Storages/Part 3) Electrical Works
1.15 | Electrical Works
Non Refrigrated Storages/Part 1) Civil works
2.1 | Excavation works
2.2 | Columns Concrete Foundation
2.3 | Tie Beam Casting
2.4 | Steel structure imstallation
2.5 | Sandwich Panel covering
2.6 | Compaction works - Sub Base Type B
2.7 | Slab Concrete Ground floor
2.8 | Door Installation
2.9 | Emergency doors
2.1 | PVC Windows
Non Refrigrated Storages/Part 2) Electrical Works
2.11 | Electrical Works
Adminstration Building- Storage Part 1) Civil works
3.1 | Excavation works
3.2 | Foundation Concrete casting
3.3 | Masonry works under DPC
3.4 | Masonry works of walls over DPC
3.5 | Slab Concrete, Beams, lintels, Parapet and cantilever Casting
3.6 | Slab Concrete Ground floor (under tiles)
3.7 | Granite Tiles
3.8 | Ceramic works (walls)
3.9 | Roof protection paving by (shtaygar) Cement plates
3.1 | Stairs handrail
3.11 | Skylight roofer
Adminstration Building- Storage Part 2) PLUMBING WORK
3.12 | Water pipes connections "Galvanized pipes" Dia. 3/4"
3.13 | Polypropylene PPR cold/warm water supply pipes Dia. 1/2"
3.14 | PVC or PP sewerage pipes DN 100 (4)” diameter
3.15 | Septic Tank Construction (2.5*3*2)
Adminstration Building- Storage Part 3) Electrical Works
3.16 | Main Switch Board (M.S.B.)
3.17 | Sub-Distribution board 18 lines
Guard Building-Storage Part 1) Civil works
4.1 | Excavation works
4.2 | Foundation Concrete casting
4.3 | Masonry works under DPC
4.4 | Masonry works of walls over DPC
4.5 | Slab Concrete, Beams, lintels, Parapet and cantilever Casting
4.6 | Slab Concrete Ground floor (under tiles)
4.7 | Porcelin Tiles
4.8 | Ceramic Tiles (floors )
4.9 | Ceramic works (walls)
4.1 | Roof protection paving by (shtaygar) Cement plates
Guard Building-Storage Part 2) PLUMBING WORK
4.11 | Water pipes connections "Galvanized pipes" Dia. 3/4"
4.12 | Polypropylene PPR cold/warm water supply pipes Dia. 1/2"
4.13 | PVC or PP sewerage pipes DN 100 (4)” diameter
4.14 | Septic Tank Construction (2.5*3*2)
Guard Building-Storage Part 3) Electrical Works
4.15 | Sub-Distribution board 6 lines
Electrical Room Control-Storage Part 1) Civil works
5.1 | Excavation works
5.2 | Foundation Concrete casting
5.3 | Masonry works under DPC
5.4 | Masonry works of walls over DPC
5.5 | Slab Concrete, lintels and Parapet Casting
5.6 | Slab Concrete Ground floor (under tiles)
5.7 | Roof protection paving by (shtaygar) Cement plates
Electrical Room Control-Storage Part 2) Electrical Works
5.8 | Main Board-1
5.9 | Main Board-2 for Refrigriated Storages
Fence-Storage) Civil works
6.1 | Excavation works
6.2 | Foundation Concrete casting
6.3 | Masonry works under DPC
6.4 | Damp Roof Course (DPC)
6.5 | Masonry work over DPC
6.6 | Fence top concrete cap
6.7 | Cement plastering (all sides)
6.8 | External Painting
6.9 | Main sliding door
Generator-Transformer) Equipments and supplies
7.1 | Exterior Transformer 400 KVA (11/0.4)KV
7.2 | High pressure Poles
7.3 | Generator 250 KVA
7.4 | Generator House
7.5 | Fuel Tank
Compound Concrete Spaces) Civil works
8.1 | Land Leveling/settlement
8.2 | Filling works-clean soil
8.3 | Compaction works - Sub Base Type (B)
8.4 | Slab Concrete for External Areas (Walkways and freespaces and internal road)
8.5 | Caravan Provision and installation (6*4)
Weighbridge-Storage
9.1 | Weighbridge-truck-loaded /unloaded weight
9.2 | Weighbridge prefabricated Caravan
Parking Shade-Storage) Equipments and supplies
10.1 | Concrete parking Floor
10.2 | Parking Shade
Lighting system-Storage) Equipments and supplies
11.1 | Lighting Poles
11.2 | Cables
11.3 | Control box