## Agriculture Normal Storages
ANNEX G : Detailed WORK PLAN Agriculture Storage in Al-Ramadi/ Anbar
Activity No. | Activity Description | Plan Start | Plan End | Duration (Days) | Resources (Man power) | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6 |  |  |  | Month 7 |  |  |  | Month 8 |  |  |  | Month 9
Activity: | Agriculture Storages Compound in Al-Ramadi/ Anbar |  |  |  |  | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4
Non Refrigrated Storages 1/Part 1) Civil works
1.1 | Excavation works
1.2 | Columns Concrete Foundation
1.3 | Tie Beam Casting
1.4 | Steel structure imstallation
1.5 | Sandwich Panel covering
1.6 | Compaction works - Sub Base Type B
1.7 | Slab Concrete Ground floor
1.8 | Door Installation
1.9 | Emergency doors
1.1 | PVC Windows
Non Refrigrated Storages 1/Part 2) Electrical Works
1.11 | Electrical Works
Non Refrigrated Storages 2/Part 1) Civil works
2.1 | Excavation works
2.2 | Columns Concrete Foundation
2.3 | Tie Beam Casting
2.4 | Steel structure imstallation
2.5 | Sandwich Panel covering
2.6 | Compaction works - Sub Base Type B
2.7 | Slab Concrete Ground floor
2.8 | Door Installation
2.9 | Emergency doors
2.1 | PVC Windows
Non Refrigrated Storages 2/Part 2) Electrical Works
2.11 | Electrical Works
Guard Building-Storage Part 1) Civil works
3.1 | Excavation works
3.2 | Foundation Concrete casting
3.3 | Masonry works under DPC
3.4 | Masonry works of walls over DPC
3.5 | Slab Concrete, Beams, lintels, Parapet and cantilever Casting
3.6 | Slab Concrete Ground floor (under tiles)
3.7 | Porcelin Tiles
3.8 | Ceramic Tiles (floors )
3.9 | Ceramic works (walls)
3.1 | Roof protection paving by (shtaygar) Cement plates
Guard Building-Storage Part 2) PLUMBING WORK
3.11 | Water pipes connections "Galvanized pipes" Dia. 3/4"
3.12 | Polypropylene PPR cold/warm water supply pipes Dia. 1/2"
3.13 | PVC or PP sewerage pipes DN 100 (4)” diameter
3.14 | Septic Tank Construction (2.5*3*2)
Guard Building-Storage Part 3) Electrical Works
3.15 | Sub-Distribution board 6 lines
Fence-Storage) Civil works
4.1 | Excavation works
4.2 | Foundation Concrete casting
4.3 | Masonry works under DPC
4.4 | Damp Roof Course (DPC)
4.5 | Masonry work over DPC
4.6 | Fence top concrete cap
4.7 | Cement plastering (all sides)
4.8 | External Painting
4.9 | Main sliding door
Generator-Transformer) Equipments and supplies
5.1 | Exterior Transformer 100 KVA (11/0.4)KV
5.2 | High pressure Poles
5.3 | Generator 13 KVA
5.4 | Generator House
5.5 | Electrical main board
Compound Concrete Spaces) Civil works
6.1 | Land Leveling/settlement
6.2 | Filling works-clean soil
6.3 | Compaction works - Sub Base Type (B)
6.4 | Slab Concrete for External Areas (Walkways and freespaces and internal road)
6.5 | Temporary Caravan Provision and installation (6*4)
Weighbridge-Storage
7.1 | Weighbridge-truck-loaded /unloaded weight
7.2 | Weighbridge prefabricated Caravan