## Workplan
Detailed Workplan Rehabilitation of concrete irrigation canals in Anbar
Important Note: in order not to cut irrigation water to all fields together, works in locations should be distributed into three lots minimum. One of these lots must include the main canal (overhanging MC1) in parallel with some sub canals. The workplan must be approved by the directorate of irrigation.
| Re-lining of damaged irrigation canals in Ramadi |  | Plan Start | Plan End | Duration (Days) | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month6
No. | Item | Location |  |  |  | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4
1 | Work Preperation | 13/LC1 |  |  | 0
|  | 15/LC1 |  |  | 0
|  | 2/MC1 |  |  | 0
|  | 4/MC1 |  |  | 0
|  | 6/MC1 |  |  | 0
|  | 8/MC1 |  |  | 0
|  | 22/MC1 |  |  | 0
|  | 24/MC1 |  |  | 0
|  | 26/MC1 |  |  | 0
2 | Backfilling works | 13/LC1 |  |  | 0
|  | 15/LC1 |  |  | 0
|  | 2/MC1 |  |  | 0
|  | 4/MC1 |  |  | 0
|  | 6/MC1 |  |  | 0
|  | 8/MC1 |  |  | 0
|  | 22/MC1 |  |  | 0
|  | 24/MC1 |  |  | 0
|  | 26/MC1 |  |  | 0
3 | Canal shaping | 13/LC1 |  |  | 0
|  | 15/LC2 |  |  | 0
|  | 2/MC1 |  |  | 0
|  | 4/MC1 |  |  | 0
|  | 6/MC1 |  |  | 0
|  | 8/MC1 |  |  | 0
|  | 22/MC1 |  |  | 0
|  | 24/MC1 |  |  | 0
|  | 26/MC1 |  |  | 0
4 | Concrete lining | 13/LC1 |  |  | 0
|  | 15/LC2 |  |  | 0
|  | 2/MC1 |  |  | 0
|  | 4/MC1 |  |  | 0
|  | 6/MC1 |  |  | 0
|  | 8/MC1 |  |  | 0
|  | 22/MC1 |  |  | 0
|  | 24/MC1 |  |  | 0
|  | 26/MC1 |  |  | 0
5 | Water outlets with 35 cm pipe | 13/LC1 |  |  | 0
|  | 15/LC1 |  |  | 0
6 | Water outlets with 20 cm pipes | 2/MC1 |  |  | 0
|  | 4/MC1 |  |  | 0
|  | 6/MC1 |  |  | 0
|  | 8/MC1 |  |  | 0
|  | 22/MC1 |  |  | 0
|  | 24/MC1 |  |  | 0
|  | 26/MC1 |  |  | 0
7 | Box culvert (aquaduct bridge) | 2/MC1 |  |  | 0
Replacing damaged concrete plates of the overhanging canal MC1 in Ramadi
No. | Item | Location |  |  | 0
1 | Preperation | MC1 |  |  | 0
2 | Casting plates | MC1 |  |  | 0
3 | Steel molds | MC1 |  |  | 0
4 | Joints treatment | MC1 |  |  | 0
5 | Installing plates | MC1 |  |  | 0
6 | Removal of supports | MC1 |  |  | 0
7 | Cast supports | MC1 |  |  | 0