Terms of Reference for Building Peaceful Futures Consortium project Electro-Chlorination unit

Building Peaceful Futures Consortium project

July 2021

# Table of Contents

Table of Contents	1

Project Summary	2

Introduction	3

Background and Context	3

Scope of Study	3

Purpose, Objectives and Scope	3

Intended Audience and Use of the Study	6

Study Methodology	6

Study Design	6

Sampling	6

Data Sources and Data Collection Methods / Tools	7

Ethical Considerations	7

Known limitations [Optional]	8

Expected Deliverables	8

Study Management	9

Study Team and Selection Criteria	11

Schedule of Payment	11

HOW TO APPLY	12

Annexes	12

# Project Summary

| Type of evaluation | Impact assessment on the efficiency of Electro-Chlorination system |
| --- | --- |
| Name of the project | IRQ DFAT BPF 2021 |
| Project Start and End dates | June 2018-December 2021 |
| Project duration | 3.5 years |
| Project locations: | Ninewa Governorate, Northern Iraq |
| Thematic areas | WASH |
| Sub themes | Water Supply |
| Donor | DFAT - Department of Foreign Affairs and Trade Australia |
| Beneficiaries Categories | Adult without disability Child without disability Adult with disability Child with disability Total 17,000 individuals |
| Overall objective of the project | Vulnerable people in Kirkuk and Ninewa Governorates become more resilient through the inclusive provision of humanitarian assistance and protection services which contributes to safe and dignified returns and social cohesion. |

# Introduction

This document provides Terms of Reference (ToR) for Impact assessment of Electro-Chlorination efficiency and impact assessment. It gives detailed description of the project background, study scope, key questions, intended methodology, reporting and governance, key deliverables and timeframes.

# Background and Context

Save the Children is the world's leading independent organization for children, working in over 120 countries around the world. It’s a child rights based organization guided by a Child Safeguarding Policy where it aims to ensure that anyone associated with the organization behaves appropriately towards children, never abuses the position of trust that comes with being a part of the Save the Children family, and will respond appropriately to issues of child abuse and the sexual exploitation of children. Save the Children’s mission is to inspire breakthroughs in the way the world treats children, and to achieve immediate and lasting change in their lives. Save the Children envisions a world in which every child attains the right to survival, protection, development and participation.

Operational in Iraq since 1991, Save the Children is among the largest international NGOs in Iraq responding to multi-sectorial humanitarian, recovery, and development needs of children and their families – including Iraqis displaced by conflict, Syrian refugees, and host communities. Save the Children seeks to meet the basic and immediate needs of children and their families through programmes in child protection, education, MHPSS, WASH, and livelihoods in five governorates across central and northern Iraq: Diyala, Dohuk, Kirkuk, Ninewa, and Salah al-Din.  We do this by operating directly on the ground, targeting those most in need, establishing strong relationships with communities, NGO actors, and local government bodies, so as to ensure sustainable and lasting impact.

The Building Peaceful Futures Consortium is led by Save the Children in close collaboration with CARE International, Norwegian Refugee Council and Humanity and Inclusion. The project supports the safe and dignified return and reintegration of displaced people in Hawija and Sinjar. The WASH component of the project intended to ensure sustained access to WASH services more especially access to safe water using Electro-Chlorination technology to guarantee safety.

A key priority is the generation and sharing of robust evidence – including evaluations – to strengthen our learning and quality culture, and to scale up programs, reach and impact for children and their families in Iraq. We are interested to hear from evaluation and research experts that would like to work with us in this.

Overall, the evaluations and its reports should inform the audiences of the successes, the challenges and relevant learning for future programming.

# Scope of Study

## Purpose, Objectives and Scope

The primary purpose of the study is to generate evidence and inform audiences about the successes, the challenges and relevant learning for future programming and upscale of  Electro-Chlorination technology in Iraqi context.

The specific objectives of the study include;

- To draw key learnings related to the value of the system efficiency in volatile or unstable environments. The desired results of the evaluation are to provide best practices, lessons learnt, and recommendations for future similar programming.

- To understand to what extent key successes, challenges and lessons learned of operating this system and its’ comparative advantage against traditional chlorination methodologies.

- To draw conclusions on the efficiency of duplicating this system and technology in other areas and how to uptake the usage of it.

- Document the current O&M practices and devise measures for sustained O&M practices

- Asses the quality of water as per the sphere standards

- Document the current WASH practices and recommend further actions for uptake after the project closure

- Desk based review of the prevalence of WASH related diseases in the catchment health facility records

The study main evaluation question:  How and to what extent did the Electro-Chlorination support beneficiaries to access clean and potable water, in comparison to old chlorination techniques?

These are broken down into;

| Type of Evaluation | Specific questions |
| --- | --- |
| Implementation/ Process | - How well was the project implemented? - Did the project reach its’ intended outcome? - Did project beneficiaries have a positive experience with the system? Including operators and other technicians. - How and why did the intervention make a difference? - How well did SCI and DoW staff/procedures work together? - How can implementation of the program be improved in terms of coordination? |
| Impact | - What positive and negative, primary and secondary long-term effects, directly or indirectly, intended or unintended can be attributed to the project? - What mechanisms worked and can explain the achievement or not achievement of the programme results? Which did not work and why? |
| Economic | - Did the project provide value for money on the long run and what is the comparative economic advantages against old techniques? - What is the economic value of the project result, and how does that compare to the cost (cost-benefit analysis)? |
| Effectiveness/outcomes | - How far the project is successful in achieving its objectives and results in line with the indicators targets? - How far has the project improved the situation of the beneficiaries and their families? - How did the WASH committees and other community members were involved in different stages of implementation? - Did the project/ reached intended beneficiaries and addressed their specific needs? - What is the perception of the beneficiaries and other stakeholders towards the quality of the services that they have received? - How and why did the intervention make a difference? |
| Efficiency | - Were the project activities/interventions implemented as planned, including timeframe; if not, why not? - Could the same results have been achieved with fewer resources? |
| Sustainability | - Are there any systems/structure in place that are likely to make the program interventions and results sustain after the project completed? - Is there an exit plan developed and implemented? - What is the capacity and willingness of the stakeholders, community structures, governmental departments to take on the project activities after the project phase-out from the area? |
| Lessons learned | - lessons learned and best practices of the project, suggesting reasons for particular successes and challenges? |
| Replicability and scale | - Are the evaluation findings generalizable to other contexts? - Will the project work in a different context? - Can the program/project be scaled up at cost? And how much does it would cost? |

Scope: The study will cover WASH thematic will be conducted in Ninewa Governorate in Northern Iraq. In additional to key stakeholders all beneficiaries’ categories will be sampled, these categories include, Adult without disability, Child without disability, Adult with disability    and     Child with disability.

## Intended Audience and Use of the Study

| Stakeholder | Further information |
| --- | --- |
| Project donor | DFAT |
| Primary implementing organisation | Save the Children (Project team; Program Development, TAs, MEAL team; Advocacy and Communications team |
| Implementing partners | NRC, CARE, HI, YBDO |
| Government stakeholders | DoW, Ninewa Governorate |
| Community groups | WASH committees in Sinjar |
| Beneficiaries | Children and adults involved in the project and the study |

The study findings will be used to inform the above audiences and others of the successes, the challenges and relevant learning for future programming.

# Study Methodology

## Study Design

The external evaluation team is expected to articulate a robust and suitable evaluation methodology in line with the scope, objectives and evaluation questions. The detailed method should include but not be limited to the following:

- A robust study design to depict the project using mixed methods (quantitative and qualitative) including the use of secondary data, and the triangulation of the findings.

- Data collection instruments, protocols and procedures

- Sampling procedures for both qualitative and quantitative methods

- Procedures for analyzing mixed methods

- How users/key project stakeholders in the research will be involved

It is preferred that evaluation method selected will involve save the children staff, beneficiaries, and partners. quantitative methods selected should contribute to the assessment of outcomes and outputs indicators. in addition, the consultant should select qualitative data collection methods e.g. focus group discussions, case stories, etc. to give deeper understanding of processes and approaches, perceptions and behaviors and other factors that have contributed to ongoing projects indicators.

The evaluation should use appropriate methods to seek feedback from children in line with the basic requirements for meaningful and safe child consultation.

## Sampling

It is recommended that applicants propose a sampling strategy. The sampling strategy should include the sampling method and the sample size calculation values. For fair and accurate comparison to be made and since there was no baseline, the project team will evaluate the communities against the comparative advantage of targeted and un-targeted communities.

## Data Sources and Data Collection Methods / Tools

All primary data collected during the study must facilitate disaggregation by gender, age, disability, location or remoteness, vulnerability status. Save the Children and partners will review and where possible provide more guidance on tools and classification schemes for this minimum dataset.

Save the Children and partners if needed/feasible will provide enumerators to assist with primary data collection (however, the consultant will cover their fees including transportation, etc.)

A range of project documentation will be made available to the study team that provides information about the design and changes made in the course of the implementation, implementation and operation of the Program].

The study team is required to adhere to the Save the Children Child Safeguarding; Protection from Sexual Exploitation and Abuse; Anti-Harassment, Intimidation and Bullying; and Data Protection and Privacy policies throughout all the evaluation activities.

## Ethical Considerations

It is expected that this study will be:

- Child participatory. Where appropriate and safe, children should be supported to participate in the evaluation process beyond simply being respondents. Opportunities for collaborative participation could include involving children in determining success criteria against which the project could be evaluated, supporting children to collect some of the data required for the evaluation themselves, or involving children in the validation of findings. Any child participation, whether consultative, collaborative or child-led, must abide by the 9 Basic Requirements for meaningful and ethical child participation.

- Inclusive. Ensure that children from different ethnic, social and religious backgrounds have the chance to participate, as well as children with disabilities and children who may be excluded or discriminated against in their community.

- Ethical: The study must be guided by the following ethical considerations:

  - Safeguarding – demonstrating the highest standards of behaviour towards children and adults.

  - Sensitive – to child rights, gender, inclusion and cultural contexts.

  - Openness - of information given, to the highest possible degree to all involved parties.

  - Confidentiality and data protection - measures will be put in place to protect the identity of all participants and any other information that may put them or others at risk.

  - Public access - to the results when there are not special considerations against this

  - Broad participation - the relevant parties should be involved where possible.

  - Reliability and independence - the study should be conducted so that findings and conclusions are correct and trustworthy.

It is expected that:

- Data collection methods will be age and gender appropriate.

- Study activities will provide a safe, creative space where children feel that their thoughts and ideas are important.

- A risk assessment will be conducted that includes any risks related to children, young people’s, or adult’s participation.

- A referral mechanism will be in place in case any child safeguarding or protection issues arise.

- Informed consent will be used where possible.

- Strict adherence to COVID 19 SoPs

# Expected Deliverables

The study deliverables and tentative timeline (subject to the commencement date of the study) are outlined below. The MEAL team, SC and Consortium partners will agree on final milestones and deadlines at the inception phase.

Deliverables and Tentative Timeline

| Deliverable / Milestones | Timeline |
| --- | --- |
| The study Team is contracted and commences work |  |
| The study Team will facilitate a workshop with the relevant stakeholders at the commencement of the project to develop the inception report. |  |
| The study Team will submit an inception report* in line with the provided template, including: - Study objectives, scope and key study questions - description of the methodology, including design, data collection methods, sampling strategy, data sources, and study matrix against the key study questions - data analysis and reporting plan - caveats and limitations of study - risks and mitigation plan - ethical considerations including details on consent - stakeholder and children communication and engagement plan - key deliverables, responsibilities, and timelines - resource requirements - data collection tools (in line with the study matrix) - Once the report is finalised and accepted, the evaluator/researcher study team must submit a request for any change in strategy or approach to the study manager or the steering committee. |  |
| Final data collection tools - Survey instrument - Data collection mechanism/plan |  |
| An Interim Report / Power Point Presentation including a summary of formative findings from the study. The focus will be on: - Summary of interim findings - Any emerging program issues or risks - Any changes that have had to be made to the study design - Key tasks for the next stage of the study and any proposed refinements or changes to methodology |  |
| A Study Report* (Draft Version – template available including the following elements: - Executive summary - Background description of the Program and context relevant to the Study - Scope and focus of the study - Overview of the study methodology and data collection methods, including a Study matrix - Findings aligned to each of the key Study questions - Specific caveats or methodological limitations of the evaluation - Conclusions outlining implications of the findings or learnings - Recommendations - Annexes (Project logframe, study ToR, Inception Report, Study schedule, List of people involved) A consolidated set of feedback from key stakeholders will be provided by Save The Children within 2 weeks of the submission of the draft report. |  |
| Data and analyses including all encrypted raw data, databases and analysis outputs |  |
| Final Study Report* incorporating feedback from consultation on the Draft Study Report |  |
| Knowledge translation materials: - PowerPoint presentation of Study findings - Summary info graphs - Evidence to Action Brief** |  |

*All reports are to use the Save the Children Final Study Report template

** The Evidence to Action Brief is a 2-4 pages summary of the full report and will be created using the Save the Children Management Response template.

All documents are to be produced in MS Word format and provided electronically by email to the SC Evaluation Project Manager. Copies of all PowerPoint presentations used to facilitate briefings for the project should also be provided to Save the Children in editable digital format.

# Study Management

The consultancy will be contracted by and report to Save the Children – Iraq Country Office. The MEAL Team, Consortium Director and consortium focal points will act as the advisory group for the evaluation process. They will provide the documents mentioned under list of documents. They will also provide technical assistance (e.g. make practical in-country travel arrangements, oversee/assist in making appointments, assist in finalizing the programme, avail any other documents and information needed etc.). The lead consultant will be responsible for managing the whole consultancy.

Study Tentative Timeline, with key deliverables. The final timeline and deliverables will be agreed upon the inception phase.

| What | Who is responsible | By when | Who else is involved |
| --- | --- | --- | --- |
| Study tender submissions | Omeed | 13th Oct 2021 | SC |
| Selection of study team | Bonny/Vian/Omeed | 25th Oct 2021 |  |
| Contracting | SC | 1st Nov 2021 | Aws |
| Documentation review, desk research | Consultant | 13th Nov 2021 | Omeed, Bonny, Vian, Mustafa, Kawkab. |
| Inception report | Consultant | 19th Nov 2021 |  |
| Review of inception report | MEAL team, Omeed | 24th Nov 2021 | Operations team |
| Data collection | Consultant | 26th Nov – 8Th Dec 2021 | Vian/ Partners |
| Data management and analysis (coding, transcriptions, data cleaning, integration and analysis) | Consultant | 26th Nov – 8Th Dec 2021 |  |
| First draft of the Final study report | Consultant | 20th Dec |  |
| Review and validation of the draft report | MEAL team, Consortium manager and partners | 2nd Jan 2022 | SCI & Consultant partners |
| Validation of study findings and recommendations | SC Project Manager/MEAL | 10th Jan 2022 | SC MEAL staff, Technical advisor |
| Final study report and submission of data and analyses | SC Project Manager/MEAL | 15th Jan 2022 | SC MEAL staff, Technical advisor |
| Knowledge translation materials | SC Project Manager/MEAL | 25th Jan 2022 | SC MEAL staff, Technical advisor |
| Project team meeting to develop Study Response Plan | SC Project Manager/MEAL | 30th Jan 2022 | SC MEAL staff, Technical advisor |
| Study final report (together with response plan) posted on OneNet and reviewed (see page 1 above for platform links) | SC Project Manager | 30th Jan 2022 | [SC Peer reviewers] |

# Study Team and Selection Criteria

Interested consultants will be required to submit an Expression of Interest in line with the provided template, which should demonstrate adherence to the following requirements.

### Understanding of Requirements and Experience

To be considered, the study team members together must have demonstrated skills, expertise and experience in:

- Designing and conducting impact assessment using mixed approaches

- Conducting Research Studies in WASH

- Leading evaluations or consultancy work in Iraq or similar settings

- Conducting ethical and inclusive studies involving children and child participatory techniques

- Conducting ethical and inclusive studies involving marginalised, deprived and/or vulnerable groups in culturally appropriate and sensitive ways

- Managing and coordinating a range of government, non-government and  community groups

- Experience conducting study in humanitarian contexts

- Sound and proven experience in conducting evaluations based on OECD-DAC evaluation criteria, particularly utilisation and learning focused evaluations

- Extensive experience of theories of change and how they can be used to carry out evaluations

- Strong written and verbal skills in communicating technical and/ or complex findings to non-specialist audiences (especially report writing and presentation skills)

- A track record of open, collaborative working with clients

There is a high expectation that:

- A team leader will be appointed who has the seniority and experience in leading complex study projects, and who has the ability and standing to lead a team toward a common goal.

- The team has the ability to commit to the terms of the project and have adequate and available skilled resources to dedicate to this study over the period.

### Financial Proposal

Save the Children seeks value for money in its work. This does not necessarily mean "lowest cost", but quality of the service and reasonableness of the proposed costs. Proposals shall include personnel allocation (role / number of days / daily rates / taxes), as well as any other applicable costs.

# Schedule of Payment

The following payments will be made to the consultant using and agreed mode of payment

- Upon approval of inception report and tools: [30%]

- Upon submission of First Draft study Report: [30%]

- Upon approval of final study report: [40%]

# HOW TO APPLY

If interested in applying for this study, please refer to the Consultant EOI Form. Contact person for this study is yasser.rashid@savethechildren.org

# Annexes

Annex 1: Project Logframe

Annex 2: List of project documents to be consulted

Annex 3: SCI Evaluation Scoring for perspective consultants

| Category | Evaluation Quality Criteria (used for internal scoring after completion) |
| --- | --- |
| Purpose, Design and Methods | 1. Does the evaluation report clearly identify the evaluation's purpose (including its key objectives, questions and criteria) as set out in the evaluation's Terms of Reference (ToR)? |
|  | 2. Are the data collection and analysis methods a clearly justified approach to addressing the evaluation's purpose and questions? (Do they provide valid, reliable and ethical data?) |
|  | 3. Is the methodology suitably tailored to the context and population groups to which the evaluation questions relate (e.g. re gender, disability, socio-economic status, geographic location, cultural context, ethnicity)? |
|  | 4. Is the size and composition of the sample in proportion to the conclusions sought by the evaluation? |
|  | 5. Does the evaluation build on what is already known, for example existing tried and tested frameworks and tools, existing data/evidence, and previous lessons learned? |
|  | 6. Are the methods used to collect and analyse data and any limitations of the quality of the data and collection methodology explained and justified? |
|  | 7. Has any personal and professional influence or potential bias among those collecting or analysing data been recorded and addressed or mitigated ethically? |
| Analysis and Findings | 8. If evaluating impact, is a point of comparison used to show that change has happened (eg. a baseline, a counterfactual, comparison with a similar group)? |
|  | 9. Is the explanation of how (e.g. theory of change, logframe, activities) the intervention contributes to change explored? |
|  | 10. Is the data well triangulated, such as by using different data collection methods, types of data and stakeholder perspectives? |
|  | 11. Are alternative factors (eg. the contribution of other actors) considered to explain the observed result alongside an intervention’s contribution? |
|  | 12. Are unintended and unexpected changes (positive or negative) identified and explained? |
|  | 13. Are the perspectives of children & communities included in the evidence, including the most deprived and marginalised? Note: For evaluations focused on young children, caregiver perspectives are adequate instead. |
|  | 14. Are the findings disaggregated according to sex, disability and other relevant social differences? |
|  | 15. Is there a clear logical link between the data that was collected and analysed, and the conclusions and recommendations presented? |
|  | 16. Are conflicting findings and divergent perspectives presented and explained in the analysis and conclusions? |
|  | 17. Are the findings and conclusions of the assessment shared with and validated by a range of key stakeholders (eg. communities, partners, Save the Children staff)? |
| Communication and Use | 18. Is the analysis and interpretation of the data well communicated through accessible language and helpful visuals (diagrams, graphs, tables as needed)? |
|  | 19. Are references, annexes and links included that provide additional relevant data, analysis or references (including key documents and which individuals/stakeholders were involved)? |
|  | 20. Is there a clear plan for how to use the results, including recommendations that are 'SMART' (Specific, Measurable, Achievable, Relevant, Timebound) and directed toward the appropriate 'end users', a dissemination plan, and specific actions for implementing these recommendations? |

| ToR prepared by: | Omeed M. Enwiya |
| --- | --- |
| ToR approved by: | Nirali Mehta |
| Date of sign off: |  |

If any Consultancy Service Provider, Freelancer or Contingent worker will have direct contact with children and/or vulnerable adults and/or beneficiaries and/or have access to any sensitive data on safeguarding and/or children and/or beneficiaries, it is the responsibility of the person receiving the consulting service to contact the local HR team and child safeguarding focal point to ensure vetting checks and on-boarding are conducted in line with statutory requirements, local policies and best practices guidance.