## Al-Falaq School
ANNEX G : Detailed WORK PLAN Al-Falaq School in Heet/ Anbar
Activity No. | Activity Description | Plan Start | Plan End | Duration (Days) | Resources (Man power) | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6 |  |  |  | Month 7 |  |  |  | Month 8 |  |  |  | Month 9
Activity: | Al-Falq School Rehabilitation & construction of six two stories extra classrooms in Heet/ Anbar |  |  |  |  | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4
Al-Falaq School Rehabilitation/Part 1) Civil works
1.1 | Main Slide Door
1.2 | Secondary Slide Door
1.3 | External Gates Columns
1.4 | Slab Construction
1.5 | Removing Old Foundations
1.6 | Sub-Base Compaction works
1.7 | Slab Concrete Ground floor
1.8 | Plastering Removal
1.9 | Removing Damaged Fence
1.1 | Fence Masonary work
1.11 | Cement plastering (outside)
1.12 | Gypsum plastering
1.13 | Internal/external walls and fence Painting
1.14 | Mastic renewal
1.15 | Entrance Sun-Shade
1.16 | Classroom Steel Doors (1*2)m
1.17 | Maintenance of Iron windows
Al-Falaq School Rehabilitation/Part 2) PLUMBING WORK
2.1 | Installing wall-mounted handwash basins with water mixer
2.2 | Water Tank
2.3 | wall-mounted western toilet
2.4 | Polypropylene PPR cold/warm water supply pipes Dia. 1/2"
2.5 | PVC reinforced Manhole
2.6 | PVC or PP sewerage pipes (6)” diameter
2.7 | PVC or PP sewerage pipes DN 100 (4)” diameter
2.8 | Rainwater downpipes (Toilet Roof)
2.9 | Water Taps 1/2"
Al-Falaq School Rehabilitation Part 3) Fire Fighting extinguishers
3.1 | Powder type fire extinguisher
3.2 | CO2 type fire extinguisher
Al-Falaq School Rehabilitation Part 4) Electrical Works
4.1 | Main Switch Board (M.S.B.)
4.2 | Sub-Distribution board 12 lines
4.3 | Energy Save Light LED 75 Watts
4.4 | Projector LED Flood Light
4.5 | Electric air ventilator
4.6 | Switch Socket, 13 A, 230 V AC
4.7 | Air cooler device 2 Ton Capacity
4.8 | Ceiling fan
4.9 | water pump
4.1 | Stand Electric warm water heater 120 liter
4.11 | Galvanized Tray Cable
4.12 | Water Cooler
4.13 | Water Filter
4.14 | 4*35 mm2 cable connection
Extra 6 Classrooms Construction Part 1) Civil works
5.1 | Land Leveling/settlement
5.2 | Excavation works
5.3 | Sub-Base Compaction works
5.4 | Termite Prevention
5.1 | Blinding under foundations
Damp Proof Coarse (D.P.C)
Walkways Foundation
5.2 | Foundations
Lintels
Beams
Slab
Columns
Ground Slab
5.3 | Masonry Works Above D.P.C Level
Masonry Works Under D.P.C Level
Parapet Masonry
5.4 | Filling works- Clear River sand
5.5 | Roof protection paving by (shtaygar) Cement plates
5.6 | Cement plastering (outside)
5.7 | Gypsum plastering
5.8 | Internal/external walls Painting
5.9 | Mosaic Tiles
5.1 | 1.2 m Ceramic Cladding
5.11 | Acoustic Gypsum false ceiling (60*60 cm)
5.12 | Stair Tiles
5.13 | Stair Slab Cladding
5.14 | Aluminum windows
5.15 | Windows Iron Protesction
5.16 | Emergency Iron Ladder
5.17 | Walkways Handrail
5.18 | Stairs handrails
5.19 | Classroom Steel Doors (1*2 m)
Extra 6 Classrooms Construction Part 2) PLUMBING WORK
6.1 | Rainwater downpipes
Extra 6 Classrooms Construction Part 3) Electrical Works
7.1 | Sub-Distribution board 16 lines
7.2 | Main Switch Board (M.S.B.)
7.3 | 4*35 mm2 cable connection
7.4 | Switch Socket, 13 A, 230 V
7.5 | Switch Socket, 32 A, 230 V
7.6 | 60*60 Drop Ceiling LED 96 Watts Light
7.7 | Wall Mounted Water Proof ED Lights
7.8 | Energy Save Light LED 75 Watts
7.9 | Projector LED Flood Light
7.1 | 60*60 Ceiling fan
7.11 | Air cooler device 3 Ton Capacity
7.12 | Earth System