## Falluja primary school
ANNEX G : Detailed WORK PLAN Falluja primary School in Falluja/ Anbar
Activity No. | Activity Description | Plan Start | Plan End | Duration (Days) | Resources (Man power) | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6 |  |  |  | Month 7
Activity: | Falluja School Rehabilitation & construction of four two classrooms and Student WC in Falluja/ Anbar |  |  |  |  | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4
Falluja primary School Rehabilitation/Part 1) Civil works
1.1 | Main Slide Door
1.2 | Partition Removal
1.3 | WC Partition building
1.4 | Internal Plastering
1.5 | Internal/external walls and fence Painting
1.6 | External plastering
1.7 | Floor Mosaic
1.8 | Skirting (DPC Ceramic Cladding)
1.9 | Mastic for Roof protection Cement plates
1.1 | Granite for stairs
1.11 | Stairs Handrail
1.12 | Outdoor walkways
1.13 | Aluminum windows
1.14 | Classroom Steel Doors (1*2)m
1.15 | Toilets Steel door (1*1.8)M
1.16 | Maintenance of Iron windows
1.17 | Plastic false ceiling (in WCs)
1.18 | Acoustic false ceiling (60*60 cm)
1.19 | PVC Doors
1.2 | Toilet floor Ceramic
1.21 | Toilet wall Ceramic
1.22 | PVC Partition
1.23 | Slab Concrete for External area and free spaces
1.24 | Septic Tank
1.25 | Iron Door Maintenance
Falluja School Rehabilitation/Part 2) PLUMBING WORK
2.1 | Installing wall-mounted handwash basins with water mixer
2.2 | Water Tank
2.3 | Installing eastern toilet
2.4 | wall-mounted western toilet
2.5 | Water pipes connections "Galvanized pipes" Dia. 3/4"
2.6 | Polypropylene PPR cold/warm water supply pipes Dia. 1/2"
2.7 | PVC reinforced Manhole
2.8 | PVC or PP sewerage pipes DN 100 (4)” diameter
2.9 | Floor drain
2.1 | Rainwater downpipes (School Roof)
2.11 | Pipes route Excavation
2.12 | Pipes linning and Connecion
2.13 | Manholes
2.14 | Water Taps 1/2"
Falluja School Rehabilitation/ Part 3) Fire Fighting extinguishers
3.1 | Powder type fire extinguisher
3.2 | CO2 type fire extinguisher
Falluja School Rehabilitation/Part 4) Electrical Works
4.1 | Main Switch Board (M.S.B.)
4.2 | Sub-Distribution board 12 lines
4.3 | Led Panel 60 Watt for false ceiling
4.4 | Outdoor light 20 Watt
4.5 | Projector light
4.6 | Electric air ventilator
4.7 | Switch Socket, 13 A, 230 V AC
4.8 | Air cooler device (3 Ton)
4.9 | Ceiling fan
4.1 | Energy save light 60 watt
4.11 | water pump
4.12 | Solar warm water heater 200 liter
4.13 | 4*35 mm cable connection
Extra 4 Classrooms Construction Part 1) Civil works
5.1 | Excavation works
5.2 | Sub-Base Compaction works
5.3 | Blinding concrete
5.4 | Foundation Concrete casting
5.5 | Masonry works under DPC
5.6 | Damp Roof Course (DPC)
5.7 | Filling works- Clear River sand
5.8 | Masonry works above DPC
5.9 | Slab Concrete, lintelsbeams, and Parapet Casting
5.1 | Roof protection paving by (shtaygar) Cement plates
5.11 | Cement plastering (outside)
5.12 | Gypsum plastering
5.13 | Internal/external walls Painting
5.14 | Slab Concrete Ground floor (under tiles)
5.15 | Outdoor footage and walk ways
5.16 | Marble tiles
5.17 | Skirting (DPC Ceramic Cladding)
5.18 | Acoustic false ceiling (60*60 cm)
5.19 | Aluminum windows
5.2 | Emergency Iron Ladder
5.21 | classroom Steel Doors (1*2 m)
Extra 4 Classrooms Construction Part 2) PLUMBING WORK
6.1 | Rainwater downpipes
Extra 4 Classrooms Construction Part 3) Electrical Works
7.1 | Sub-Distribution board 8 lines
7.2 | Switch Socket, 13 A, 230 V AC
7.3 | Switch Socket, 32 A, 230 V AC
7.4 | Led Panel 60 Watt for false ceiling
7.5 | Out door wall lamp fixtures Lighting Fixture Led 50 Watt
7.6 | Air cooler device 2 Ton Capacity
7.7 | Outdoor light 20 Watt
7.8 | Energy save light 60 watt
Students WC Construction Part 1) Civil works
8.1 | building removal
8.2 | Excavation works
8.3 | Sub-Base Compaction works
8.4 | Blinding concrete
8.5 | Foundation Concrete casting
8.6 | Masonry works under DPC
8.7 | Damp Proof Course (DPC)
8.8 | Filling works- Clear River sand
8.9 | Masonry works above DPC
8.1 | Slab Concrete, lintels and Parapet Casting
8.11 | Roof protection paving by (shtaygar) Cement plates
8.12 | Cement plastering (outside)
8.13 | Gypsum plastering
8.14 | Internal/external walls and fence Painting
8.15 | Slab Concrete Ground floor (under tiles)
8.16 | Toilet floor Ceramic
8.17 | Toilet wall Ceramic
8.18 | Septic Tank
8.19 | false ceiling (60*60 cm)
8.2 | Aluminum Door
8.21 | PVC Doors
Students WC Construction Part 2) PLUMBING WORK
9.1 | wall-mounted western toilet
9.2 | Installing eastern toilet
9.3 | Installing wall-mounted handwash basins with water mixer
9.4 | Water Taps 1/2"
9.5 | Water Tank
9.6 | PVC reinforced Manhole
9.7 | Rainwater downpipes
9.8 | PVC or PP sewerage pipes DN 100 (4)” diameter
9.9 | Water pipes connections "Galvanized pipes" Dia. 3/4"
9.1 | Polypropylene PPR cold/warm water supply pipes Dia. 1/2"
Students WC Construction Part 3) Electrical Works
10.1 | Lighting Fixture Led 18 Watt for WCs
10.2 | Electric air ventilator
10.3 | Switch Socket, 13 A, 230 V AC
10.4 | Out door wall lamp fixtures Lighting Fixture Led 50 Watt
10.5 | Solar warm water heater 200 liter