TERMS OF REFERENCE FOR FINAL EVALUATION OF

AHLAN SIMSIM-IRAQ (AS-I) PROGRAM FOR NCREASING RESILIENCE CAPACITIES FOR CONFLICT AFFECTED POPULATION

- INTRODUCTION AND BACKGROUND OF THE PROJECT

BACKGROUND

Save the Children is the world's leading independent organization for children, working in over 120 countries around the world. It’s a child rights-based organization guided by a Child Safeguarding Policy where it aims to ensure that anyone associated with the organization behaves appropriately towards children, never abuses the position of trust that comes with being a part of the Save the Children family, and will respond appropriately to issues of child abuse and the sexual exploitation of children. Save the Children’s mission is to inspire breakthroughs in the way the world treats children, and to achieve immediate and lasting change in their lives. Save the Children envisions a world in which every child attains the right to survival, protection, development, and participation.

Operational in Iraq since 1991, Save the Children is among the largest international NGOs in Iraq responding to multi-sectorial humanitarian, recovery, and development needs of children and their families – including Iraqis displaced by conflict, Syrian refugees, and host communities. Save the Children seeks to meet the basic and immediate needs of children and their families through programmes in child protection, education, MHPSS, WASH, and livelihoods in five governorates across central and northern Iraq: Diyala, Dohuk, Kirkuk, Ninewa, and Salah al-Din. We do this by operating directly on the ground, targeting those most in need, establishing strong relationships with communities, NGO actors, and local government bodies, so as to ensure sustainable and lasting impact.

## PROGRAM DESCRIPTION

In partnership with the United States Agency for International Development/Iraq (USAID−Iraq), Sesame Workshop (SW) leads the consortium together with Mercy Corps (MC) and Save the Children International (SCI) to implement a program called Ahlan Simsim-Iraq (AS-I).

The overall goal of the program states that: Families and communities impacted by conflict and violence create and participate in inclusive Early Childhood Development (ECD) opportunities and have increased resilience capacities that help to counter malign influences. The activity uses a multi-generation, integrated and layered approach targeting children, families, teachers, and youth in Anbar, Baghdad, Basrah, Kirkuk, Ninewa, and Salah-al-Din.

Ahlan Simsim-Iraq intended to leverage Ahlan Simsim’s unique approach that combines locally driven, crisis-sensitive, and age-appropriate interventions to increase resilience capacities among children, families, and communities impacted by conflict and violence. To achieve its overall goal, the activity implemented a combination of approaches, including; original multimedia that promotes inclusion and reflects the diversity of Iraqi society; direct services that reduce the vulnerability of children; and youth engagement programming that lays the foundation for self-efficacy and participation. AS-I is designed to help USAID reach its goal of contributing to a stable, sovereign Iraq that can respond in a timely and transparent manner to the needs of its citizens.

Save the Children International proposed a 29-month partnership with Sesame Workshop to implement the SO1 and SO2 of the Ahlan Simsim-Iraq program across Anbar, Baghdad, Basrah, Kirkuk, Ninewa, and Salah-al-Din Governorates. In line with Ahlan Simsim’s results framework, the proposed intervention focused on bellow Ahlan Simsim’s Strategic Objectives targeting children ages 3-8 years Children from marginalized communities including Religious and Ethnic Minorities (REM), their families, and educators.

SO1: Children have improved foundational skills.

IR 1.1 Improved social and emotional skills

IR 1.2 Improved learner readiness

IR 1.3 Increased appreciation for identity, self, and other.

SO2: Facilitators have improved effectiveness.

IR 2.1 Teachers implement evidence-based learner readiness and psychosocial support strategies (PSS)

IR 2.2 Increased appreciation for diversity and inclusion.

To achieve these Strategic Objectives, the intervention coordinated with the Ministry of Education (MoE) and its directorates in Baghdad, Basra, Ninawa, Kirkuk, Salah al-Din, and Anbar and Ninewa established two ECCD centers in each governorate targeted conflict-affected and vulnerable children and their families.

# Project Summary

| Type of evaluation | Final Evaluation |
| --- | --- |
| Name of the program | Ahlan Simsim-Iraq (AS-I) |
| Program Start and End dates | November 2021-March 2024 |
| Program duration | 3 Years |
| Program locations: | Basra, Baghdad, Anbar, Ninewa and Kirkuk and Salah Al Deen Iraq |
| Thematic areas | Education |
| Sub themes | Basic Education and Early Childhood Development |
| Donor | USAID-Sesame Workshop (SW) |
| Overall objective of the project | Families and communities impacted by conflict and violence create and participate in inclusive ECD opportunities and have increased resilience capacities that help counter malign influence |

Beneficiaries Categories

| Activity | Target Beneficiaries |
| --- | --- |
| Children ages 3-8 Years old directly reached through teaching and learning materials (TLMs) along with Social and emotional learning (SEL) and Early Literacy and Math (ELM). | 17,00 |
| Parents and caregivers reached through ELM at home sessions including AS-I Videos | 616 |
| Educators/Facilitators/Education supervisors | 96 |
| Parent-Teacher Association (PTA) Members | 170 |
| Teacher Learning Circle (TLC) members | 71 |
| Father Engagement Events on ECCD | 180 |
| None-beneficiaries (Controle group) | TBD |

OBJECTIVE OF THE PROJECT

The project strives to strengthening resilience capacity of the local community through implementation of inclusive ECCD activities through

- Improvement of children foundational skills

- Facilitators have improved effectiveness

- Youth have asset and agency

- Improvement of quality and relevance (through data and evidence).

The expected results of the project are:

  - Improved social and emotional skills;

- Improve learner readiness;

- Increase appreciation for diversity and inclusion

- Teachers implement evidence based learner readiness and PSS strategies

- Informed strategic collaboration

- Output and delivery informed by MEL

- Adaptation approach include feedback loops

- Increased appreciation for identify, self and others

- Improved soft skills (implemented by MC)

- Improved skills in story telling and media capacities (implemented by MC)

Increased meaningful and inclusive engagement (implemented by MC)

- PURPOSE AND SPECIFIC OBJECTIVES OF THE EVALUATION

Purpose:

Save the Children International (SCI) is seeking for an external consultant to design and carry out a final summative evaluation of AHLAN SIMSIM-IRAQ program that targets Anbar, Baghdad, Basrah, Kirkuk, Ninewa, and Salah-al-Din Governorates,

to assess the performance of the project, expected outcomes, identify factors that contributed to success or failure, and evaluate the validity of underlying theories and assumptions used in the program development. The findings of the evaluation will inform any future iterations of the program and influence the agency’s overall learning and growth. Save the Children intends to use the findings of this evaluation to organize reflection sessions with key program stakeholders – including local partners – as well as current and potential funding. In addition, the findings will inform the design and implementation of future SCI’s ECCD Sector programs in Iraq and similar contexts.

Specific Objectives:

- Assess the results and progress of the AS-I project in terms of effectiveness (achieved outcomes) and the efficiency of implementation (output achieved against inputs and budget (resources) used).

- Assess the level of partnership with relevant government entities and the target community's involvement in decision-making processes and resource allocation.

- Identify evidence of project strengths (including successful innovations and promising practices) and weaknesses (factors impeding progress) in program planning, design, implementation, M&E, and community ownership and local authorities.

- Assess the impacts of the project on children and their families, identifying gaps and causes that deter the project from effectively addressing their wellbeing.

- Evaluate the program's engagement and benefits for vulnerable groups (gender, marginalized groups, children, and the disabled) throughout the project lifecycle.

- Evaluate the functionality and effectiveness of SW educational videos integration approach and implementation modality

- Draw constructive lessons and document new knowledge from the entire project development process and provide specific, actionable, and practical recommendations for focus on key sectors for future similar actions.

Evaluation criteria and key questions

The evaluation will assess the performance and impacts of the program against the main OECD DAC evaluation criteria of relevance, effectiveness, efficiency, coherence, and sustainability.

The following criteria will guide the key questions to be asked

- Relevance:

- To what extent the program design responded to the needs of children in the targeted areas

- How well did programmes’s response meet the needs of the affected children and their families, and affected community members?

- How well did the program adapt to changing needs over time?

- To what extent was programme able to adapt and provide appropriate response to context changes and emerging local needs, and the priorities of beneficiaries?

- Effectiveness:

- Were the planned benefits delivered and received, as perceived by all key stakeholders?

- What were the major factors influencing the achievement of the objectives of the project?

- What opportunities for collaboration have been, utilized and how have these contributed to increased effectiveness? or otherwise?

- To what extent were the SW videos effective for facilitators in areas of SEL, MRU and social cohesion.

- Efficiency:

- How well did the various activities transform the available resources into the intended outputs, in terms of quantity, quality and timeliness?

- What are the recommendations regarding appropriate resource requirements – human, financial, technical and support services?

- Was the project activity implementation (modality), considered to have been cost-efficient, while not compromising quality?

- Response coverage: T

- What, extent have the project beneficiaries been reached and what mechanisms were in place to improve coverage?

- Coordination:

- How well did SC and partner plans complement those of other NGOs and or government?

- How has the coordination and engagement with MOE and DOE contributed to achieving the intended results?

- Sustainability:

- Will the changes caused by this program  continue beyond the life of the programme?

- What, mechanisms have, Save the Children, and partners put in place to sustain the key program Outputs and Outcomes?

How has the program worked with local partners to increase their capacity in a sustainable way?

- PROPOSED EVALUATION METHODOLOGY

An external consultancy firm or team of consultants will be responsible for conducting the outcome evaluation. The firm/team is expected to conduct a desk review of relevant project documents (external and internal) and monitoring reports/data, meet with senior management, program staff, partners, and relevant stakeholder, and participate in consultation and debriefing meetings. The firm/team is then expected to develop a detailed methodology, appropriate data collection tools, and a detailed data analysis plan. Any quantitative survey should include a sample size calculation that will render the results statistically valid. Discussions on the sample size and proposed tools are to be shared with the MEAL Team before the commencement of the actual fieldwork.

The consultant will be expected to include a mix of quantitative and qualitative data collection methods such as surveys, focus group discussions, key informant interviews, and field observation visits. Triangulation of data through different tools and sources is considered necessary.

- The following is the potential list of methods that SC expects the consultant to use in order to answer evaluation questions. The list is non-exhaustive, and others may be suggested. Key Informant Interviews (KIIs): In-depth interviews will be conducted with key informants who possess extensive knowledge and experience of the programme. These individuals will be selected from the targeted governorates to gain a comprehensive perspective. Whenever possible, female KIIs will be included to ensure a balanced representation of viewpoints.

- Focus Group Discussions (FGDs): FGDs will be conducted with children who have benefited from various project services over the past years. These discussions will aim to measure the positive outcomes and impacts of key project activities on children's personal and family well-being. The FGDs will be conducted in a child-friendly and age-appropriate manner, ensuring that all For this evaluation three methodologies will be included

- Data Collection Methods: A comprehensive data collection strategy will be employed to gather evidence and assess the project's impact from multiple perspectives:

- Interviews with Parents and Teachers: In-depth interviews will be conducted with parents and teachers from project-supported schools and ECCD centers to gain insights into the project's impact on children's learning, well-being, and overall school environment. The interviews will also focus on the involvement of parents and teachers in the project's implementation and their perceptions of its effectiveness.

- Stakeholder Interviews: Semi-structured interviews will be conducted with key stakeholders at various levels, including: These interviews will focus on the overall implementation of the project, including its design, synergies, integration with other similar programs, and complementarities in the intervention areas.

- Field Visits and Community Interviews: Field visits will be conducted to the project's operational areas, and community interviews will be held with parents and teachers (PTAs). These interactions will provide direct observations of project activities and community participation. Additionally, observations of the structures developed through the project will be conducted to assess their functionality and impact.

- Presentation of Findings: A final, approved report summarizing the evaluation findings will be presented to key staff at Save the Children's Erbil Office. This presentation will provide an opportunity for discussion, feedback, and recommendations for future programming.

## Ethical Considerations

It is expected that this study will be:

- Child participatory. Where appropriate and safe, children should be supported to participate in the evaluation process beyond simply being respondents. Opportunities for collaborative participation could include involving children in determining success criteria against which the project could be evaluated, supporting children to collect some of the data required for the evaluation themselves, or involving children in the validation of findings. Any child participation, whether consultative, collaborative or child-led, must abide by the 9 Basic Requirements for meaningful and ethical child participation.

- Inclusive. Ensure that children from different ethnic, social and religious backgrounds have the chance to participate, as well as children with disabilities and children who may be excluded or discriminated against in their community.

- Ethical: The study must be guided by the following ethical considerations:

  - Safeguarding – demonstrating the highest standards of behaviour towards children and adults.

  - Sensitive – to child rights, gender, inclusion and cultural contexts.

  - Openness - of information given, to the highest possible degree to all involved parties.

  - Confidentiality and data protection - measures will be put in place to protect the identity of all participants and any other information that may put them or others at risk.

  - Public access - to the results when there are not special considerations against this

  - Broad participation - the relevant parties should be involved where possible.

  - Reliability and independence - the study should be conducted so that findings and conclusions are correct and trustworthy.

It is expected that:

- Data collection methods will be age and gender appropriate.

- Study activities will provide a safe, creative space where children feel that their thoughts and ideas are important.

- A risk assessment will be conducted that includes any risks related to children, young people’s, or adult’s participation.

- A referral mechanism will be in place in case any child safeguarding or protection issues arise.

- Informed consent will be used where possible.

- EXPECTED OUTPUTS

- Detailed Proposal for Work: A comprehensive proposal outlining the evaluation methodology, work plan, evaluation matrix, and timeline of activities

- Draft Report for Review: A draft report prepared in MS Word format for review by Save the Children, adhering to the provided reporting template

- Presentation of Findings and Results: A presentation summarizing the evaluation findings and results, following the agreed-upon reporting template

- Knowledge Translation Materials: A PowerPoint presentation encapsulating the key findings of the study

- Summary infographics highlighting the essential takeaways

- An Evidence to Action Brief (2-4 pages) concisely summarizing the full report, utilizing the Save the Children Management Response template

- Final Report Submission: The final report in electronic format, including any databases generated from fieldwork

- Hard copies of the final report and any associated databases

- All documents prepared in MS Word format

- Electronic submission of all documents via email to the Save the Children Program Manager

- Copies of all PowerPoint presentations used for project briefings, provided to Save the Children in editable digital format

- ROLES AND RESPONSIBILITIES

An external consultant, who will be recruited, according to the Save the Children external consultancy policy guidelines, will conduct the evaluation. The Program Manager will be responsible for the overall process of the consultancy while relevant thematic leads or relevant technical advisors and MEAL team will be responsible for technical backstopping the evaluation team on the methodology, ensuring that the evaluation task becomes a learning and sharing process among stakeholders.

  - RESPONSIBILITIES OF THE CONSULTANT

- Submit technical and financial proposal with clear statement of the proposed methodologies.

- Submit inception report in line with the ‘inception report template’.

- Establish contacts with pre-identified organizations and explaining the objective of the work.

- Lead consultations with all informants of the evaluation.

- Administer data collection, data entry and analysis of questionnaires and key informant interviews.

- Review of relevant documents and literature.

- Provide reports as per the pre-agreed reporting template and timeframe of the evaluation.

  - RESPONSIBILITIES of Save the Children

- Provide relevant documents produced by or used for the project

- Ensure involvement of government stakeholders as a members of the evaluation team and also informants

- Provide transport to and from areas of the study

- Facilitate consultations with the relevant informants

- Ensure lists of contacts in areas of the study are shared

- Arrange translators, when necessary

- Provide necessary information, documents

- Review the draft report and provide feedback to the consultant in line with the agreed timeframe

- Disburse payment of the service as per the contract agreement.

Add on evaluation budget (without mentioning the budget) but mention what costs the consultant is expected to cover. Especially travelling, accommodation, reporting, enumerators etc. during field work

- REPORT STRUCTURE

Report should have the following structure:

- Executive Summary

- Background description of the Program and context relevant to the Study

- Scope and focus of the study

- Overview of the study methodology and data collection methods, including a Study matrix

- Findings aligned to each of the key Study questions

- Specific caveats or methodological limitations of the evaluation

- Conclusions outlining implications of the findings or learnings

- Recommendations

- Annexes including tools used, people contacted, etc

- Total report should not exceed 30 pages

## MANAGEMENT OF THE EVALUATIOM

| What | Who is responsible | By when | Who else is involved |
| --- | --- | --- | --- |
| Share project documents with consultant | PM and MEAL Coordinator | 15th of January 2024 | MEAL Coordinator and PM |
| Documentation review, desk research | Consultant | 23rd of January 2024 | Consultant |
| Inception report | Consultant | 31st of January 2024 | Consultant |
| Review of inception report | MEAL team and PM | 12th of Feb 2024 | Technical advisors, MEAL Coordinator |
| Data collection | Consultant | 29th of Feb 2024 | Consultant and MEAL Team |
| Data management and analysis (coding, transcriptions, data cleaning, integration and analysis) | Consultant | 15th of March 2024 | Consultant |
| First draft of the Final study report | Consultant | 25th of March 2024 | Consultant |
| Review and validation of the draft report | MEAL team, PM and TAs | 8th of April 2024 | SCI & Consultant and TAs |
| Validation of study findings and recommendations | SC Project Manager/MEAL | 15th of April 2024 | SC MEAL staff, Technical advisor |
| Final study report and submission of data and analyses | SC Project Manager/MEAL | 30th of April | SC MEAL staff, Technical advisor |

Save the Children seeks value for money in its work. This does not necessarily mean "lowest cost", but quality of the service and reasonableness of the proposed costs. Proposals shall include personnel allocation (role / number of days / daily rates / taxes), as well as any other applicable costs.

# SCHEDULE OF PAYMENT

The following payments will be made to the consultant using and agreed mode of payment

- Upon approval of inception report and evaluation tools: [30%]

- Upon submission of the first draft study report: [30%]

- Upon approval of the final evaluation report: [40%]

## LEVEL OF ACCESS TO CHILDREN

The consultant will have access to the children in the field while discussing their needs and interests in the schools and in the communities. The consultant is required to sign and adhere to the Save the Children Child Safeguarding; Protection from Sexual Exploitation and Abuse; Anti-Harassment, Intimidation and Bullying; and Data Protection and Privacy policies throughout all the evaluation activities.

- SELECTION CRITERIA

Interested consultants will be required to submit an Expression of Interest in line with the provided template, which should demonstrate adherence to the following requirements:

- Advanced degree related with development studies, education, protection and governance

- At least 10 years of working/research/study/evaluation experience on humanitarian and/or development work of similar action of similar scopes using mixed approaches in multiple sectors such as Education and Child protection

- Sound and proven experience in conducting evaluations based on OECD-DAC evaluation criteria, particularly utilization and learning focused evaluations to education and protection

- Leading evaluations or consultancy work in Iraq or similar settings in humanitarian and recovery contexts;

- Experience of conducting ethical and inclusive studies involving children and child participatory techniques;

- Experience of conducting ethical and inclusive studies involving marginalized, deprived and/or vulnerable groups in culturally appropriate and sensitive ways;

- Managing and coordinating a range of government, non-government and  community groups;

- Strong written and verbal skills in communicating technical and/ or complex findings to non-specialist audiences (especially report writing and presentation skills);

- A track record of open, collaborative working with clients.

## Submission of proposalS

In response to these terms of reference, potential consultants are requested to submit online using the link provided by Save the Children. The technical proposal should outline methodology, study instrument, task assignment of staff members, detailed work plan and so on. Recent and detailed curriculum vitae of proposed staff, and other supporting documents (an example of previous research reports from similar work including Save the Children if any) should be annexed.

If interested in applying for this study, please refer to the Consultant EOI Form. For more information, you may reach out using the following address: xxxx@savethechildren.org.

- Deadline for submission

Proposals should be submitted on XX January 2024 till 4:00pm using the online link provided for the submission of the expression of Interest (EOI).

=====/////=======

Annexes (only the first four Annexes to be shared with the potential consultants)

  - Expression of Interest application template

  - Inception report template

  - Reporting template

  - SCI Evaluation Scoring for perspective consultants (on the report submission)

| Category | Evaluation Quality Criteria (used for internal scoring after completion of the report) |
| --- | --- |
| Purpose, Design and Methods | 1. Does the evaluation report clearly identify the evaluation's purpose (including its key objectives, questions and criteria) as set out in the evaluation's Terms of Reference (ToR)? |
|  | 2. Are the data collection and analysis methods a clearly justified approach to addressing the evaluation's purpose and questions? (Do they provide valid, reliable and ethical data?) |
|  | 3. Is the methodology suitably tailored to the context and population groups to which the evaluation questions relate (e.g. re gender, disability, socio-economic status, geographic location, cultural context, ethnicity)? |
|  | 4. Is the size and composition of the sample in proportion to the conclusions sought by the evaluation? |
|  | 5. Does the evaluation build on what is already known, for example existing tried and tested frameworks and tools, existing data/evidence, and previous lessons learned? |
|  | 6. Are the methods used to collect and analyse data and any limitations of the quality of the data and collection methodology explained and justified? |
|  | 7. Has any personal and professional influence or potential bias among those collecting or analysing data been recorded and addressed or mitigated ethically? |
| Analysis and Findings | 8. If evaluating impact, is a point of comparison used to show that change has happened (eg. a baseline, a counterfactual, comparison with a similar group)? |
|  | 9. Is the explanation of how (e.g. theory of change, logframe, activities) the intervention contributes to change explored? |
|  | 10. Is the data well triangulated, such as by using different data collection methods, types of data and stakeholder perspectives? |
|  | 11. Are alternative factors (eg. the contribution of other actors) considered to explain the observed result alongside an intervention’s contribution? |
|  | 12. Are unintended and unexpected changes (positive or negative) identified and explained? |
|  | 13. Are the perspectives of children & communities included in the evidence, including the most deprived and marginalised? Note: For evaluations focused on young children, caregiver perspectives are adequate instead. |
|  | 14. Are the findings disaggregated according to sex, disability and other relevant social differences? |
|  | 15. Is there a clear logical link between the data that was collected and analysed, and the conclusions and recommendations presented? |
|  | 16. Are conflicting findings and divergent perspectives presented and explained in the analysis and conclusions? |
|  | 17. Are the findings and conclusions of the assessment shared with and validated by a range of key stakeholders (eg. communities, partners, Save the Children staff)? |
| Communication and Use | 18. Is the analysis and interpretation of the data well communicated through accessible language and helpful visuals (diagrams, graphs, tables as needed)? |
|  | 19. Are references, annexes and links included that provide additional relevant data, analysis or references (including key documents and which individuals/stakeholders were involved)? |
|  | 20. Is there a clear plan for how to use the results, including recommendations that are 'SMART' (Specific, Measurable, Achievable, Relevant, Timebound) and directed toward the appropriate 'end users', a dissemination plan, and specific actions for implementing these recommendations? |

| ToR prepared by: |  |
| --- | --- |
| ToR approved by: |  |
| Date of sign off: |  |

If any Consultancy Service Provider, Freelancer or Contingent worker will have direct contact with children and/or vulnerable adults and/or beneficiaries and/or have access to any sensitive data on safeguarding and/or children and/or beneficiaries, it is the responsibility of the person receiving the consulting service to contact the local HR team and child safeguarding focal point to ensure vetting checks and on-boarding are conducted in line with statutory requirements, local policies and best practices guidance.