## Customs building Rehabilitation
Detailed WORK PLAN Customs building Rehabilitation / Baghdad
Activity No. | Activity Description | Plan Start | Plan End | Duration (Days) | Resources (Man power) | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4
Activity: | Customs building Rehabilitation / Baghdad |  |  |  |  | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4
Customs building/Part 1) Civil works
1.1 | Ceramic Removal
1.2 | Partition Removal
1.3 | Walls/ Door Opening
1.4 | Wall Door/Partitions Closing
1.5 | Marble tiles (European origin)
1.6 | Granite Tiles
1.7 | Gypsum board partition
1.8 | Internal Plastering
1.9 | Walls Cover and Decoration (Wood)
1.1 | Roof Decoration
1.11 | Internal/external walls Painting
1.12 | Wall Marble (Travertine)
1.13 | Acoustic false ceiling (60*60 cm)
1.14 | Glass Seperators
1.15 | Building Façade
1.16 | Natural Stone (Halan) for Windows frame
1.17 | Main Safe Door
1.18 | Aluminum Door (1.3*2) m
1.19 | Aluminum Door (1.8*2) m
1.2 | External Steel Doors (for the entrances)(1.8*2 m)
1.21 | Aluminum windows
1.22 | Interior Wooden Door
Customs building/Part Part 2) Fire Fighting extinguishers
2.1 | Powder type fire extinguisher
2.2 | CO2 type fire extinguisher
Customs building/Part 3) Electrical Works
3.1 | Sub-Distribution board 12 lines
3.2 | Led Panel 60 Watt for false ceiling
3.3 | indoor light 6 Watt
3.4 | Magnetic ruler directed lights
3.5 | LED lights (linear profile)
3.6 | Outdoor light 20 Watt
3.7 | Projector light
3.8 | Switch Socket, 13 A, 230 V AC
3.9 | Air cooler device (1 Ton)
3.1 | Air cooler device (5 Ton)
3.11 | AC 4 Ton cassette
3.12 | 4*35 mm cable connection
Total Duration/Days